## Eng_Proc_Cons
Category | Actual progress | Baseline Percentage Forecast
Engineering | 54% | 55%
Procurement | 9% | 9%
Construction and assembly works | 7% | 3%
Commissioning | 0% | 0%