## EC decision
|  |  | wprowadzone do budżetu |  |  | NIEBIESKIE WRZUCONE NA DBA - obustronnie podpisane
| Budget | Measurement | Decision number | Technical scope - short | Technical scope - details | Subcontractor / Subvendor | SAP vendor number | Amount | Budget position | Date of decision | Date of Order | P.O. number | nr zam po migracji | Podpisy EC | Zamówienie/Umowa/Aneks status | Czy dodano do PSa? | Nr poz. PS | PCW
|  |  | ECD no. 1 | MON plates | Purchase of MON plates 1000 x 469,00 | BUDIZOL | 2703715 | 469000 | 5.1.1 - indirect cost 5.3.1 - indirect cost | 2025-12-05 | contract | 4502902128 |  | signed | nie dotyczy | TAK |  | Roger
|  |  | ECD no. 2 | Container rental | Rental of office containers, two-month period | CONTAINEX | 1015276 | 4080 | 3.1.1 - indirect cost | 2025-12-08 | 2025-12-15 | 4502914369 |  | signed | sig 2 | TAK
|  |  | ECD no. 3 | Rental of a crane | Rental of a crane for shoveling | BUDIZOL | 2703715 | 962 | 2.2.1 - indirect cost | 2025-12-08 | 2025-12-15 | 4502914407 |  | signed | sig 2 | TAK
|  |  | ECD no. 4 | Security | Security | SOLID SECURITY | 1173360 | 563696.81 | 4.6.1 - indirect cost | 2025-12-08 | contract | 4502939860 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 5 | WATER INSTALLATION | WATER INSTALLATION | KRZYŚ | 1177960 | 151500 | 3.18 - indirect cost 2.5.1 - indirect cost | 2025-12-29 | contract | 4502939080 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 6 | SURVEYOR | SURVEYOR | GEOBET | 2711518 | 505550 | 4.8 - indirect cost 2.5.2 - indirect cost | 2025-12-29 | contract | 4502939075 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 7 | Power supply installation |  | EL-MAR | 2723781 | 737000 | 5.2 - indirect cost | 2025-12-29 | contract | 4502939085 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 8 | organization of the opening meeting |  | KaBo | 2723802 | 6277.78 | 3.9.1 - indirect cost | 2026-01-12 | 2026-01-13 | 4502940616 |  | signed |  | TAK
|  |  | ECD no. 9 | FURNITURE RENTAL | FURNITURE RENTAL | MEBLORENT | 1172175 | 99632 | 3.16 - indirect cost 3.17 - indirect cost | 2026-01-12 | 2026-01-15 | 4502943059 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 10 | Hourly assistant construction workers |  | Adam Kujawka | 2723644 | 361500 | 6.6.1 - indirect cost | 2026-01-13 |  | 4502948806 |  | signed | nie dotyczy | TAK
|  |  | ECD no.11 | Hourly assistant construction workers |  | Grzegorz Kujawka | 1161233 | 361500 | 6.6.2 - indirect cost | 2026-01-13 |  | 4502948820 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 12 | municipal waste |  | SANIKO | 1173364 | 50000 | 3.2.1 - indirect cost | 2026-01-15 | 2026-01-15 | 4502943626 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 13 | Building and detailed design of the GPO/GPZ station |  | MENOS | 2723655 | 390000 | 1.2.5.1 - direct cost | 2026-01-15 | 2026-01-15 | 4502943755 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 14 | kruszywo |  | MAT BUD | 1170959 | 232320 | 3.19 - indirect cost 4.10 - indirect cost 5.3 - indirect cost 5.2.0 - indirect cost 2.5 - indirect cost | 2026-01-19 | 2026-01-07 | 4502934293 |  | signed | zrobić dec zmniejszającą rev 1 | TAK | 8.7.1.3
|  |  | ECD no. 15 | transport | WYNAJEM BIURA | SILOGISTIC | 1177984 | 2500 | 2.2 - indirect cost | 2026-01-19 | 2026-01-19 | 4502946426 |  | signed | sig 3 | TAK
|  |  | ECD no. 9 rev 1 | FURNITURE RENTAL | FURNITURE RENTAL | MEBLORENT | 1172175 | 95272 | 3.16 - indirect cost 3.17 - indirect cost | 2026-01-12 | 2026-01-15 | 4502943059 |  | signed | nie dotyczy | TAK
|  |  | ECD no. 16 | FENCE |  | PORR/PES |  | 97440 | 5.5 - indirect cost | 2026-01-20 | contract |  |  | signed |  | TAK
|  |  | ECD no. 17 | MOBILE TOILETS | DRUKARKA | WC SERWIS | 1165297 | 26466 | 4.7 - indirect cost | 2026-01-21 | 2026-01-22 | 4502950161 |  | signed | sig 3 | TAK
|  |  | ECD no. 18 | Open order - purchase of small items |  | MAT BUD | 1170959 | 50000 | 2.3.1 - indirect cost | 2026-01-22 | 2026-01-22 | 4502950515 |  | signed | sig 3 | TAK
|  |  | ECD no. 19 | Open order - purchase of small items |  | AM TOOLS - hurtownia | 1173121 | 50000 | 2.3.2 - indirect cost | 2026-01-22 | 2026-01-22 | 4502950551 |  | signed | sig 3 | TAK
|  |  | ECD no. 20 | CONTAINERS | FENCE | PORR/PES |  | 821840 | 3.1 - indirect cost | 2026-01-26 |  |  |  | signed |  | TAK | 8.2.1.1
|  |  | ECD no. 21 | woda |  | MPWIK | 1173249 | 66880 | 4.3 - indirect cost | 2026-01-26 | contract | 4502972410 |  | signed | nie dotyczy | TAK | 8.2.5.1
|  |  | ECD no. 22 | kamera |  | SETCON | 2723982 | 16616.25 | 6.2 - indirect cost | 2026-01-26 | 2026-01-30 | 4502957582 |  | signed | sig 3 | TAK | 8.8.2
|  |  | ECD no. 23 | wynajem sali konferencyjnej |  | HOTEL ALEKSANDER | 2721717 | 1340 | 3.9.2 - indirect cost | 2026-01-28 | 2026-01-28 | 4502955423 |  | signed |  | TAK | 8.2.1.5
|  |  | ECD no. 24 | WYNAJEM BIURA |  | STALER MARKET | 1173773 | 7278 | 3.1 - indirect cost | 2026-01-28 | contract | 4502952746 |  | signed |  | TAK | 8.2.1.6
|  |  | ECD no. 25 | piezometr |  | GEOTEST | 2717751 | 13280 | 6.3 - indirect cost | 2026-01-28 | contract | 4502956394 |  | signed |  | TAK | 8.6.2.1
o |  |  | ECD no. 26 | prąd |  | MPEC | 2724539 | 50000 | 3.3 - indirect cost | 2026-01-29 | contract | 4503016221 |  | signed |  | TAK | 8.2.3.1
|  |  | ECD no. 5 rev 1 | WATER INSTALLATION |  | KRZYŚ | 1177960 | 21000 | 2.5 - indirect cost | 2026-01-29 | contract | 4502939080 |  | signed |  | TAK | 8.5.4
|  |  | ECD no. 27 | Integrated permit consultant |  | ZAKŁAD SOZOTECHNIKI | 2724068 | 113000 | 1.2.7 - direct cost | 2026-02-02 | contract | 4502966963 |  | signed |  | TAK | 1.2.7.1
|  |  | ECD no. 14 rev 1 | kruszywo |  | MAT BUD | 1170959 | 230307 | 3.19 - indirect cost 4.10 - indirect cost 5.3 - indirect cost 5.2.0 - indirect cost 2.5 - indirect cost | 2026-02-04 | contract | 4502934293 |  | signed | nie dotyczy | TAK | 8.7.1.3
|  |  | ECD no. 7 rev 1 | Power supply installation |  | EL-MAR | 2723781 | 135000 | 5.2 - indirect cost | 2026-02-04 | contract | 4502939085 |  | signed |  | TAK | 8.7.2.1
|  |  | ECD no. 28 | coffee machine rental |  | COFFEE PARTNER | 1178896 | 50000 | 3.9 - indirect cost | 2026-02-10 | contract | 4502960536 |  | signed |  | TAK | 8.2.9.1
|  |  | ECD no. 29 | drinking water machine rental |  | AQUAMO | 1163845 | 8500 | 4.2 - indirect cost | 2026-02-04 | contract | 4502960520 |  | signed |  | TAK | 8.2.4.1
|  |  | ECD no. 15 rev 1 | transport |  | SILOGISTIC | 1177984 | 2500 | 2.2 - indirect cost | 2026-02-04 | 2026-01-19 | 4502946426 |  | signed | sig 3 | TAK | 8.7.2.2
|  |  | ECD no. 30 | time lapse camera installation |  | ARBO-DRWAL | 2724141 | 1463.41 | 6.2 - indirect cost | 2026-02-10 | 2026-02-12 | 4502971778 |  | signed | sig 3 | TAK | 8.8.2.2
|  |  | ECD no. 31 | laboratory services |  | BARG | 1164058 | 181560 | 2.5.1 - direct cost 4.9 - indirect cost | 2026-02-10 | contract | 4502968920 |  | signed |  | TAK | 8.6.2.2 - 49 500,00 PLN 2.5.1.5 - 132 060,00 PLN
|  |  | ECD no. 32 | Open order - office supplies |  | ABIS | 1166292 | 90000 | 3.7 - indirect cost | 2026-02-10 | - | - |  | signed |  | TAK | 8.2.7.1
|  |  | ECD no. 33 | tv |  | AV KREATOR | 2714226 | 11980 | 3.12 - indirect cost | 2026-02-11 | 2026-02-12 | 4502971588 |  | signed | sig 3 | TAK | 8.2.11.1
|  |  | ECD no. 34 | tymczasowa organizacja ruchu |  | PROJBUD | 2724138 | 950 | 8.1 - direct cost | 2026-02-11 | 2026-02-12 | 4502971480 |  | signed | sig 3 | TAK | 8.7.1.5
|  |  | ECD no. 35 | cleaning services |  | CERBER | 2724173 | 178200 | 3.8 - indirect cost | 2026-02-16 | contract | 4502976093 |  | signed |  | TAK | 8.2.8.1
|  |  | ECD no. 36 | office kitchen furniture |  | MIRRO | 2724168 | 13414.64 | 3.17 - indirect cost | 2026-02-17 | 2026-02-17 | 4502975895 |  | signed | sig 3 | TAK | 8.5.2.2
|  |  | ECD no. 37 | internet |  | THORNET | 1173693 | 27350 | 3.14 - indirect cost 3.12 - indirect cost | 2026-02-20 | 2026-02-23 | 4502980811 |  | signed | sig 3 | TAK | 8.5.1
|  |  | ECD no. 38 | construction waste |  | PREZERO | 2719396 | 290720 | 4.5 - indirect cost | 2026-02-20 | contract | 4502980901 |  | signed |  | TAK | 8.3.5
|  |  | ECD no. 15 rev 2 | transport |  | SILOGISTIC | 1177984 | 2400 | 2.2 - indirect cost | 2026-02-23 |  | 4502946426 |  | signed | sig 3 | TAK | 8.7.2.2
|  |  | ECD no. 39 | open order - sanitary industry assortment |  | INSTALNOVA | 1179835 | 30000 | 4.2 - indirect cost | 2026-02-24 | 2026-02-24 | 4502983881 |  | signed | sig 3 | TAK | 8.1.3.3
|  |  | ECD no. 40 | open order - sanitary industry assortment |  | ATMOMAT | 2724093 | 30000 | 3.8 - indirect cost | 2026-02-24 | 2026-02-24 | 4502983951 |  | signed | sig 3 | TAK | 8.1.3.4
|  |  | ECD no. 30 rev 1 | time lapse camera installation |  | ARBO-DRWAL | 2724141 | 336.59 | 6.2 - indirect cost | 2026-02-26 | 2026-02-12 | 4502971778 |  | signed | sig 3 | TAK | 8.8.2
|  |  | ECD no. 41 | design office - technological equipment |  | ODS | 2724336 | 943000 | 1.2.2 - direct cost 2.6.1 - direct cost | 2026-03-02 | contract | 4502993588 |  | signed |  | TAK | 1.2.2
|  |  | ECD no. 42 | road signs |  | DROG-ZNAK | 1172865 | 2000 | 6.3 - indirect cost | 2026-03-03 | 2026-03-03 | 4502992375 |  | signed | sig 3 | TAK | 8.7.1
|  |  | ECD no. 15 rev 3 | transport |  | SILOGISTIC | 1179834 | 1400 | 2.2 - indirect cost | 2026-03-05 | 2026-01-19 | 4502946426 |  | signed | sig 3 | TAK | 8.7.2.2
|  |  | ECD no. 43 | personal OHS equipment | Osobisty sprzęt BHP | PROSAVE | 1162319 | 30000 | 6.5 - indirect cost | 2026-03-09 |  |  |  | signed | zamówienie generowane z ariby | TAK | 8.4.1
|  |  | ECD no. 44 | generator rental | Wynajem generatorów | MOBIL SERWIS | 1176915 | 23904 | 2.2 - indirect cost | 2026-03-12 | 2026-03-12 | 4503007260 |  | signed | sig 3 | TAK | 8.3.1
|  |  | ECD no. 45 | concrete rubble |  | Usługi Sprzętowo - Transportowe Sławomir Boruczkowski | 2724506 | 83200 | 2.1 - direct cost | 2026-03-16 | 2026-03-16 | 4503011598 | 4503104333 | signed | sig 3 | TAK | 8.7.1
|  |  | ECD no. 46 | crushed aggregate |  | KSM Parsęcko | 1178892 | 134400 | 2.14.2 - direct cost | 2026-03-16 | contract | 4503012737 |  | signed |  | TAK | 2.14.2.2
|  |  | ECD no. 15 rev 4 | transport |  | SILOGISTIC | 1177984 | 500 | 2.2 - indirect cost | 2026-03-19 |  | 4502946426 |  | signed | sig 3 | TAK | 8.7.2.2
|  |  | ECD no. 14 rev 2 | kruszywo |  | MAT BUD | 1170959 | 25305.58 | 5.5 - indirect cost | 2026-03-23 |  | 4502934293 |  | signed |  | TAK | 8.7.1.3
|  |  | ECD no. 47 | HAZOP, ATEX, SIL analyses |  | UDT CERT | 1038145 | 214974 | 1.4 - direct cost | 2026-03-23 | contract | 4503027816 |  | signed |  | TAK | 1.4
|  |  | ECD no. 48 | TAS stairs |  | TLC Rental | 1166722 | 17 530,00 PLN | 5.5 - indirect cost | 2026-04-07 | 2026-04-09 | 4503050386 |  | signed | sig 3 | TAK | 8.1.1
|  |  | ECD no. 49 | pompa drenażowa - wynajem |  | PPHU Klaudia | 1167377 | 4600 | 2.2 - indirect cost | 2026-04-10 | 2026-04-15 | 4503061913 |  | signed | sig 2 | TAK | 2.3
|  |  | ECD no. 50 | drainage |  | HAMER | 2718641 | 70 000,00 PLN | 2.3 - direct cost | 2026-04-16 | contract | 4503066286 |  | signed |  | TAK | 2.3
|  |  | ECD no. 51 | izolacja przeciwwodna |  | TWS Sp. z o.o. | 2724996 | 31352 | 2.4 - direct cost | 2026-04-20 | contract | 4503071267 |  | signed | sig 3 | TAK | 2.4
|  |  | ECD no. 14 rev 3 | materials for the insulation of foundations | materiały do izolacji fundamentów | MAT BUD | 1170959 | 27600 | 2.4 - direct cost | 2026-04-21 | contract | 4502934293 |  | signed |  | TAK | 2.4
|  |  | ECD 7 rev 2 | Power supply installation |  | EL-MAR | 2723781 | 17000 | 5.2 - indirect cost | 2026-04-22 | contract | 4502939085 |  | signed |  | TAK | 8.7.2.1
|  |  | ECD no. 2 rev 1 | Container rental |  | CONTAINEX | 1015276 | 720 | 3.1 - indirect cost | 2026-04-24 | 2025-12-15 | 4502914369 |  | signed |  | TAK
|  |  | ECD no. 15 rev 5 | transport |  | SILOGISTIC | 1177987 | 2500 | 2.2 - indirect cost | 2026-04-24 |  | 4502946426 |  | signed |  | TAK | 8.7.2.2
|  |  | ECD no. 52 | oznakowanie poziome i pionowe | oznakowanie poziome i pionowe | ZNAKTOM | 3200651 | 920 | 5.5 - indirect cost | 2026-04-24 | 2026-05-22 | 4503121343 |  | signed |  | TAK | 8.7.1.8
|  |  | ECD no. 53 | lunches | obiady | Michelin | 2723938 | 5711 | 2.1 - indirect cost | 2026-04-30 |  |  |  | signed |  | TAK | 8.1.1
|  |  | ECD no. 54 | gas network renovation | Renowacja sieci gazowej | P.W. Markopol | 3200502 | 16000 | 4.11 - indirect cost | 2026-05-05 | contract |  |  | signed |  | TAK | 8.8.4.2
|  |  | ECD no. 55 | access control | dodatkowa kontrola dostępu | SOLID SECURITY | 1173360 | 5418 | 4.6.2 - indirect cost | 2026-05-14 | 2026-05-15 | 4503103862 |  | signed
|  |  | ECD no. 53 rev 1 | lunches |  | Michelin | 2723938 | 5233.54 | 2.1 - indirect cost | 2026-05-15 |  |  |  | signed
|  |  | ECD no. 51 rev 1 | izolacja przeciwwodna |  | TWS Sp. z o.o. | 2724996 | 46983 | 2.4 - direct cost | 2026-05-18 | contract | 4503071267 |  | signed
|  |  | ECD no.50 rev 1 | drainage |  | HAMER | 2718641 | 35000 | 2.3 - direct cost | 2026-05-18 | contract | 4503066286 |  | signed
|  |  | ECD no. 56 | transport |  | Frogstrans | 3200708 | 2700 | 2.2 - indirect cost | 2026-05-19 | 2026-05-22 | 4503121690 |  | signed
|  |  | ECD no. 9 rev 2 | office furniture |  | MEBLORENT | 1172175 | 4410 | 3.17 - indirect cost | 2026-05-19 | 2026-01-15 | 4502943059 |  | signed
|  |  | ECD no. 54 rev 1 | gas network renovation |  | P.W. Markopol | 3200502 | 0 | - | 2026-05-22 | - | - |  | signed
|  |  | ECD no. 56 rev 1 | transport |  | Frogstrans | 3200708 | 5000 | 2.2 - indirect cost
|  |  | ECD no. 2 rev 2 | Container rental |  | CONTAINEX | 1015276 | 660 | 3.1 - indirect cost
|  |  |  | equipment rental |  | PES
|  |  |  | bony Sodexo |  |  |  | 2000
|  |  |  | DRUKARKA |  |  |  |  | od 01.26
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: STRATA
Note on M11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wprowadzono ale rozliczenie przez kkg na 618510900
Note on M12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gm 2201020
Note on M19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gm 2201020
Note on I33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zmniejszenie kwoty o 48
Note on I67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budżet 1150802 Reply: Zmiana kwoty na decyzji na 720
Note on I68: Author: 55 834,00
Note on I69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 199772,42 budżet
Note on M451: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hej, Edi zostawmy to już tak – nie wycofujmy. Z poważaniem Monika Mazurkiewicz Kierownik ds. ekonomicznych projektu From: Cyran Edyta <edyta.cyran@porr.pl> Sent: Monday, March 10, 2025 2:02 PM To: Mazurkiewicz Monika <m.mazurkiewicz@porr.pl> Subject: FW: [EXTERN]R: ITPOE_2 Rzeszów ECD no 272 – KRAJ Monia, Tą decyzję mam wycofać rewizją tak i kwota wróci do budżetu? Bo to miało tak zostać zrobione jak będzie ta decyzja na zamówienia otwarte.
Note on M455: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ECR no 58 1 550 000,00 PLN 05.07.2024 ECR no 58 rev_1 55 493,70 PLN 10.10.2024 ECD no 225 75 337,00 PLN 20.11.2024 ECD no 235 15 544,20 PLN 09.12.2024 ECD no 236 110 000,00 PLN 09.12.2024 ECD no 275 26 500,00 PLN 20.02.2025 ECD no 276 13 000,00 PLN 20.02.2025 1 845 874,90 PLN
Note on P466: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zmniejszenie zamówienia
Note on M508: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zmiana kontrahenta, patrz ECD 309 rev 1
Note on P514: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zmniejszenie zamówienia, nie wykorzystano
Note on P517: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mazurkiewicz Monika <m.mazurkiewicz@porr.pl> Sent: Wednesday, April 2, 2025 10:34 AM To: Potyra Rafal <rafal.potyra@porr.pl> Cc: Cyran Edyta <edyta.cyran@porr.pl>; Krzemien Justyna <justyna.krzemien@porr.pl> Subject: RE: rewizja decyzji Cześć, Faktury rozliczane w NKUP (imprezy, spotkania itd.) rozliczane są w brutto bo od nich nie możemy odliczyć VATu.