## 00_Report
Wloclawek - Waste-to-Energy Project Dashboard Report
Generato: 2026-05-12 10:44 |  |  |  | Budget: Budget.xlsm
Report aggiornato al momento del download: i dati derivano dai file Excel presenti in data/current.
KPI | Value | KPI | Value
Budget 0 (col. I) |  | Budget attuale (col. AB)
Delta AB - I |  | Delta %
Ordini chiusi ultimi 3 mesi |  | Prossimi ordini 3 mesi
Milestones penalizzate |  | Da ordinare / Planned
Curva S degli ordini rispetto al pianificato |  |  |  |  | Totale ordinato / da ordinare / negoziazione

## 01_Budget_Delta
Budget Delta - Totale e WBS
I dati sono linkati al foglio 07_Source_Budget_Delta. Budget 0 = colonna I del Budget; Budget attuale = colonna AB; Delta AB-I e Delta % sono formule.
Budget 0 - col. I | Budget attuale - col. AB | Delta AB-I | Delta %
Section | WBS | Description PL | Description EN | Budget 0 - col. I | Budget attuale - col. AB | Delta AB-I | Delta %

## 02_PORR_Production
Month | PORR declared production / Budget monthly | Cumulative
Year | Annual total declared
2025
2026
2027
2028

## 03_Milestones
Nota logica
Le milestone qui riportate sono considerate “penalizzate” perché sono classificate nella sezione “Milestones penalizzate” del file Programma Wloclawek_Milestones.xlsx. Non è un calcolo automatico della penale scattata: indica milestone contrattualmente soggette a penale / penalizzabili.
No. | Milestone | Start date | Finish date
1 | Water pressure test | 2027-10-16 | 2027-10-16
2 | Placement of the turbo-generator on the foundation | 2027-09-16 | 2027-09-16
3 | Measurement of guaranteed parameters A | 2028-06-23 | 2028-06-23
4 | Handover of the ITPO project to operation | 2028-06-30 | 2028-06-30

## 04_Orders_3M
Type | WBS | Package | Status | Date | Value | Buyer

## 05_Status_Mix
Status group | Count | Value | Percentage

## 06_S_Curve_Data
Month | Label | Procurement monthly | Procurement cumulative | Budget monthly | Budget cumulative | Contracted monthly | Contracted cumulative | Current marker

## 07_Source_Budget_Delta
Nota origine dati
Dati estratti dal file Budget in data/current: Budget.xlsm, sheet Włocławek Budget. Totale Budget 0 = cella I12; Budget attuale = cella AB12. La tabella WBS sotto riporta le righe top-level trovate in colonna A: WBS 1-8 della sezione costi diretti e WBS 1-17 della sezione riepilogo/finanziaria. I valori Budget 0 e Budget attuale derivano rispettivamente dalle colonne I e AB; Delta e Delta % sono formule nel report.
Metric | Value | Source file | Source sheet | Source cell
Budget 0 - col. I | 505343424 | Budget.xlsm | Włocławek Budget | I12
Budget attuale - col. AB | 501457852.9912 | Budget.xlsm | Włocławek Budget | AB12
Section | WBS | Description PL | Description EN | Budget 0 - col. I | Budget attuale - col. AB | Delta AB-I | Delta % | Source row | Source cells
Direct cost / root budget group | 1 | PROJEKTOWANIE | DESIGN | 30550000 | 27169999.9971 |  |  | 13 | I13 / AB13
Direct cost / root budget group | 2 | Roboty branży budowlano-konstrukcyjnej | Civil works | 113409768 | 108109766.9919 |  |  | 38 | I38 / AB38
Direct cost / root budget group | 3 | BRANŻA ELEKTRYCZNA | ELECTRICAL WORKS | 10912000 | 58345340 |  |  | 143 | I143 / AB143
Direct cost / root budget group | 4 | Roboty branży sanitarnej i ppoż | Sanitary works and fire-fighting system | 34223555 | 21293319.0015 |  |  | 160 | I160 / AB160
Direct cost / root budget group | 5 | Roboty branży mechanicznej i technologicznej | Mechanical and technological works | 293798902 | 258666645.9992 |  |  | 185 | I185 / AB185
Direct cost / root budget group | 6 | Zimny i gorący rozruch, Ruch próbny instalacji technologicznych | Cold and hot commissioning & Trial run of technological equipment | 8499199 | 8499999.9971 |  |  | 257 | I257 / AB257
Direct cost / root budget group | 7 | Wyrównanie do wartości z TCO / Rezerwa | Alignment to TCO values / Backup | 0 | 538352 |  |  | 276 | I276 / AB276
Direct cost / root budget group | 8 | Pozostałe koszty |  | 0 | 414429 |  |  | 279 | I279 / AB279
Financial summary / WBS 1-17 | 1 | TKW |  | 505757853 | 501457852.9912 |  |  | 283 | I283 / AB283
Financial summary / WBS 1-17 | 1 | PERSONEL | STAFF | 0 | 0 |  |  | 290 | I290 / AB290
Financial summary / WBS 1-17 | 2 | TKW Razem | Direct + indirect costs | 546148867.15 | 563915104.8631 |  |  | 428 | I428 / AB428
Financial summary / WBS 1-17 | 3 | Kwota narzutów kalkulacyjnych |  | 85237132.85 | 63170895.14 |  |  | 429 | I429 / AB429
Financial summary / WBS 1-17 | 4 | % narzutów kalkulacyjnych |  | 0.15607 | 0.11202 |  |  | 430 | I430 / AB430
Financial summary / WBS 1-17 | 5 | Zlecenie otrzymane/Planowany przerób |  | 631386000 | 627086000 |  |  | 440 | I440 / AB440
Financial summary / WBS 1-17 | 6 | Podwykonawstwo wewn. udzielone |  | 0 | 0 |  |  | 441 | I441 / AB441
Financial summary / WBS 1-17 | 7 | Planowany Przerób po REGIE | Planned capacity (REGIE) | 631386000 | 627086000 |  |  | 442 | I442 / AB442
Financial summary / WBS 1-17 | 8 | Korekta kosztowa wpływająca tylko na wynik |  | 0 | 0 |  |  | 445 | I445 / AB445
Financial summary / WBS 1-17 | 9 | Kwota narzutów kalkulacyjnych |  | 85237132.85 | 63170895.14 |  |  | 446 | I446 / AB446
Financial summary / WBS 1-17 | 10 | Kwota narzutów kalkulacyjnych po korekcie | Amount of imputed mark-ups after correction | 0 | 63170895.14 |  |  | 447 | I447 / AB447
Financial summary / WBS 1-17 | 11 | Alokacje - REGIE |  | 45080960.4 | 31178096.0196 |  |  | 463 | I463 / AB463
Financial summary / WBS 1-17 | 12 | EBT w PLN - po uwzględnieniu REGIE |  | 40156172.45 | 31992799.1204 |  |  | 465 | I465 / AB465
Financial summary / WBS 1-17 | 13 | % EBT bez revaluation |  | 0.0636 | 0.051018 |  |  | 466 | I466 / AB466
Financial summary / WBS 1-17 | 14 | EBT z Rewaluation |  | 40156172.45 | 54091334.2704 |  |  | 468 | I468 / AB468
Financial summary / WBS 1-17 | 15 | % EBT bez Contingency |  | 0.0636 | 0.086258 |  |  | 469 | I469 / AB469
Financial summary / WBS 1-17 | 16 | Wartość robót wykonywanych przez konsorcjantów |  | 0 | 0 |  |  | 476 | I476 / AB476
Financial summary / WBS 1-17 | 17 | Łączna wartość kontraktu (BBB + konsorcjanci) |  | 631386000 | 627086000 |  |  | 477 | I477 / AB477

## 08_Source_PORR_Production
Nota origine dati
Dati estratti dal file Budget in data/current: Budget.xlsm, sheet Włocławek Budget. La produzione mensile dichiarata PORR / budget monthly deriva dalla riga 12, colonne AM:BW; le intestazioni mese sono sulla riga 11.
Month | Value | Source cell | Source header cell
2025-12-01 00:00:00 | 6199140 | AM12 | AM11
2026-01-01 00:00:00 | 1209845.03 | AN12 | AN11
2026-02-01 00:00:00 | 4914057.77 | AO12 | AO11
2026-03-01 00:00:00 | 5765471.9428 | AP12 | AP11
2026-04-01 00:00:00 | 6905734.0931 | AQ12 | AQ11
2026-05-01 00:00:00 | 8873827.147 | AR12 | AR11
2026-06-01 00:00:00 | 10285632.2932 | AS12 | AS11
2026-07-01 00:00:00 | 10740381.9377 | AT12 | AT11
2026-08-01 00:00:00 | 11563023.0632 | AU12 | AU11
2026-09-01 00:00:00 | 16961088.6609 | AV12 | AV11
2026-10-01 00:00:00 | 20646901.9259 | AW12 | AW11
2026-11-01 00:00:00 | 16967267.5713 | AX12 | AX11
2026-12-01 00:00:00 | 19654432.3326 | AY12 | AY11
2027-01-01 00:00:00 | 27037107.2534 | AZ12 | AZ11
2027-02-01 00:00:00 | 31052003.955 | BA12 | BA11
2027-03-01 00:00:00 | 37364643.971 | BB12 | BB11
2027-04-01 00:00:00 | 32844839.1013 | BC12 | BC11
2027-05-01 00:00:00 | 34135803.9485 | BD12 | BD11
2027-06-01 00:00:00 | 28870543.177 | BE12 | BE11
2027-07-01 00:00:00 | 25137377.5264 | BF12 | BF11
2027-08-01 00:00:00 | 19034792.3265 | BG12 | BG11
2027-09-01 00:00:00 | 24283221.7612 | BH12 | BH11
2027-10-01 00:00:00 | 12421394.0622 | BI12 | BI11
2027-11-01 00:00:00 | 10204106.9827 | BJ12 | BJ11
2027-12-01 00:00:00 | 18501734.7906 | BK12 | BK11
2028-01-30 00:00:00 | 5817816.9662 | BL12 | BL11
2028-02-01 00:00:00 | 3279069.2332 | BM12 | BM11
2028-03-01 00:00:00 | 2859802.3872 | BN12 | BN11
2028-04-01 00:00:00 | 308626.9264 | BO12 | BO11
2028-05-01 00:00:00 | 3335488.4409 | BP12 | BP11
2028-06-01 00:00:00 | 966685.0738 | BQ12 | BQ11
2028-07-01 00:00:00 | 0 | BR12 | BR11
2028-08-01 00:00:00 | 0 | BS12 | BS11
2028-09-01 00:00:00 | 174000 | BT12 | BT11
2028-10-01 00:00:00 | 0 | BU12 | BU11
2028-11-01 00:00:00 | 0 | BV12 | BV11
2028-12-01 00:00:00 | 42828572.34 | BW12 | BW11

## 09_Source_Status_Mix
Nota origine e logica calcolo
Dati derivati dal file Procurement in data/current, sheet Procurement Schedule. Colonne di riferimento: Q = stato procurement, S = Budget AK / budget aggiornato, T = valore contracted quando disponibile. Raggruppamento: Closed / Finalized / PCT approval = Ordinato; Planned = Da ordinare; tutti gli altri stati attivi = In negoziazione. Count = numero pacchetti nel gruppo; Value = somma economica del gruppo; Percentage = Value gruppo / totale Value dei tre gruppi.
Status group | Count | Value | Percentage
Ordinato | 83 | 218667759.04
In negoziazione | 30 | 128599285.78
Da ordinare | 231 | 238223502.86

## 10_Source_Orders_3M
Type | WBS | Package | Status | Date | Value | Buyer
Closed last 3 months | 2.5.1.5 | Laboratory services - testing of concrete mix and hardened concrete ECd_31 | closed | 2026-02-10 | 132060
Closed last 3 months | 8.2.7.1 | Open order - office supplies ECd_32 | closed | 2026-02-10 | 90000
Closed last 3 months | 8.2.9.1 | Coffee machine rental ECd_28 | closed | 2026-02-10 | 50000
Closed last 3 months | 8.6.2.2 | Laboratory services ECd_31 | closed | 2026-02-10 | 49500
Closed last 3 months | 8.8.2.2 | Monitoring - installation of timelaps camera ECd_30 | closed | 2026-02-10 | 1800
Closed last 3 months | 8.2.11.1 | TV ECd_33 | closed | 2026-02-11 | 11980
Closed last 3 months | 8.7.1.5 | Temporary Traffic Management ECd_34 | closed | 2026-02-11 | 950
Closed last 3 months | 1.2.7.1 | Preparation of an application for an integrated permit, together with all necessary documents. | closed | 2026-02-13 | 113000
Closed last 3 months | 2.1 | Foundation works | closed | 2026-02-15 | 0
Closed last 3 months | 2.1.1 | Diaphragm wall 100 cm thick and 6 adjacent barrettes | closed | 2026-02-15 | 3176000 | Jank Szczubiał
Closed last 3 months | 2.1.2 | Slotted wall 100 cm thick and 6 berets | closed | 2026-02-15 | 1124000 | Jank Szczubiał
Closed last 3 months | 8.1.5 | Stationary Cranes | closed | 2026-02-15 | 0 | Damian Gadowski
Closed last 3 months | 8.1.5.1 | Stationary tower crane + self-erecting crane | closed | 2026-02-15 | 1170200 | Damian Gadowski
Closed last 3 months | 8.2.1.1 | Office Space or Container Rental - Consortium's facility ECd_20 | closed | 2026-02-15 | 821840 | Urszula Szwarc
Closed last 3 months | 8.2.8.1 | Cleaning services ECd_35 | closed | 2026-02-16 | 178200
Closed last 3 months | 8.5.2.2 | Office kitchen furniture ECd_36 | closed | 2026-02-17 | 13414.64
Closed last 3 months | 8.5.1 | Internet Connection ECd_37 | closed | 2026-02-20 | 27350
Closed last 3 months | 8.1.3.3 | Open order - sanitary industry assortment ECd_39 | closed | 2026-02-24 | 30000
Closed last 3 months | 8.1.3.4 | Open order - sanitary industry assortment ECd_40 | closed | 2026-02-24 | 30000
Closed last 3 months | 5.4.1 | Boiler - pressure parts | PCT/approval | 2026-02-28 | 0 | Roger Gołombek
Closed last 3 months | 5.4.1.1 | Boiler - pressure parts | PCT/approval | 2026-02-28 | 45990000 | Roger Gołombek
Closed last 3 months | 8.4.1.1 | Personal Occupational Health and Safety Equipment ECd_43 | closed | 2026-03-09 | 30000
Closed last 3 months | 8.3.1.2 | Generator rental ECd_44 | closed | 2026-03-15 | 23904
Closed last 3 months | 8.7.1.6 | Purchase of road signs ECd_42 | closed | 2026-03-15 | 2000
Closed last 3 months | 8.7.1.7 | Purchase of rubble for the construction of storage yards and work platforms ECd_45 | closed | 2026-03-15 | 83200
Closed last 3 months | 2.11.5.3 | Concrete slab installation on the ground | closed | 2026-03-25 | 1735392.78 | Agnieszka Zając
Closed last 3 months | 2.14.2.2 | External road - aggregate delivery ECd_46 | closed | 2026-03-25 | 134400 | Agnieszka Zając
Closed last 3 months | 2.4.1 | Insulation - work | closed | 2026-03-25 | 733045.25 | Agnieszka Zając
Closed last 3 months | 2.5.1.3 | Construction of reinforced concrete foundations and underground structures | closed | 2026-03-25 | 5276959.37 | Agnieszka Zając
Closed last 3 months | 2.5.2.1 | Reinforced concrete structure of the above-ground part of the B1 building - delivery and assembly of prefabricated elements | closed | 2026-03-25 | 16616880 | Jan Szczubiał
Closed last 3 months | 2.5.2.2.3 | Reinforced concrete structure of the above-ground part of the B3 building - delivery and assembly of prefabricated elements | closed | 2026-03-25 | 2115950 | Jan Szczubiał
Closed last 3 months | 2.5.2.2.4 | Reinforced concrete structure of the above-ground part of the other buildings | closed | 2026-03-25 | 708072.75 | Jan Szczubiał
Closed last 3 months | 2.6.2.1 | Precast reinforced concrete structure of facility B3 (change from steel structure compared to the acquisition stage) | closed | 2026-03-25 | 1004390 | Robert Klimczak
Closed last 3 months | 2.6.3.1 | Precast reinforced concrete structure of facility B4 (change from steel structure compared to the acquisition stage) | closed | 2026-03-25 | 246780 | Robert Klimczak
Closed last 3 months | 5.10.2 | Auxiliary crane and hoists for the maintenance of the steam turbine | PCT/approval | 2026-04-03 | 499000 | Magdalena Białorucka
Closed last 3 months | 5.2.1 | Overhead crane, grab and operator seat + Spare Grab | PCT/approval | 2026-04-03 | 8701000 | Magdalena Białorucka
Closed last 3 months | 2.14.2.1 | External road- sub-base construction | PCT/approval | 2026-04-10 | 250640 | Agnieszka Zając
Closed last 3 months | 8.3.1.1 | Electricity Costs | PCT/approval | 2026-04-10 | 100000
Closed last 3 months | 8.7.1.4 | Construction of aggregate squares | PCT/approval | 2026-04-10 | 124700 | Agnieszka Zając
Closed last 3 months | 8.8.4 | Removing collisions related to site preparation and construction | PCT/approval | 2026-04-10 | 50000
Next orders 3 months | 1.2.6 | Piping and ducts design | planned | 2026-05-15 | 2000000
Next orders 3 months | 1.2.6.2 | Piping design | planned | 2026-05-15 | 0
Next orders 3 months | 5.10.12 | Stabilising pumps 2 x 100%, network pumps 3 x 50%, condensate pumps 2 x 100%, feed water pumps 3 pcs., cooling pumps | planned | 2026-05-15 | 5517325 | Stanisław Rucki
Next orders 3 months | 5.10.3 | Air cooled condenser | planned | 2026-05-15 | 9000000 | Roger Gołombek
Next orders 3 months | 5.7.4 | Fly ash silos | planned | 2026-05-15 | 2000000 | Roger Gołombek
Next orders 3 months | 2.7 | Brick walls | planned | 2026-05-31 | 687451.25
Next orders 3 months | 3.4.3 | Emission monitoring system (CEMS) | planned | 2026-05-31 | 1960000 | Radosław Zdancewicz
Next orders 3 months | 4.1 | Deodorization system | planned | 2026-05-31 | 1009700 | Stanisław Rucki
Next orders 3 months | 4.2.1 | Fire detection and alarm system | enquiry | 2026-05-31 | 2211870 | Magdalena Białorucka
Next orders 3 months | 4.2.10 | Smoke extraction from waste bunker and tipping hall | enquiry | 2026-05-31 | 1178293 | Magdalena Białorucka
Next orders 3 months | 4.2.2 | Firefighting water tank | enquiry | 2026-05-31 | 275700 | Magdalena Białorucka
Next orders 3 months | 4.2.3 | Firefighting water pumping | enquiry | 2026-05-31 | 715920 | Magdalena Białorucka
Next orders 3 months | 4.2.4 | Firefighting water external distribution, hoses, sprinklers | enquiry | 2026-05-31 | 821016 | Magdalena Białorucka
Next orders 3 months | 4.2.5 | Installation of internal hydrants in buildings B1 and B2 | enquiry | 2026-05-31 | 240990 | Magdalena Białorucka
Next orders 3 months | 4.2.6 | Wireless radio controller system type WRC, gun control | enquiry | 2026-05-31 | 45500 | Magdalena Białorucka
Next orders 3 months | 4.2.7 | Firefighting water external distribution, hoses, sprinklers | enquiry | 2026-05-31 | 542750 | Magdalena Białorucka
Next orders 3 months | 4.2.8 | Dry bunker sprinkler system. Installation of water and foam cannons in the bunker hall, and assembly of the valve sub-control unit. | enquiry | 2026-05-31 | 1925350 | Magdalena Białorucka
Next orders 3 months | 4.2.9 | Natural gas (if any) and ammonia detection system | enquiry | 2026-05-31 | 285000 | Magdalena Białorucka
Next orders 3 months | 5.10.13.5 | Control valves | planned | 2026-05-31 | 700000 | Roger Gołombek
Next orders 3 months | 5.2.2 | Trapdoors for grab maintenance | planned | 2026-05-31 | 81600
Next orders 3 months | 5.3.6 | Primary & secondary air dampers | planned | 2026-05-31 | 220000
Next orders 3 months | 5.3.7 | Flue gas recirculation dampers | planned | 2026-05-31 | 40000
Next orders 3 months | 5.10.8 | Cooler tank, condensate tank | planned | 2026-06-15 | 1000000 | Roger Gołombek
Next orders 3 months | 5.13.4 | Auxiliary fuel pumps (light oil/diesel oil), demi water pumps, other water pumps | planned | 2026-06-15 | 3337500 | Stanisław Rucki
Next orders 3 months | 1.8 | Notification Bodies | planned | 2026-06-28 | 350000
Next orders 3 months | 5.10.11 | Heat exchangers 2 pcs., LP pre-heater, external economizer | planned | 2026-06-30 | 3242866 | Stanisław Rucki
Next orders 3 months | 5.13.3 | Light oil unloading installation with TDT documentation approval | planned | 2026-06-30 | 200000
Next orders 3 months | 5.4.4 | Sampling system | planned | 2026-06-30 | 1010500 | Magdalena Białorucka
Next orders 3 months | 5.4.5 | Chemical dosing for the boiler | planned | 2026-06-30 | 223600 | Magdalena Białorucka
Next orders 3 months | 5.7.1 | SNCR DeNOx system including silo, pumps | planned | 2026-06-30 | 1090000 | Magdalena Białorucka
Next orders 3 months | 4.3.1 | Boiler room roof ventilators and wall shutters | planned | 2026-07-15 | 1500000 | Magdalena Przeździak
Next orders 3 months | 4.3.2 | HVAC for the technological buildings | planned | 2026-07-15 | 3107033 | Magdalena Przeździak
Next orders 3 months | 4.3.3 | HVAC for the other buildings | planned | 2026-07-15 | 1548256 | Magdalena Przeździak
Next orders 3 months | 2.11.1 | Painting | planned | 2026-07-31 | 669442.8 | Magdalena Białorucka
Next orders 3 months | 2.11.10 | Plasterboard wall, sandwich panel wall | planned | 2026-07-31 | 39026.75
Next orders 3 months | 2.11.11 | Glass wall | planned | 2026-07-31 | 75045.3
Next orders 3 months | 2.11.12 | Plastering | planned | 2026-07-31 | 1241084.64 | Magdalena Białorucka
Next orders 3 months | 2.11.13 | Carpet / polyamide | planned | 2026-07-31 | 87497.52
Next orders 3 months | 2.11.14 | Wall and column protection up to 2.5 m + hydrophobic protection | planned | 2026-07-31 | 186490.48
Next orders 3 months | 2.11.2 | Furniture | planned | 2026-07-31 | 631074 | Magdalena Białorucka
Next orders 3 months | 2.11.3 | Tiles | planned | 2026-07-31 | 498448.22 | Magdalena Białorucka
Next orders 3 months | 2.11.4 | Raised floor | planned | 2026-07-31 | 621907.75 | Magdalena Białorucka
Next orders 3 months | 2.11.5 | Concrete floor + screed | enquiry | 2026-07-31 | 610629.23
Next orders 3 months | 2.11.5.4 | Concrete flooring and screed with insulation | planned | 2026-07-31 | 0
Next orders 3 months | 2.11.6 | Microcement floor | planned | 2026-07-31 | 133705.44
Next orders 3 months | 2.11.7 | Resin floor | planned | 2026-07-31 | 655174.75 | Magdalena Białorucka
Next orders 3 months | 2.11.8 | Suspended ceilings | planned | 2026-07-31 | 220670.05
Next orders 3 months | 2.11.9 | Segmented sliding wall | planned | 2026-07-31 | 65014.1
Next orders 3 months | 2.12.1 | Passenger and good elevator | enquiry | 2026-07-31 | 415350 | Izabela Malarecka
Next orders 3 months | 2.12.2 | Passenger elevator | enquiry | 2026-07-31 | 98643.6 | Izabela Malarecka
Next orders 3 months | 2.13 | Weigh bridge | planned | 2026-07-31 | 551900 | Stanisław Rucki
Next orders 3 months | 3.4.2 | DCS System | planned | 2026-07-31 | 2752000 | Roger Gołombek
Next orders 3 months | 5.1.1 | Radioactivity detector | planned | 2026-07-31 | 185000
Next orders 3 months | 5.10.6 | Chemical dossing for thermal cycle and district heating | planned | 2026-07-31 | 550000 | Magdalena Białorucka
Next orders 3 months | 5.13.9 | Grate cooling system | planned | 2026-07-31 | 731000 | Magdalena Białorucka
Next orders 3 months | 5.14.2 | Mechanical installation of technological equipment | planned | 2026-07-31 | 1500000 | Stanisław Rucki
Next orders 3 months | 5.3.4 | Primary / secondary air ducts + Flue gas recirculation ducts + Auxiliary burners ducts + Supporting structures | planned | 2026-07-31 | 2502500 | Stanisław Rucki
Next orders 3 months | 5.3.5 | Fire curtain for primary air opening | planned | 2026-07-31 | 100000 | Magdalena Przeździak
Next orders 3 months | 5.3.8 | Camera for furnace monitoring | planned | 2026-07-31 | 51600
Next orders 3 months | 5.4.6 | Compensator between boiler and ECO | planned | 2026-07-31 | 129000
Next orders 3 months | 5.5 | Refractory | planned | 2026-07-31 | 3993000 | Magdalena Białorucka

## 11_Source_S_Curve_Data
Nota origine e logica calcolo
La Curva S deriva dal dashboard payload rigenerato dai file Excel in data/current. Procurement schedule cumulativo: somma mensile/cumulata dei valori Updated Budget / Budget AK del Procurement Schedule secondo le date procurement. Budget / programma cliente cumulativo: curva mensile/cumulata letta dal Budget, riga 12, colonne AM:BW. Ordini contrattualizzati cumulativo: somma mensile/cumulata dei valori Contracted secondo le date di chiusura/contrattualizzazione disponibili nel Procurement Schedule.
Month | Label | Procurement monthly | Procurement cumulative | Budget monthly | Budget cumulative | Contracted monthly | Contracted cumulative | Current marker
2025-12 | dic-2025 | 115638522 | 115638522 | 6228403.09 | 6228403.09 | 6555096.13 | 6555096.13
2026-01 | gen-2026 | 45700071.29 | 161338593.29 | 998971.02 | 7227374.11 | 9141730.35 | 15696826.48
2026-02 | feb-2026 | 76022869.73 | 237361463.02 | 6546793.06 | 13774167.17 | 15465425.35 | 31162251.83
2026-03 | mar-2026 | 88309663.92 | 325671126.94 | 7176290.91 | 20950458.08 | 16589181.86 | 47751433.69
2026-04 | apr-2026 | 48433156 | 374104282.94 | 8113301.34 | 29063759.42 | 16046849.05 | 63798282.74
2026-05 | mag-2026 | 31458465.25 | 405562748.19 | 9941192.99 | 39004952.41 | 15938082.38 | 79736365.12 | Current
2026-06 | giu-2026 | 10454466 | 416017214.19 | 11449359.64 | 50454312.05 | 20061023.47 | 99797388.59
2026-07 | lug-2026 | 25450493.63 | 441467707.82 | 11945534.53 | 62399846.58 | 20061023.47 | 119858412.06
2026-08 | ago-2026 | 19976583.62 | 461444291.44 | 12793266.68 | 75193113.26 | 13709940.11 | 133568352.17
2026-09 | set-2026 | 2700000 | 464144291.44 | 18322466.44 | 93515579.7 | 13709940.11 | 147278292.28
2026-10 | ott-2026 | 6370804.95 | 470515096.39 | 22031641.2 | 115547220.9 | 13709940.11 | 160988232.39
2026-11 | nov-2026 | 21614194 | 492129290.39 | 18303188.07 | 133850408.97 | 10641303.74 | 171629536.13
2026-12 | dic-2026 | 11742140 | 503871430.39 | 20973541.61 | 154823950.58 | 10641303.74 | 182270839.87
2027-01 | gen-2027 | 0 | 503871430.39 | 28459243.85 | 183283194.43 | 10438307.09 | 192709146.96
2027-02 | feb-2027 | 0 | 503871430.39 | 32669974.5 | 215953168.93 | 9518307.09 | 202227454.05
2027-03 | mar-2027 | 350000 | 504221430.39 | 38835536.12 | 254788705.05 | 9518307.09 | 211745761.14
2027-04 | apr-2027 | 9497187.35 | 513718617.74 | 34214344.15 | 289003049.2 | 9518307.09 | 221264068.23
2027-05 | mag-2027 | 0 | 513718617.74 | 35498343.67 | 324501392.87 | 3351809.77 | 224615878
2027-06 | giu-2027 | 0 | 513718617.74 | 30198471.72 | 354699864.59 | 3351809.77 | 227967687.77
2027-07 | lug-2027 | 100000 | 513818617.74 | 26418793.52 | 381118658.11 | 3278672.27 | 231246360.04
2027-08 | ago-2027 | 0 | 513818617.74 | 20336129.45 | 401454787.56 | 3278672.27 | 234525032.31
2027-09 | set-2027 | 150000 | 513968617.74 | 25382232.36 | 426837019.92 | 3278672.27 | 237803704.58
2027-10 | ott-2027 | 0 | 513968617.74 | 13522659.03 | 440359678.95 | 3278672.27 | 241082376.85
2027-11 | nov-2027 | 0 | 513968617.74 | 11192771.95 | 451552450.9 | 1558196.07 | 242640572.92
2027-12 | dic-2027 | 4375494 | 518344111.74 | 19445695.76 | 470998146.66 | 1545664.07 | 244186236.99
2028-01 | gen-2028 | 0 | 518344111.74 | 6648799.1 | 477646945.76 | 1499751.03 | 245685988.02
2028-02 | feb-2028 | 0 | 518344111.74 | 3975051.37 | 481621997.13 | 1499751.03 | 247185739.05
2028-03 | mar-2028 | 0 | 518344111.74 | 3638072.61 | 485260069.74 | 1499751.03 | 248685490.08
2028-04 | apr-2028 | 187000 | 518531111.74 | 1168312.87 | 486428382.61 | 1499751.03 | 250185241.11
2028-05 | mag-2028 | 0 | 518531111.74 | 3965109.38 | 490393491.99 | 1499751.03 | 251684992.14
2028-06 | giu-2028 | 0 | 518531111.74 | 1532685.49 | 491926177.48 | 1499751.03 | 253184743.17
2028-07 | lug-2028 | 0 | 518531111.74 | 22455920.92 | 514382098.4 | 0 | 253184743.17
2028-08 | ago-2028 | 0 | 518531111.74 | 429440.19 | 514811538.59 | 0 | 253184743.17
2028-09 | set-2028 | 0 | 518531111.74 | 252357.31 | 515063895.9 | 0 | 253184743.17
2028-10 | ott-2028 | 0 | 518531111.74 | 49117.31 | 515113013.21 | 0 | 253184743.17
2028-11 | nov-2028 | 0 | 518531111.74 | 49117.31 | 515162130.52 | 0 | 253184743.17
2028-12 | dic-2028 | 0 | 518531111.74 | 48439555.36 | 563601685.88 | 0 | 253184743.17