## Eng_Proc_Cons
Category | Actual progress | Baseline Percentage Forecast
Engineering | 41% | 41%
Procurement | 5% | 6%
Construction and assembly works | 2% | 2%
Commissioning | 0% | 0%