## Executive Summary
Wloclawek - Waste-to-Energy Project Dashboard
Report combinato Curva S + Procurement Schedule
Generato: 2026-04-24T07:54:17 |  |  | Budget file: Budget.xlsm |  |  | Procurement file: Procurement.xlsx
Overall status | AT RISK | Updated Budget | 520024051.92 | Baseline Budget | 501457852.99 | Contracted | 253185495.51
Completion % | 42.05 | Variance % | 3.7 | Contract prep. count | 15 | Packages overdue | 8
Executive note
Main risk today: 2.5.1.1 Supply of reinforcing steel is overdue by 114 days with 2432900 PLN still exposed.

## S_Curve_Data
Month | Label | Proc Monthly | Proc Cumulative | Proc % | Budget Monthly | Budget Cumulative | Budget % | Current Marker
2025-12 | dic-2025 | 115638522 | 115638522 | 22.3 | 6228403.09 | 6228403.09 | 1.11
2026-01 | gen-2026 | 45700071.29 | 161338593.29 | 31.11 | 998971.02 | 7227374.11 | 1.28
2026-02 | feb-2026 | 76022869.73 | 237361463.02 | 45.78 | 6546793.06 | 13774167.17 | 2.44
2026-03 | mar-2026 | 88309663.92 | 325671126.94 | 62.81 | 7176290.91 | 20950458.08 | 3.72
2026-04 | apr-2026 | 48433156 | 374104282.94 | 72.15 | 8113301.34 | 29063759.42 | 5.16 | Current
2026-05 | mag-2026 | 31458465.25 | 405562748.19 | 78.21 | 9941192.99 | 39004952.41 | 6.92
2026-06 | giu-2026 | 10454466 | 416017214.19 | 80.23 | 11449359.64 | 50454312.05 | 8.95
2026-07 | lug-2026 | 25450493.63 | 441467707.82 | 85.14 | 11945534.53 | 62399846.58 | 11.07
2026-08 | ago-2026 | 19976583.62 | 461444291.44 | 88.99 | 12793266.68 | 75193113.26 | 13.34
2026-09 | set-2026 | 2700000 | 464144291.44 | 89.51 | 18322466.44 | 93515579.7 | 16.59
2026-10 | ott-2026 | 6370804.95 | 470515096.39 | 90.74 | 22031641.2 | 115547220.9 | 20.5
2026-11 | nov-2026 | 21614194 | 492129290.39 | 94.91 | 18303188.07 | 133850408.97 | 23.75
2026-12 | dic-2026 | 11742140 | 503871430.39 | 97.17 | 20973541.61 | 154823950.58 | 27.47
2027-01 | gen-2027 | 0 | 503871430.39 | 97.17 | 28459243.85 | 183283194.43 | 32.52
2027-02 | feb-2027 | 0 | 503871430.39 | 97.17 | 32669974.5 | 215953168.93 | 38.32
2027-03 | mar-2027 | 350000 | 504221430.39 | 97.24 | 38835536.12 | 254788705.05 | 45.21
2027-04 | apr-2027 | 9497187.35 | 513718617.74 | 99.07 | 34214344.15 | 289003049.2 | 51.28
2027-05 | mag-2027 | 0 | 513718617.74 | 99.07 | 35498343.67 | 324501392.87 | 57.58
2027-06 | giu-2027 | 0 | 513718617.74 | 99.07 | 30198471.72 | 354699864.59 | 62.93
2027-07 | lug-2027 | 100000 | 513818617.74 | 99.09 | 26418793.52 | 381118658.11 | 67.62
2027-08 | ago-2027 | 0 | 513818617.74 | 99.09 | 20336129.45 | 401454787.56 | 71.23
2027-09 | set-2027 | 150000 | 513968617.74 | 99.12 | 25382232.36 | 426837019.92 | 75.73
2027-10 | ott-2027 | 0 | 513968617.74 | 99.12 | 13522659.03 | 440359678.95 | 78.13
2027-11 | nov-2027 | 0 | 513968617.74 | 99.12 | 11192771.95 | 451552450.9 | 80.12
2027-12 | dic-2027 | 4375494 | 518344111.74 | 99.96 | 19445695.76 | 470998146.66 | 83.57
2028-01 | gen-2028 | 0 | 518344111.74 | 99.96 | 6648799.1 | 477646945.76 | 84.75
2028-02 | feb-2028 | 0 | 518344111.74 | 99.96 | 3975051.37 | 481621997.13 | 85.45
2028-03 | mar-2028 | 0 | 518344111.74 | 99.96 | 3638072.61 | 485260069.74 | 86.1
2028-04 | apr-2028 | 187000 | 518531111.74 | 100 | 1168312.87 | 486428382.61 | 86.31
2028-05 | mag-2028 | 0 | 518531111.74 | 100 | 3965109.38 | 490393491.99 | 87.01
2028-06 | giu-2028 | 0 | 518531111.74 | 100 | 1532685.49 | 491926177.48 | 87.28
2028-07 | lug-2028 | 0 | 518531111.74 | 100 | 22455920.92 | 514382098.4 | 91.27
2028-08 | ago-2028 | 0 | 518531111.74 | 100 | 429440.19 | 514811538.59 | 91.34
2028-09 | set-2028 | 0 | 518531111.74 | 100 | 252357.31 | 515063895.9 | 91.39
2028-10 | ott-2028 | 0 | 518531111.74 | 100 | 49117.31 | 515113013.21 | 91.4
2028-11 | nov-2028 | 0 | 518531111.74 | 100 | 49117.31 | 515162130.52 | 91.41
2028-12 | dic-2028 | 0 | 518531111.74 | 100 | 48439555.36 | 563601685.88 | 100

## Orders_Status
Order mix
Bucket | Count | Value | Share %
Ordinato | 83 | 218667759.04 | 24.1
In negoziazione | 30 | 128599285.78 | 8.7
Da ordinare | 231 | 238223502.86 | 67.2
Ordini in chiusura
WBS | Package | Status | Updated Budget | Date
5.4.1.1 | Boiler - pressure parts | PCT/approval | 49332010.78 | 2026-02-28
5.2.1 | Overhead crane, grab and operator seat + Spare Grab | PCT/approval | 9072785 | 2026-04-03
5.4.1 | Boiler - pressure parts | PCT/approval | 5000000 | 2026-02-28
8.2.1 | Office Space or Container Rental | PCT/approval | 1148500 | 2025-12-31
5.10.2 | Auxiliary crane and hoists for the maintenance of the steam turbine | PCT/approval | 300000 | 2026-04-03
Specifiche emesse
WBS | Package | Status | Updated Budget | Date
3.3 | GPO/GPZ power supply | enquiry | 13510000 | 2026-08-31
5.10.1 | Steam turbine - gear box - generator. Including accessories: oil system, coolers, insulation, pipes and valves, control panel, protection panel, synchro system etc. | negotiation | 13374290 | 2026-04-30
2.10 | Roofs | enquiry | 7198646.13 | 2026-03-31
5.4.2 | Boiler - supporting structure including walkways | enquiry | 6374146.52 | 2026-03-15
2.5.1 | Reinforced concrete foundation structure | enquiry | 4299513.5 | 2026-02-20

## Direct_Packages
WBS | Package | Status | Buyer | Category | Baseline Budget | Updated Budget | Contracted | Variance | Deadline Closing | Overdue Days
1 | DESIGN |  |  |  | 27170000 | 0 | 0 | -27170000 |  | 0
1.1 | TME design | closed |  | 2 | 9890000 | 9890000 | 9890000 | 0 | 2025-12-04 | 0
1.2 | Detailed architectural, structural, sanitary and road designs |  |  | 2 | 100000 | 0 | 0 | -100000 |  | 0
1.2.1 | Detailed architectural, structural, sanitary and road designs | closed |  | 2 | 12100000 | 12200000 | 12100000 | 100000 | 2025-12-31 | 0
1.2.2 | Detailed design: boiler support steel structure and equipment support structures | contract prep. |  | 2 | 500000 | 943000 | 943000 | 443000 | 2026-02-27 | 56
1.2.3 | Detailed design: fire-fighting system | planned |  | 2 | 260000 | 260000 | 0 | 0 |  | 0
1.2.4 | Electrical & I/C detailed design | contract prep. |  | 2 | 1580000 | 1580000 | 1620000 | 0 |  | 0
1.2.5 | Building and detailed design of the GPO/GPZ station | contract prep. |  | 2 | 50000 | 440000 | 390000 | 390000 |  | 0
1.2.5.1 | Building and detailed design of the GPO/GPZ station |  |  |  | 390000 | 0 | 0 | -390000 |  | 0
1.2.6 | Piping and ducts design | planned |  | 2 | 2000000 | 2000000 | 0 | 0 |  | 0
1.2.6.1 | Ducts design | planned |  | 2 | 0 | 0 | 0 | 0 |  | 0
1.2.6.2 | Piping design | planned |  | 2 | 0 | 0 | 0 | 0 |  | 0
1.2.7 | Other documentation, opinions, agreements, permits, provisions, approvals and decisions necessary for the design, execution of the Works and commissioning of the investment (concession documentation for the generation of electricity and heat from a renewable energy source, ITPOE operating permit, integrated permit, geological designs and documentation, commissioning designs, operating instructions, etc.). | planned |  | 2 | 187000 | 187000 | 0 | 0 |  | 0
1.2.7.1 | Preparation of an application for an integrated permit, together with all necessary documents. | closed |  | 2 | 113000 | 113000 | 113000 | 0 | 2026-02-13 | 0
1.3 | Noise Analysis and noise protection design | planned |  | 2 | 100000 | 100000 | 0 | 0 |  | 0
1.4 | HAZOP study and SIL analysis | contract prep. |  | 2 | 35026 | 250000 | 214974 | 214974 | 2026-03-21 | 34
1.4.1 | HAZOP study and SIL analysis |  |  |  | 214974 | 0 | 0 | -214974 |  | 0
1.5 | Fire safety instructions | planned |  | 2 | 100000 | 100000 | 0 | 0 |  | 0
1.6 | Explosion hazard assessment | planned |  | 2 | 120000 | 120000 | 0 | 0 |  | 0
1.7 | Technical Consultant for certification and for complying with European Directives | planned |  | 2 | 100000 | 100000 | 0 | 0 |  | 0
1.8 | Notification Bodies | planned |  | 2 | 350000 | 350000 | 0 | 0 |  | 0
1.9 | Translations (Polish / English) | planned |  | 2 | 250000 | 250000 | 0 | 0 |  | 0
1.10 | NC Rfg certification | planned |  | 2 | 150000 | 150000 | 0 | 0 |  | 0
1.11 | Obtaining decisions and permits | closed |  | 2 | 0 | 17000000 | 17400000 | 17000000 | 2025-12-04 | 0
2 | Civil works |  |  |  | 108109766.99 | 0 | 0 | -108109766.99 |  | 0
2.1 | Foundation works | closed |  | 2 | 0 | 313087.02 | 0 | 313087.02 | 2026-02-15 | 0
2.1.1 | Diaphragm wall 100 cm thick and 6 adjacent barrettes | closed | Jank Szczubiał | 2 | 229887 | 3176000 | 3176000 | 2946113 | 2026-02-15 | 0
2.1.2 | Slotted wall 100 cm thick and 6 berets | closed | Jank Szczubiał | 2 | 0 | 1124000 | 1124000 | 1124000 | 2026-02-15 | 0
2.1.3 | Beret 19 pcs |  |  |  | 0 | 0 | 0 | 0 |  | 0
2.1.4 | Gruz betonowy ECD 45 |  |  |  | 83200 | 0 | 0 | -83200 |  | 0
2.2 | Earthworks | closed |  | 2 | 0 | 0 | 0 | 0 | 2026-01-15 | 0
2.2.1 | Working platform for foundation works | closed | Agnieszka Zając | 2 | 176673 | 2686634.05 | 2328438.49 | 2509961.05 | 2026-01-15 | 0
2.2.2 | Earthworks |  |  |  | 2196542 | 0 | 0 | -2196542 |  | 0
2.2.3 | Earthworks – backfilling of retaining wall |  |  |  | 313419 | 0 | 0 | -313419 |  | 0
2.3 | Drainage | enquiry |  | 2 | 437599 | 437599.45 | 0 | 0.46 |  | 0
2.4 | Insulation | enquiry |  | 2 | 403973 | 403973.38 | 0 | 0.38 |  | 0
2.4.1 | Insulation - work | closed | Agnieszka Zając | 2 | 735000 | 735000 | 733045.25 | 0 | 2026-03-25 | 0
2.4.2 | Insulation - supply | enquiry |  | 1 | 0 | 0 | 0 | 0 |  | 0
2.5.1 | Reinforced concrete foundation structure | enquiry |  | 2 | 5117413.3 | 4299513.5 | 0 | -817899.8 |  | 0
2.5.1.1 | Supply of reinforcing steel | contract prep. | Robert Klimczak | 1 | 33680.7 | 2432900 | 2432900 | 2399219.3 | 2025-12-31 | 114
2.5.1.1.1 | Supply of reinforcing steel |  |  |  | 1821319 | 0 | 0 | -1821319 |  | 0
2.5.1.1.2 | Badanie betonu |  |  |  | 132060 | 0 | 0 | -132060 |  | 0
2.5.1.1.3 | Roboty żelbetowe |  |  |  | 5500000 | 0 | 0 | -5500000 |  | 0
2.5.1.2 | Supply of concrete mix with pumping service | contract prep. | Alicja Romanowska | 1 | 3420000 | 3160000 | 3152493.51 | -260000 | 2026-02-15 | 68
2.5.1.3 | Construction of reinforced concrete foundations and underground structures | closed | Agnieszka Zając | 2 | 0 | 5500000 | 5276959.37 | 5500000 | 2026-03-25 | 0
2.5.1.4 | Execution of pre-wall insulation | enquiry |  | 2 | 0 | 500000 | 0 | 500000 |  | 0
2.5.1.5 | Laboratory services - testing of concrete mix and hardened concrete ECd_31 | closed |  | 2 | 0 | 132060 | 132060 | 132060 |  | 0
2.5.2.1 | Reinforced concrete structure of the above-ground part of the B1 building - delivery and assembly of prefabricated elements | closed | Jan Szczubiał | 2 | 0 | 18708793.99 | 16616880 | 18708793.99 | 2026-03-25 | 0
2.5.2.1.1 | Reinforced concrete structure of the above-ground part of the B1 building - delivery and assembly of prefabricated elements |  |  |  | 18708794 | 0 | 0 | -18708794 |  | 0
2.5.2.2 | Reinforced concrete structure of the above-ground part of the remaining buildings, including prefabricated elements | enquiry | Agnieszka Zając | 2 | 990112 | 591078.21 | 0 | -399033.79 |  | 0
2.5.2.2.1 | Supply of reinforcing steel | contract prep. | Robert Klimczak | 1 | 750000 | 219700 | 219700 | -530300 | 2025-12-31 | 114
2.5.2.2.2 | Supply of concrete mix with pumping service / above-ground part of buildings | contract prep. | Alicja Romanowska | 1 | 0 | 140000 | 132735.32 | 140000 | 2026-02-15 | 68
2.5.2.2.3 | Reinforced concrete structure of the above-ground part of the B3 building - delivery and assembly of prefabricated elements | closed | Jan Szczubiał | 2 | 0 | 1725869.43 | 2115950 | 1725869.43 | 2026-03-25 | 0
2.5.2.2.4 | Reinforced concrete structure of the above-ground part of the other buildings | closed | Jan Szczubiał | 2 | 0 | 750000 | 708072.75 | 750000 | 2026-03-25 | 0
2.5.2.3 | Supply of reinforcing steel | enquiry | Agnieszka Zając | 2 | 0 | 386500 | 0 | 386500 |  | 0
2.5.2.3.1 | Supply of reinforcing steel |  |  |  | 1602761 | 0 | 0 | -1602761 |  | 0
2.5.2.4 | Supply of concrete mix with pumping service | enquiry | Agnieszka Zając | 2 | 29639 | 718448.41 | 0 | 688809.41 |  | 0
2.5.2.5 | Flyover for belt conveyor |  |  |  | 386500 | 0 | 0 | -386500 |  | 0
2.5.2.6 | Retaining wall |  |  |  | 718448 | 0 | 0 | -718448 |  | 0
2.5.4.4.1 | Dostawa mieszanki betonowej wraz z usługą pompowania ECR 12 |  |  |  | 54136 | 0 | 0 | -54136 |  | 0
2.6.1 | Structure, including platforms, walkways, ladders, roofing | planned | Robert Klimczak | 2 | 21982670 | 20670885.7 | 0 | -1311784.3 |  | 0
2.6.1.1 | Detailed design: boiler support steel structure and equipment support structures |  |  |  | 443000 | 0 | 0 | -443000 |  | 0
2.6.1.2 | Konstrukcja żelbetowa części nadziemnej obiektu B1 - dostawa i montaż elementów prefabrykowanych ECR 10 |  |  |  | 1275206 | 0 | 0 | -1275206 |  | 0
2.6.2 | Steel structure of the staircase in the B1.4 facility (change from the reinforced concrete structure in relation to the acquisition stage) | planned | Robert Klimczak | 2 | 470146 | 812000 | 0 | 341854 |  | 0
2.6.2.1 | Precast reinforced concrete structure of facility B3 (change from steel structure compared to the acquisition stage) | closed | Robert Klimczak | 2 | 0 | 1400000 | 1004390 | 1400000 | 2026-03-25 | 0
2.6.3 | Gantry beams | planned | Robert Klimczak | 2 | 425469 | 124990 | 0 | -300479 |  | 0
2.6.3.1 | Precast reinforced concrete structure of facility B4 (change from steel structure compared to the acquisition stage) | closed | Robert Klimczak | 2 | 0 | 250000 | 246780 | 250000 | 2026-03-25 | 0
2.6.4 | Steel structure of the staircase in the B1.4 facility (change from the reinforced concrete structure in relation to the acquisition stage) | planned | Robert Klimczak | 2 | 0 | 470146.23 | 0 | 470146.23 |  | 0
2.6.5 | Gantry beams | planned | Robert Klimczak | 2 | 0 | 425469.43 | 0 | 425469.43 |  | 0
2.7 | Brick walls | planned |  | 2 | 687451 | 687451.25 | 0 | 0.25 |  | 0
2.8.1 | Parapet | planned | Joanna Sawicka | 2 | 82476 | 82476 | 0 | 0 |  | 0
2.8.2 | Steel-aluminum canopy | planned | Joanna Sawicka | 2 | 120923 | 120922.87 | 0 | -0.13 |  | 0
2.8.3 | Aluminum-glass facade | planned | Joanna Sawicka | 2 | 296487 | 296487.48 | 0 | 0.48 |  | 0
2.8.4 | ETICS | planned | Joanna Sawicka | 2 | 122038 | 122038.26 | 0 | 0.26 |  | 0
2.8.5 | Flashings | planned | Joanna Sawicka | 2 | 366599 | 366598.98 | 0 | -0.02 |  | 0
2.8.6 | Sheet metal cladding | planned | Joanna Sawicka | 2 | 1172887 | 1172886.87 | 0 | -0.13 |  | 0
2.8.7 | Sandwich panel cladding | planned | Joanna Sawicka | 2 | 5792280 | 5792279.88 | 0 | -0.12 |  | 0
2.8.8 | Fiber cement panel cladding | planned | Joanna Sawicka | 2 | 241171 | 241170.5 | 0 | -0.5 |  | 0
2.8.9 | Substructures | planned | Joanna Sawicka | 2 | 419580 | 419580 | 0 | 0 |  | 0
2.8.10 | Soffit lining | planned | Joanna Sawicka | 2 | 308662 | 308662.24 | 0 | 0.24 |  | 0
2.8.11 | Scaffolding | planned | Joanna Sawicka | 2 | 77076 | 77076 | 0 | 0 |  | 0
2.8.12 | Safety system | planned | Joanna Sawicka | 2 | 150018 | 150018.35 | 0 | 0.35 |  | 0
2.8.13 | Shutters | planned | Joanna Sawicka | 2 | 107601 | 107600.56 | 0 | -0.44 |  | 0
2.9 | Doors, windows, gates and hatches |  |  | 2 | 0 | 0 | 0 | 0 |  | 0
2.9.1 | Gates | planned | Magdalena Białorucka | 2 | 1169929 | 1169928.68 | 0 | -0.32 |  | 0
2.9.2 | Interior doors | planned | Izabela Malarecka | 2 | 433042 | 433041.85 | 0 | -0.15 |  | 0
2.9.3 | Exterior doors | planned | Izabela Malarecka | 2 | 164459 | 164458.64 | 0 | -0.36 |  | 0
2.9.4 | Windows | planned | Izabela Malarecka | 2 | 366536 | 366535.63 | 0 | -0.37 |  | 0
2.9.5 | Bunker windows | planned | Izabela Malarecka | 2 | 205428 | 205428.18 | 0 | 0.18 |  | 0
2.9.6 | Hatches | planned | Magdalena Białorucka | 2 | 327191 | 327190.64 | 0 | -0.36 |  | 0
2.10 | Roofs | enquiry | Joanna Sawicka | 2 | 7198646 | 7198646.13 | 0 | 0.13 |  | 0
2.11.1 | Painting | planned | Magdalena Białorucka | 2 | 669443 | 669442.8 | 0 | -0.2 |  | 0
2.11.2 | Furniture | planned | Magdalena Białorucka | 2 | 631074 | 631074 | 0 | 0 |  | 0
2.11.3 | Tiles | planned | Magdalena Białorucka | 2 | 498448 | 498448.22 | 0 | 0.22 |  | 0
2.11.4 | Raised floor | planned | Magdalena Białorucka | 2 | 621908 | 621907.75 | 0 | -0.25 |  | 0
2.11.5 | Concrete floor + screed | enquiry |  | 2 | 1631868 | 610629.23 | 0 | -1021238.77 |  | 0
2.11.5.1 | Supply of reinforcing steel | contract prep. | Robert Klimczak | 1 | 1050361 | 771600 | 771600 | -278761 | 2025-12-31 | 114
2.11.5.1.1 | Roboty żelbetowe |  |  |  | 1750000 | 0 | 0 | -1750000 |  | 0
2.11.5.2 | Supply of concrete mix with pumping service / floors, slabs on the ground | contract prep. | Alicja Romanowska | 1 | 0 | 1300000 | 1268907.17 | 1300000 | 2026-02-15 | 68
2.11.5.3 | Concrete slab installation on the ground | closed | Agnieszka Zając | 2 | 0 | 1750000 | 1735392.78 | 1750000 | 2026-03-25 | 0
2.11.5.4 | Concrete flooring and screed with insulation | planned |  | 2 | 0 | 0 | 0 | 0 |  | 0
2.11.6 | Microcement floor | planned |  | 2 | 133705 | 133705.44 | 0 | 0.44 |  | 0
2.11.7 | Resin floor | planned | Magdalena Białorucka | 2 | 655175 | 655174.75 | 0 | -0.25 |  | 0
2.11.8 | Suspended ceilings | planned |  | 2 | 220670 | 220670.05 | 0 | 0.05 |  | 0
2.11.9 | Segmented sliding wall | planned |  | 2 | 65014 | 65014.1 | 0 | 0.1 |  | 0
2.11.10 | Plasterboard wall, sandwich panel wall | planned |  | 2 | 39027 | 39026.75 | 0 | -0.25 |  | 0
2.11.11 | Glass wall | planned |  | 2 | 75045 | 75045.3 | 0 | 0.3 |  | 0
2.11.12 | Plastering | planned | Magdalena Białorucka | 2 | 1241085 | 1241084.64 | 0 | -0.36 |  | 0
2.11.13 | Carpet / polyamide | planned |  | 2 | 87498 | 87497.52 | 0 | -0.48 |  | 0
2.11.14 | Wall and column protection up to 2.5 m + hydrophobic protection | planned |  | 2 | 186490 | 186490.48 | 0 | 0.48 |  | 0
2.12.1 | Passenger and good elevator | enquiry | Izabela Malarecka | 2 | 415350 | 415350 | 0 | 0 |  | 0
2.12.2 | Passenger elevator | enquiry | Izabela Malarecka | 2 | 98644 | 98643.6 | 0 | -0.4 |  | 0
2.13 | Weigh bridge | planned | Stanisław Rucki | 2 | 551900 | 551900 | 0 | 0 |  | 0
2.14.1 | Internal road | planned | Agnieszka Zając | 2 | 4457840 | 4457840.23 | 0 | 0.22 |  | 0
2.14.2 | External road | enquiry | Agnieszka Zając | 2 | 1448126 | 1448126.27 | 0 | 0.27 |  | 0
2.14.2.1 | External road- sub-base construction | PCT/approval | Agnieszka Zając | 2 | 134400 | 250640 | 250640 | 116240 |  | 0
2.14.2.2 | External road - aggregate delivery ECd_46 | closed | Agnieszka Zając | 1 | 250640 | 134400 | 134400 | -116240 | 2026-03-25 | 0
2.14.2.3 | External road - surface layer construction | planned | Agnieszka Zając | 2 | 0 | 0 | 0 | 0 |  | 0
2.14.3 | Pavement surface | planned | Agnieszka Zając | 2 | 1112965 | 1112964.72 | 0 | -0.28 |  | 0
2.15 | Greenery | planned | Agnieszka Zając | 2 | 1097187 | 1097187.35 | 0 | 0.35 |  | 0
2.16 | Fencing | planned |  | 2 | 0 | 0 | 0 | 0 |  | 0
2.16.1 | Delivery of fences, gates and wickets | planned | Roger Gołombek | 1 | 321395 | 321394.76 | 0 | -0.24 |  | 0
2.16.2 | Installation of fences, gates and wickets | planned | Roger Gołombek | 2 | 416382 | 416382.29 | 0 | 0.29 |  | 0
3 | ELECTRICAL WORKS |  |  | 2 | 58345340 | 0 | 0 | -58345340 |  | 0
3.1.1 | Delivery and installation of electrical equipment | PCT/approval | Radosław Zdancewicz | 2 | 1700000 | 0 | 0 | -1700000 |  | 0
3.1.1.1 | Delivery and installation of electrical equipment | contract prep. | Radosław Zdancewicz | 2 | 28282000 | 28282000 | 27750000 | 0 |  | 0
3.1.1.2 | Implementation of power supply and control for HVAC devices | planned | Radosław Zdancewicz | 2 | 0 | 1700000 | 0 | 1700000 |  | 0
3.1.2 | Electrical heat treacing of piping - hot part | planned | Magdalena Białorucka | 2 | 742140 | 742140 | 0 | 0 |  | 0
3.1.3 | Aviation warning lights | planned |  | 2 | 140000 | 140000 | 0 | 0 |  | 0
3.1.4 | Fire detection and alarm system ( electrical&teletechnical part ) | planned | Radosław Zdancewicz | 2 | 980000 | 980000 | 0 | 0 |  | 0
3.1.5 | Smoke extraction from waste bunker and tipping hall (electrical&teletechnical part ) | planned | Radosław Zdancewicz | 2 | 175000 | 175000 | 0 | 0 |  | 0
3.2 | Teletechnical installations | contract prep. | Radosław Zdancewicz | 2 | 0 | 2579200 | 1750000 | 2579200 |  | 0
3.2.1 | Dostawa i montaż urządzeń elektrycznych |  |  |  | 2579200 | 0 | 0 | -2579200 |  | 0
3.3 | GPO/GPZ power supply | enquiry | Radosław Zdancewicz | 2 | 13510000 | 13510000 | 0 | 0 |  | 0
3.4.1 | Automation system and instrumentation, communication networks and control room devices | PCT/approval | Radosław Zdancewicz | 2 | 316200 | 0 | 0 | -316200 |  | 0
3.4.1.1 | Automation system and instrumentation, communication networks and control room devices | contract prep. | Radosław Zdancewicz | 2 | 5208800 | 5225000 | 6280000 | 16200 |  | 0
3.4.1.2 | Delivery of instrumentation for the boiler | planned | Radosław Zdancewicz | 1 | 0 | 300000 | 0 | 300000 |  | 0
3.4.2 | DCS System | planned | Roger Gołombek | 2 | 2752000 | 2752000 | 0 | 0 |  | 0
3.4.3 | Emission monitoring system (CEMS) | planned | Radosław Zdancewicz | 2 | 1960000 | 1960000 | 0 | 0 |  | 0
4 | Sanitary works and fire-fighting system |  |  | 2 | 21293319 | 0 | 0 | -21293319 |  | 0
4.1 | Deodorization system | planned | Stanisław Rucki | 2 | 1009700 | 1009700 | 0 | 0 |  | 0
4.2.1 | Fire detection and alarm system | enquiry | Magdalena Białorucka | 2 | 2211870 | 2211870 | 0 | 0 |  | 0
4.2.2 | Firefighting water tank | enquiry | Magdalena Białorucka | 2 | 275700 | 275700 | 0 | 0 |  | 0
4.2.3 | Firefighting water pumping | enquiry | Magdalena Białorucka | 2 | 715920 | 715920 | 0 | 0 |  | 0
4.2.4 | Firefighting water external distribution, hoses, sprinklers | enquiry | Magdalena Białorucka | 2 | 821016 | 821016 | 0 | 0 |  | 0
4.2.5 | Installation of internal hydrants in buildings B1 and B2 | enquiry | Magdalena Białorucka | 2 | 240990 | 240990 | 0 | 0 |  | 0
4.2.6 | Wireless radio controller system type WRC, gun control | enquiry | Magdalena Białorucka | 2 | 45500 | 45500 | 0 | 0 |  | 0
4.2.7 | Firefighting water external distribution, hoses, sprinklers | enquiry | Magdalena Białorucka | 2 | 542750 | 542750 | 0 | 0 |  | 0
4.2.8 | Dry bunker sprinkler system. Installation of water and foam cannons in the bunker hall, and assembly of the valve sub-control unit. | enquiry | Magdalena Białorucka | 2 | 1925350 | 1925350 | 0 | 0 |  | 0
4.2.9 | Natural gas (if any) and ammonia detection system | enquiry | Magdalena Białorucka | 2 | 285000 | 285000 | 0 | 0 |  | 0
4.2.10 | Smoke extraction from waste bunker and tipping hall | enquiry | Magdalena Białorucka | 2 | 1178293 | 1178293 | 0 | 0 |  | 0
4.3.1 | Boiler room roof ventilators and wall shutters | planned | Magdalena Przeździak | 2 | 1500000 | 1500000 | 0 | 0 |  | 0
4.3.2 | HVAC for the technological buildings | planned | Magdalena Przeździak | 2 | 3107033 | 3107033 | 0 | 0 |  | 0
4.3.3 | HVAC for the other buildings | planned | Magdalena Przeździak | 2 | 1548256 | 1548256 | 0 | 0 |  | 0
4.3.4 | Service water storage, pumping, underground and external distribution + Sanitary facilities (toilets, showers, etc.) | planned | Magdalena Przeździak | 2 | 1053444 | 1053444 | 0 | 0 |  | 0
4.3.5 | Sanitary water, connection to source, storage, pumping, underground and external distribution | planned | Magdalena Przeździak | 2 | 637613 | 637613 | 0 | 0 |  | 0
4.3.6 | Emergency showers and eye washers | planned | Magdalena Przeździak | 2 | 10000 | 10000 | 0 | 0 |  | 0
4.3.7 | Sanitary waste water collection, treatment and connection to discharge point | planned | Magdalena Przeździak | 2 | 624272 | 624272 | 0 | 0 |  | 0
4.3.8 | Waste water collection and connection to discharge point | planned | Magdalena Przeździak | 2 | 200969 | 200969 | 0 | 0 |  | 0
4.3.9 | Rain water and snowmelt collection, treatment and connection to discharge point | planned | Magdalena Przeździak | 2 | 3359643 | 3359643 | 0 | 0 |  | 0
5 | Mechanical and technological works |  |  | 2 | 258666646 | 0 | 0 | -258666646 |  | 0
5.1.1 | Radioactivity detector | planned |  | 2 | 185000 | 185000 | 0 | 0 |  | 0
5.2.1 | Overhead crane, grab and operator seat + Spare Grab | PCT/approval | Magdalena Białorucka | 2 | 9072785 | 9072785 | 8701000 | 0 |  | 0
5.2.2 | Trapdoors for grab maintenance | planned |  | 2 | 81600 | 81600 | 0 | 0 |  | 0
5.3.1 | Furnace charging hopper + Furnace supporting steel structure + Complete grate fired furnace with waste feeding system + Hoppers under grate | closed | - | 2 | 33755000 | 33755000 | 33755000 | 0 | 2025-12-04 | 0
5.3.2 | Primary and secondary air fan, Flue gas recirculation fan, ID Fan | enquiry | Magdalena Białorucka | 1 | 595000 | 595000 | 0 | 0 |  | 0
5.3.3 | Primary & secondary air heat exchanger | planned | Stanisław Rucki | 1 | 1281400 | 1281400 | 0 | 0 |  | 0
5.3.4 | Primary / secondary air ducts + Flue gas recirculation ducts + Auxiliary burners ducts + Supporting structures | planned | Stanisław Rucki | 2 | 2502500 | 2502500 | 0 | 0 |  | 0
5.3.5 | Fire curtain for primary air opening | planned | Magdalena Przeździak | 2 | 100000 | 100000 | 0 | 0 |  | 0
5.3.6 | Primary & secondary air dampers | planned |  | 1 | 220000 | 220000 | 0 | 0 |  | 0
5.3.7 | Flue gas recirculation dampers | planned |  | 1 | 40000 | 40000 | 0 | 0 |  | 0
5.3.8 | Camera for furnace monitoring | planned |  | 2 | 51600 | 51600 | 0 | 0 |  | 0
5.4.1 | Boiler - pressure parts | PCT/approval | Roger Gołombek | 2 | 8342011 | 5000000 | 0 | -3342011 |  | 0
5.4.1.1 | Boiler - pressure parts | PCT/approval | Roger Gołombek | 2 | 45990000 | 49332010.78 | 45990000 | 3342010.78 |  | 0
5.4.2 | Boiler - supporting structure including walkways | enquiry | Roger Gołombek | 2 | 6374147 | 6374146.52 | 0 | -0.48 |  | 0
5.4.3 | Fly ash extraction system for the boiler and conveyors | planned | Roger Gołombek | 2 | 4260000 | 4260000 | 0 | 0 |  | 0
5.4.4 | Sampling system | planned | Magdalena Białorucka | 1 | 1010500 | 1010500 | 0 | 0 |  | 0
5.4.5 | Chemical dosing for the boiler | planned | Magdalena Białorucka | 2 | 223600 | 223600 | 0 | 0 |  | 0
5.4.6 | Compensator between boiler and ECO | planned |  | 1 | 129000 | 129000 | 0 | 0 |  | 0
5.5 | Refractory | planned | Magdalena Białorucka | 2 | 3993000 | 3993000 | 0 | 0 |  | 0
5.6 | Burners including fans | enquiry | Stanisław Rucki | 1 | 1062800 | 1062800 | 0 | 0 |  | 0
5.7.1 | SNCR DeNOx system including silo, pumps | planned | Magdalena Białorucka | 2 | 1090000 | 1090000 | 0 | 0 |  | 0
5.7.2 | Flue gas treatment (FGT): Bag filter, Reactor, DeNOx, Flue gas condensation, Lime and activated carbon silos, dosing system | closed | - | 2 | 33755000 | 33755000 | 33755000 | 0 | 2025-12-04 | 0
5.7.3 | Bag filters delivery | planned | Roger Gołombek | 1 | 400000 | 400000 | 0 | 0 |  | 0
5.7.4 | Fly ash silos | planned | Roger Gołombek | 2 | 2000000 | 2000000 | 0 | 0 |  | 0
5.8.1 | Chain conveyor under grate + Bottom ash extractor + Vibrating table / bulk screen | enquiry | Stanisław Rucki | 1 | 1567228 | 1567228 | 0 | 0 |  | 0
5.8.2 | Belt conveyors | planned | Stanisław Rucki | 1 | 2347800 | 2347800 | 0 | 0 |  | 0
5.9 | Bottom ash / slag valorization | planned | Roger Gołombek | 1 | 8271000 | 8271000 | 0 | 0 |  | 0
5.10.1 | Steam turbine - gear box - generator. Including accessories: oil system, coolers, insulation, pipes and valves, control panel, protection panel, synchro system etc. | negotiation | Magdalena Białorucka / Stanisław Rucki | 2 | 13374290 | 13374290 | 0 | 0 |  | 0
5.10.2 | Auxiliary crane and hoists for the maintenance of the steam turbine | PCT/approval | Magdalena Białorucka | 2 | 300000 | 300000 | 499000 | 0 |  | 0
5.10.3 | Air cooled condenser | planned | Roger Gołombek | 2 | 9000000 | 9000000 | 0 | 0 |  | 0
5.10.4 | Feed water tank and Deaerator | enquiry | Magdalena Białorucka | 1 | 1000000 | 1000000 | 0 | 0 |  | 0
5.10.5 | Piping, fitting and supports | planned | Stanisław Rucki | 2 | 18664194 | 18664194 | 0 | 0 |  | 0
5.10.6 | Chemical dossing for thermal cycle and district heating | planned | Magdalena Białorucka | 1 | 550000 | 550000 | 0 | 0 |  | 0
5.10.7 | Main cooler | planned | Roger Gołombek | 1 | 2000000 | 2000000 | 0 | 0 |  | 0
5.10.8 | Cooler tank, condensate tank | planned | Roger Gołombek | 1 | 1000000 | 1000000 | 0 | 0 |  | 0
5.10.9 | Water pressure stabilization system | planned |  | 2 | 350000 | 350000 | 0 | 0 |  | 0
5.10.10 | Water tank 100 m3 | planned | Magdalena Białorucka | 2 | 200000 | 200000 | 0 | 0 |  | 0
5.10.11 | Heat exchangers 2 pcs., LP pre-heater, external economizer | planned | Stanisław Rucki | 2 | 3242866 | 3242866 | 0 | 0 |  | 0
5.10.12 | Stabilising pumps 2 x 100%, network pumps 3 x 50%, condensate pumps 2 x 100%, feed water pumps 3 pcs., cooling pumps | planned | Stanisław Rucki | 1 | 5517325 | 5517325 | 0 | 0 |  | 0
5.10.13.1 | Manual valves | planned | Roger Gołombek | 1 | 2200000 | 2200000 | 0 | 0 |  | 0
5.10.13.2 | Motorized valves | planned | Roger Gołombek | 1 | 1000000 | 1000000 | 0 | 0 |  | 0
5.10.13.3 | Safety valves | planned | Roger Gołombek | 1 | 200000 | 200000 | 0 | 0 |  | 0
5.10.13.4 | ON/OFF valves | planned | Roger Gołombek | 1 | 400000 | 400000 | 0 | 0 |  | 0
5.10.13.5 | Control valves | planned | Roger Gołombek | 1 | 700000 | 700000 | 0 | 0 |  | 0
5.11 | Stack | negotiation | Magdalena Białorucka | 2 | 1850000 | 1850000 | 0 | 0 |  | 0
5.12 | Boiler and piping insulation | planned | Magdalena Białorucka | 2 | 11000000 | 11000000 | 0 | 0 |  | 0
5.13.1 | Compressors 2 x 50% + 1 x 50% | planned | Roger Gołombek | 2 | 1500000 | 1500000 | 0 | 0 |  | 0
5.13.2 | Auxiliary fuel tank (light oil/diesel oil) | planned | Magdalena Białorucka | 2 | 200000 | 200000 | 0 | 0 |  | 0
5.13.3 | Light oil unloading installation with TDT documentation approval | planned |  | 2 | 200000 | 200000 | 0 | 0 |  | 0
5.13.4 | Auxiliary fuel pumps (light oil/diesel oil), demi water pumps, other water pumps | planned | Stanisław Rucki | 1 | 3337500 | 3337500 | 0 | 0 |  | 0
5.13.5 | Auxiliary system pipelines – light oil, demineralised water, chemical dosing, compressed air | planned | Stanisław Rucki | 2 | 2600000 | 2600000 | 0 | 0 |  | 0
5.13.6 | Auxiliary hoists for maintenance | planned | Magdalena Białorucka | 1 | 350000 | 350000 | 0 | 0 |  | 0
5.13.7 | Demi water system including storage tank 100m3 and piping | planned | Magdalena Białorucka | 2 | 3010000 | 3010000 | 0 | 0 |  | 0
5.13.8 | Chemical dosing system for thermal cycle and district heating | planned | Magdalena Białorucka | 2 | 838500 | 838500 | 0 | 0 |  | 0
5.13.9 | Grate cooling system | planned | Magdalena Białorucka | 1 | 731000 | 731000 | 0 | 0 |  | 0
5.13.10 | Centralized cleaning system for Boiler house | planned | Roger Gołombek | 2 | 800000 | 800000 | 0 | 0 |  | 0
5.14.1 | Scaffoldings | closed | Katarzyna Turek | 2 | 300000 | 300000 | 0 | 0 |  | 0
5.14.1.1 | Scaffoldings | closed | Katarzyna Turek | 2 | 700000 | 700000 | 700000 | 0 | 2026-01-31 | 0
5.14.2 | Mechanical installation of technological equipment | planned | Stanisław Rucki | 2 | 1500000 | 1500000 | 0 | 0 |  | 0
5.14.3 | Devices support structures | enquiry | Robert Klimczak | 2 | 1000000 | 1000000 | 0 | 0 |  | 0
5.14.4 | Installation marking | planned | Magdalena Białorucka | 2 | 350000 | 350000 | 0 | 0 |  | 0
6 | Cold and hot commissioning & Trial run of technological equipment |  |  |  | 8500000 | 0 | 0 | -8500000 |  | 0
6.1.1 | Start-up personnel | planned | Roger Gołombek | 2 | 5000000 | 5000000 | 0 | 0 |  | 0
6.1.2 | Boiler boiling | planned | Roger Gołombek | 2 | 200000 | 200000 | 0 | 0 |  | 0
6.1.3 | Steam blowing | planned | Roger Gołombek | 2 | 550000 | 550000 | 0 | 0 |  | 0
6.1.4 | Nitrogenation | planned | Roger Gołombek | 2 | 50000 | 50000 | 0 | 0 |  | 0
6.2.1 | Fuel (light oil) | planned | Roger Gołombek | 1 | 500000 | 500000 | 0 | 0 |  | 0
6.2.2 | Nitrogen cylinders | planned |  | 1 | 50000 | 50000 | 0 | 0 |  | 0
6.2.3 | Handling and disposal of bottom and fly ash | planned |  | 1 | 150000 | 150000 | 0 | 0 |  | 0
6.2.4 | Chemical supplies | planned |  | 1 | 50000 | 50000 | 0 | 0 |  | 0
6.2.5 | Lime supplies | planned |  | 1 | 350000 | 350000 | 0 | 0 |  | 0
6.2.6 | Active carbon supplies | planned |  | 1 | 200000 | 200000 | 0 | 0 |  | 0
6.2.7 | Disposal of waste after testing - discharge of waste water | planned |  | 1 | 150000 | 150000 | 0 | 0 |  | 0
6.3 | Training | planned |  | 2 | 500000 | 500000 | 0 | 0 |  | 0
6.4 | Spare parts (guarantee period 48 msc) | planned |  | 2 | 400000 | 400000 | 0 | 0 |  | 0
6.4.1 | Extension of the guarantee and warranty period to 48 months for electrical, technical and I&C works | contract prep. | Radosław Zdancewicz | 2 | 100000 | 100000 | 350000 | 0 |  | 0
6.5 | Compliance tests and simulations of the generation module | planned |  | 2 | 150000 | 150000 | 0 | 0 |  | 0
6.6 | Operating instructions | planned |  | 2 | 100000 | 100000 | 0 | 0 |  | 0
7 | Alignment to TCO values / Backup | planned |  | 2 | 754491.19 | 538351.64 | 0 | -216139.55 |  | 0
7.1 | Roboty ziemne ECR 3 |  |  |  | 322212.81 | 0 | 0 | -322212.81 |  | 0
8 | Services and works regarding indirect cost |  |  | 2 | 414429 | 0 | 0 | -414429 |  | 0
8.1.1 | Occupational Health and Safety equipment | planned |  | 2 | 0 | 96000 | 0 | 96000 |  | 0
8.1.2 | Small equipment rental | planned | Damian Gadowski | 2 | 0 | 90000 | 0 | 90000 |  | 0
8.1.3 | 30-T Truck Crane | planned | Damian Gadowski | 2 | 0 | 154000 | 0 | 154000 |  | 0
8.1.3.1 | Purchase of small construction materials and tools ECd_18 | closed |  | 1 | 0 | 50000 | 50000 | 50000 | 2026-01-31 | 0
8.1.3.2 | Purchase of small construction materials and tools ECd_19 | closed |  | 1 | 0 | 50000 | 50000 | 50000 | 2026-01-31 | 0
8.1.3.3 | Open order - sanitary industry assortment ECd_39 | closed |  | 1 | 0 | 30000 | 30000 | 30000 |  | 0
8.1.3.4 | Open order - sanitary industry assortment ECd_40 | closed |  | 1 | 0 | 30000 | 30000 | 30000 |  | 0
8.1.4 | Manitou Loader | planned | Damian Gadowski | 2 | 0 | 544000 | 0 | 544000 |  | 0
8.1.5 | Stationary Cranes | closed | Damian Gadowski | 2 | 0 | 89800 | 0 | 89800 | 2026-02-15 | 0
8.1.5.1 | Stationary tower crane + self-erecting crane | closed | Damian Gadowski | 2 | 0 | 1170200 | 1170200 | 1170200 | 2026-02-15 | 0
8.2.1 | Office Space or Container Rental | PCT/approval | Urszula Szwarc | 2 | 0 | 1148500 | 0 | 1148500 |  | 0
8.2.1.1 | Office Space or Container Rental - Consortium's facility ECd_20 | closed | Urszula Szwarc | 2 | 0 | 821840 | 821840 | 821840 | 2026-02-15 | 0
8.2.1.2 | Container rental - construction inauguration ECd_02 | closed | Urszula Szwarc | 2 | 0 | 4080 | 4080 | 4080 | 2025-12-04 | 0
8.2.1.3 | Container assembly for the construction inauguration ECd_03 | closed | Urszula Szwarc | 2 | 0 | 962 | 962 | 962 | 2025-12-04 | 0
8.2.1.4 | Office Space or Container Rental | enquiry | Urszula Szwarc | 2 | 0 | 0 | 0 | 0 |  | 0
8.2.1.5 | Conference room rental ECd_23 | closed |  | 2 | 0 | 1340 | 1340 | 1340 | 2026-01-28 | 0
8.2.1.6 | Office rental ECd_24 | closed |  | 2 | 0 | 7278 | 7278 | 7278 | 2026-01-28 | 0
8.2.2 | Municipal Waste Collection | closed |  | 2 | 0 | 64240 | 0 | 64240 |  | 0
8.2.2.1 | Municipal Waste Collection ECd_12 | closed |  | 2 | 0 | 50000 | 50000 | 50000 | 2025-12-31 | 0
8.2.3 | Electricity | planned | Rafał Tomczyk | 2 | 0 | 169130 | 0 | 169130 |  | 0
8.2.3.1 | The temporary power sypply installation ECd_26 | closed |  | 2 | 0 | 50000 | 50000 | 50000 | 2026-01-29 | 0
8.2.4 | Potable Water Cost | planned |  | 2 | 0 | 100300 | 0 | 100300 |  | 0
8.2.4.1 | Drinking water machine rental ECd_29 | closed |  | 2 | 0 | 8500 | 8500 | 8500 |  | 0
8.2.5 | Sewage/Septic Tank Removal | planned |  | 2 | 0 | 90880 | 0 | 90880 |  | 0
8.2.5.1 | Water consumption and sewage disposal ECd_21 | closed |  | 2 | 0 | 66880 | 66880 | 66880 | 2025-12-31 | 0
8.2.6 | Monthly Internet Costs | planned |  | 2 | 0 | 179520 | 0 | 179520 |  | 0
8.2.7 | Office Supplies | planned |  | 2 | 0 | 84080 | 0 | 84080 |  | 0
8.2.7.1 | Open order - office supplies ECd_32 | closed |  | 1 | 0 | 90000 | 90000 | 90000 |  | 0
8.2.8 | Cleaning | planned |  | 2 | 0 | 104680 | 0 | 104680 |  | 0
8.2.8.1 | Cleaning services ECd_35 | closed |  | 2 | 0 | 178200 | 178200 | 178200 |  | 0
8.2.9 | Coffee and Tea | planned |  | 2 | 0 | 34320 | 0 | 34320 |  | 0
8.2.9.1 | Coffee machine rental ECd_28 | closed |  | 2 | 0 | 50000 | 50000 | 50000 |  | 0
8.2.10 | PORR Office Costs (with PC Service) | planned |  | 2 | 0 | 500480 | 0 | 500480 |  | 0
8.2.11 | Office Equipment | planned |  | 2 | 0 | 31540 | 0 | 31540 |  | 0
8.2.11.1 | TV ECd_33 | closed |  | 1 | 0 | 11980 | 11980 | 11980 |  | 0
8.2.12 | Cleaning Supplies | planned |  | 2 | 0 | 38080 | 0 | 38080 |  | 0
8.3 | Construction (Monthly Cost) | planned |  | 2 | 0 | 0 | 0 | 0 |  | 0
8.3.1 | Electricity Costs | planned |  | 2 | 0 | 1445876 | 0 | 1445876 |  | 0
8.3.1.1 | Electricity Costs | PCT/approval |  | 2 | 0 | 100000 | 100000 | 100000 |  | 0
8.3.1.2 | Generator rental ECd_44 | closed |  | 2 | 0 | 23904 | 23904 | 23904 | 2026-03-15 | 0
8.3.2 | Potable Water Costs | planned |  | 2 | 0 | 190400 | 0 | 190400 |  | 0
8.3.3 | Sewage Costs | planned |  | 2 | 0 | 272000 | 0 | 272000 |  | 0
8.3.4 | Municipal Waste Collection | planned |  | 2 | 0 | 108800 | 0 | 108800 |  | 0
8.3.5 | Construction Waste Removal ECd_38 | contract prep. |  | 2 | 0 | 326400 | 290720 | 326400 |  | 0
8.3.6 | Site Security ECd_04 | closed |  | 2 | 0 | 585600 | 563696.81 | 585600 | 2025-12-31 | 0
8.3.7 | Toi-Toi ECd_17 | closed |  | 2 | 0 | 44030 | 26466 | 44030 | 2026-01-31 | 0
8.4 | Miscellaneous Costs | planned |  | 2 | 0 | 0 | 0 | 0 |  | 0
8.4.1 | Personal Occupational Health and Safety Equipment | planned |  | 2 | 0 | 130208 | 0 | 130208 |  | 0
8.4.1.1 | Personal Occupational Health and Safety Equipment ECd_43 | closed |  | 1 | 0 | 30000 | 30000 | 30000 | 2026-03-09 | 0
8.4.2 | Final Cleaning | planned |  | 2 | 0 | 50000 | 0 | 50000 |  | 0
8.4.3 | Construction Support - Manual Workers | enquiry |  | 2 | 0 | 557000 | 0 | 557000 |  | 0
8.4.3.1 | Construction Support - Manual Workers ECd_11 | closed |  | 2 | 0 | 361500 | 361500 | 361500 | 2025-12-31 | 0
8.4.3.2 | Construction Support - Manual Workers ECd_10 | closed |  | 2 | 0 | 361500 | 361500 | 361500 | 2025-12-31 | 0
8.5 | Construction Office - Connections and Equipment | planned |  | 2 | 0 | 0 | 0 | 0 |  | 0
8.5.1 | Internet Connection ECd_37 | closed |  | 2 | 0 | 25000 | 27350 | 25000 |  | 0
8.5.2 | Equipment (kitchen and office equipment + furniture) | closed |  | 2 | 0 | 0 | 0 | 0 | 2026-01-31 | 0
8.5.2.1 | Equipment (kitchen and office equipment + furniture) ECd_09 | closed |  | 2 | 0 | 50000 | 95272 | 50000 | 2026-01-31 | 0
8.5.2.2 | Office kitchen furniture ECd_36 | closed |  | 2 | 0 | 0 | 13414.64 | 0 |  | 0

## Notes
Note e mapping
Total budget KPI comes from Budget column AB row 12.
Updated budget comes from Procurement column S row 16.
Contracted value comes from Procurement column T row 16.
S-curve green line comes from budget row 'TKW Razem' distributed on monthly columns.
New WBS child rows are accepted automatically as long as the item code follows the numeric hierarchy.