## EC recommendation
| Budget | Measurement | Recomendation number | Technical scope - short | Technical scope - details | Subcontractor / Subvendor | SAP vendor number | Amount | Budget position | Date of decision | Date of Order | P.O. number | Podpisy EC | Zamówienie/Umowa/Aneks status | Podpis zamówienia przez PW | PCW | Czy dodano do PSa? | Nr poz. PS
|  |  | ECR no. 1 | Design | Design | FOROOM | 2711785 | 12100000 | 1.2 - direct cost | 2025-12-15 |  | 4502938068 | signed |  |  |  | TAK
| Yes | No | ECR no. 2 | Reinforcing steel | REINFORCING STEEL | THYSSENKRUPP | 1065384 | 3424080 | 2.5.1.1 - direct cost 2.5.2.3 - direct cost | 2025-12-30 | contract | 4502938804 | signed |  |  |  | TAK
| Yes | No | ECR no. 3 | Earthworks | Earthworks | MARKOP | 2717747 | 3143491.4 | 2.2 - direct cost 7.1 - direct cost 5.2.0.1 - indirect cost | 2026-01-09 | contract | 4502939064 | signed |  |  |  | TAK
| Yes | No | ECR no. 4 | additional permits | additional permits | KaBo Borkowski Sp. k. | 2723802 | 17400000 | 1.11 - direct cost 8.1.1 - direct cost | 2026-01-12 | contract | 4502946461 | sig |  |  |  | TAK
| Yes | No | ECR no. 5 | Scaffoldings | Scaffoldings | AS Rusztowania | 2718999 | 3295075 | 5.14.1.1 - direct cost | 2026-01-15 | 2026-01-15 | 4502943561 | signed |  |  |  | TAK
|  |  | ECR no. 6 | diaphragm walls and barrettes | Complete and comprehensive construction of diaphragm walls and barrettes, including the development of designs and as-built documentation, and the provision of the necessary materials, equipment, and personnel | STUMP FRANKI | F1030 | 4300000 | 2.1 - direct cost | 2026-02-13 | contract | 4502970689 | signed
| Yes | No | ECR no. 7 | AKPiA | Comprehensive EPC implementation of electrical, I&C, and telecommunications work, including commissioning and start-up of the installation | ELEKTROSERW | 2714750 | 37750000 | 1.2.4 - direct cost 3.1.1 - direct cost 3.2.1 - direct cost 3.4.1 - direct cost 6.4.1 - direct cost | 2026-04-07 | contract | 4502977090 | signed
| Yes | No | ECR no. 8 | tower cranes | tower cranes | ŻURAWIE WIELKOPOLSKA | 2709639 | 1170200 | 2.5 - indirect cost 2.3 - indirect cost | 2026-02-20 | contract | 4502983014 | signed
| Yes | No | ECR no. 9 | concrete mixes | Delivery of concrete in quantities and grades according to Appendix 1 (List of quantities and unit prices) | BUSZREM | 2711840 | 4490109 | 2.5.1.2 - direct cost 2.5.2.4 - direct cost 2.11.5 - direct cost | 2026-02-20 | contract | 4502986603 | signed
| Yes | No | ECR no. 10 | prefabricated elements | Complete and comprehensive preparation of project documentation, construction, delivery, and assembly of structures B1, B3, and B4 from prefabricated elements, including the provision of necessary materials, equipment, personnel, and preparation of as-built documentation. | BETARD | 1165926 | 19984000 | 2.5.2.1 - direct cost 2.6.1 - direct cost | 2026-03-04 | contract | 4502996937 | signed
| Yes | No | ECR no. 11 | reinforced concrete works | Comprehensive execution of works: reinforced concrete works of works specified in Annex No. 1, in accordance with the Contract Documentation. | AF KONSTRUKCJE | 1164276 | 8453470.15 | 2.4.1 - direct cost 2.5.1 - direct cost 2.5.2.2 - direct cost 2.11.5 - direct cost | 2026-03-05 | contract | 4502997466 | signed
| Yes | No | ECR no. 12 | concrete mixes |  | HOLCIM | 1175121 | 4554136 | 2.5.1.2 - direct cost 2.5.2.4 - direct cost 2.11.5 - direct cost | 2026-03-31 | contract | SAP4/HANA - 4503105904 (SAP 3 - 4503025053) | signed
| Yes | No | ECR no. 9 rev 1 | concrete mixes |  | BUSZREM | 2711840 | 0 |  | 2026-03-31 | anulowane |  | signed
| Yes | No | ECR no. 13 | steam boiler |  | SEFAKO | 2713841 | 45990000 | 5.4.1 - direct cost | 2026-04-01 |  | 4503036513 | signed
| Yes | No | ECR no. 14 | waste bunker cranes |  | ZBUD | 1162281 | 9150000 | 5.2.1 - direct cost 5.10.2 - direct cost | 2026-04-13 | contract | 4503036767 | signed
| Yes | No | ECR no. 3 rev 1 | Earthworks |  | MARKOP | 2717747 | 525 340,00 PLN | 2.2 - direct cost 7.1 - direct cost 2.14.2.1 - direct cost 5.2.0.1 - indirect cost | 2026-04-07 |  |  | signed
| Yes | No | ECR no. 15 | stack | Complete and comprehensive prefabrication, delivery and installation of the stack, including the preparation of the design documentation and the provision of the necessary personnel, equipment and materials | AVANTEA STEEL SOLUTIONS | 2719201 | 340 500,00 EUR 1 503 682,05 PLN | 5.11 - direct cost | 2026-04-13 | contract | 4503064698 | signed
| Yes | No | ECR no. 16 | steel constructions | Konstrukcje stalowe | NOWOSTAL | 1172599 | 19801595 | 2.6.1.3 - direct cost 2.6.3.1 - direct cost 5.4.2 - direct cost | 2026-04-28 | contract | 4503085836 | signed
| Yes | No | ECR no. 17 | slag extractor | Ekstraktor żużla | LOIBL Förderanlagen GmbH | 2015286 | 340 000,00 EUR 1 448 400,00 PLN | 5.8.1 - direct cost | 2026-05-05 | contract | 4503106362 | signed
| Yes | No | ECR no. 18 | feedwater tanks | Zbiorniki zasilające | ESTANC AS | 3200722 | 251 800,00 EUR 1 082 740,00 PLN | 5.10.4 - direct cost 5.10.9 - direct cost | 2026-05-11 | contract | 4503121635 | signed
| Yes | No | ECR no. 19 | steam turbine generator | Generator turbiny parowej | TRIVENI TURBINES | 3200723 | 3 018 580,00 EUR 12 979 894,00 PLN | 5.10.1 - direct cost | 2026-05-14 | contract | 4503120533 | signed
| YES | NO | ECR no. 20 | air and flue gas ducts design |  | ODS | 2724336 | 1042000 | 1.2.6 - direct cost | 2026-05-14 |  |  | signed
| Yes | No | ECR no. 21 | burners | palniki | BCE (Lamtec) |  | 365 000,00 EUR 1 554 900,00 PLN | 5.6 - direct cost 5.4.1 - direct cost | 2026-05-25 | contract |  | wysłane 25.05.2026
4 | Yes | No
| Yes | No |  | air preheaters |  | AS Technologie |  | 2400000 | 5.3.3 - direct cost 5.4.1 - direct cost
| Yes | No
| Yes | No |  |  |  | owent |  | 2500000
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| YES | nO
| yes | no
| YES | no
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| yes | no
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | no
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
| Yes | No
Note on I8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Koszt konsorcjum 700 000
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dostawa betonu. Za buszrem
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4,26