## TABLE DASHBOARD
| ORDINATO | DA ORDINARE
DESIGN | 24886974.0045 | 20703026.0081
CIVIL WORKS | 53496524.1586 | 54613242.8514
ELECTRICAL WORKS | 36070000 | 22275340
SANITARY WORKS AND FF | 0 | 21293319.0015
MECHANICAL AND TECHNOLOGICAL | 153053763.0559 | 105612882.9457
COMMISSIONING | 100000 | 8399999.9971
ALIGNEMENT AND BACKUP | 723162.81 | 229618.19
Total | 268330424.029 | 233127428.9938
| 53.51% | 46.49%

## JV RIEPILOGO
ANALISI BUDGET WLOCLAWEK - MAG 26
| Budget Apertura |  | B02 - Gennaio 2026 |  | B7 - Febbraio 2026 |  | B0 Riferimento (14) - Marzo 2026 |  | B17 - Maggio 2026 | B19 - Giugno 2026 |  |  |  | ORDINATO | BUDGET | 2026-05-01 |  | 2026-06-01 |  | 2026-07-01 | 2026-08-01 |  | 2026-05-01 | 2026-06-01
DESIGN | 45590000 |  | 45590000 | DESIGN | 45590000 |  | 45590000.0126 |  | 45590000.0122 | 45590000.0126 |  |  |  | DESIGN | 45590000.0126 | 24397974 | 53.52% | 24886974.0045 | 54.59% |  |  | Costi Indiiretti | 40036817.2737 | 40357633
Ordinato | - |  | 21990000 | Ordinato | 24270000 | 85.89% | 24886974.0045 |  | 24787974.0046 | 24886974.0045 | 54.59% |  |  | CIVIL WORKS | 108109767.01 | 33404101 | 30.9% | 53496524.1586 | 49.48% |  |  | Costi di garanzia, difetti, imprevisti | 22098535.15 | 22098535
In negoziazione + buffer | - |  | 17540000 | In negoziazione + buffer | 17890000 | 4.284% | 17372026 |  | 17372026 | 17372026 |  |  |  | ELECTRICAL WORKS | 58345340 | 36070000 | 61.82% | 36070000 | 61.82% |  |  | Totale Costi | 563593205.4465 | 563914021.0228
Da ordinare | 45590000 |  | 6060000 | Da ordinare | 3430000 | 9.089% | 3331000.0081 |  | 3430000.0076 | 3331000.0081 |  |  |  | SANITARY WORKS AND FF | 21293319.0015 | 0 | 0% | 0 | 0%
CIVIL WORKS | 112409767 |  | 112400766.993 | CIVIL WORKS | 108109767 |  | 108109767.01 |  | 108109767.0078 | 108109767.01 |  |  |  | MECHANICAL AND TECHNOLOGICAL | 258666646.0016 | 131227829 | 50.73% | 153053763.0559 | 59.17% |  |  | Ricavi | 627086000 | 627086000
Ordinato | - |  | 9610714 | Ordinato | 25047291 |  | 53496524.1586 |  | 53701520.1564 | 53496524.1586 | 49.48% |  |  | COMMISSIONING | 8499999.9971 | 100000 | 1.176% | 100000 | 1.176% |  |  | Margine | 63492794.5535 | 63171978.9772
In negoziazione + buffer | - |  | 34045674 | In negoziazione + buffer | 20510200 |  | 16378806.852 |  | 16091827.852 | 16378806.852 |  |  |  | ALIGNEMENT AND BACKUP | 952781 | 723162.81 | 75.9% | 723162.81 | 75.9% |  |  |  | 11.27% | 11.2%
Da ordinare | 112409767 |  | 68744378.993 | Da ordinare | 62552276 |  | 38234435.9994 |  | 38316418.9994 | 38234435.9994 |  |  |  |  | 501457853.0228 | 225923066.81 | 45.05% | 268330424.029 | 53.51%
ELECTRICAL WORKS | 58345340 |  | 58345340 | ELECTRICAL WORKS | 58327340 |  | 58345340 |  | 58345340 | 58345340
Ordinato | - |  | 0 | Ordinato | 38068200 |  | 36070000 |  | 36070000 | 36070000 | 61.82%
In negoziazione + buffer | - |  | 37400000 | In negoziazione + buffer | 0 |  | 2016200 |  | 2016200 | 2016200
Da ordinare | 58345340 |  | 20945340 | Da ordinare | 20259140 |  | 20259140 |  | 20259140 | 20259140
SANITARY WORKS AND FF | 21293319 |  | 21293319 | SANITARY WORKS AND FF | 21293319 |  | 21293319.0015 |  | 21293319.0015 | 21293319.0015
Ordinato | - |  | 0 | Ordinato | 0 |  | 0 |  | 0 | 0 | 0%
In negoziazione + buffer | - |  | 0 | In negoziazione + buffer | 0 |  | 0 |  | 0 | 0
Da ordinare | 21293319 |  | 21293319 | Da ordinare | 21293319 |  | 21293319.0015 |  | 21293319.0015 | 21293319.0015
MECHANICAL AND TECHNOLOGICAL | 258666646 |  | 258666645.9977 | MECHANICAL AND TECHNOLOGICAL | 258666646 |  | 258666646.0016 |  | 258666646.0016 | 258666646.0016
Ordinato | - |  | 67509999.9978 | Ordinato | 67810000 |  | 153053763.0559 |  | 131227829.0524 | 153053763.0559 | 59.17%
In negoziazione + buffer | - |  | 1000000 | In negoziazione + buffer | 85700000 |  | 6615897.95 |  | 9211113.95 | 6615897.95
Da ordinare | 258666646 |  | 190156645.9999 | Da ordinare | 105156646 |  | 98996984.9957 |  | 118227702.9947 | 98996984.9957
COMMISSIONING | 8500000 |  | 8500000 | COMMISSIONING | 8500000 |  | 8499999.9971 |  | 8499999.9971 | 8499999.9971
Ordinato | - |  | 0 | Ordinato | 500000 |  | 100000 |  | 100000 | 100000 | 1.176%
In negoziazione + buffer | - |  | 0 | In negoziazione + buffer | 0 |  | 399999.9984 |  | 399999.9984 | 399999.9984
Da ordinare | 8500000 |  | 8500000 | Da ordinare | 8000000 |  | 7999999.9987 |  | 7999999.9987 | 7999999.9987
ALIGNEMENT AND BACKUP | 952781 |  | 952781 | ALIGNEMENT AND BACKUP | 952781 |  | 952781 |  | 952781 | 952781
Ordinato | - |  | 722212.81 | Ordinato | 723163 |  | 723162.81 |  | 723162.81 | 723162.81 | 75.9%
In negoziazione + buffer | - |  | 0 | In negoziazione + buffer | 0 |  | 229618.19 |  | 229618.19 | 229618.19
Da ordinare | 952781 |  | 230568.19 | Da ordinare | 229618 |  | 0 |  | 0 | 0
Diretti | 505757853 |  | 505748852.9907 | Diretti | 506157852.9887 |  | 501457853.0228 |  | 501457853.0203 | 501457853.0228 |  |  |  | 40357633.0645
Indiretti | 40391014.15 |  | 40391014.15 |  | 40386273.2902 |  | 40355204.7049 |  | 40036817.2737 | 40357635.0624
Manutenzione | 0 |  | 22098535.15 |  | 22098535.15 |  | 22098535.15 |  | 22098535.15 | 22098535.15
Totale Costi | 546148867.15 |  | 568238402.2907 |  | 568642661.4289 |  | 563911592.8777 |  | 563593205.4428 | 563914023.2353 |  | 132685652.5259 | 26537130.5052
| Totale ordinato |  | 99832926.8078 | 19.74% | 156418654 | 30.49% | 234276624.029 | 46.72% | 268330424.029 | 268330424.029 | 53.51%
| Totale in neg + buffer |  | 89985674 |  | 124100200 |  |  |  | 43012548.9904 | 43012548.9904 | 8.578%
| Totale da ordinare |  | 315930252.1829 | 62.47% | 220920999 | 61.56% | 190114880.0034 | 37.91% | 190114880.0034 | 190114880.0034 | 37.91%
Ricavi Base | 631386000 |  | 631386000 |  | 631385999.73 |  | 627086000 |  | 627086000 | 627086000 |  | 148951543.943 | 29790308.7886
Margine | 85237132.85 | 15.61% | 63147597.7093 | 11.11% | 62743338.3011 | 11.03% | 63174407.1223 | 11.2% | 63492794.5572 | 63171976.7647 | 11.2% | 14863994.5329 | 2972798.9066 | 11.2%
Note on I42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tolto Stump Franki (4.300.000 PLN)

## INTERNA
| 2025 | 2026 | oltre
produzione | 244.462 | 8888 | 13414.595
costi | 220.0378 | 8000 | 12074.343
margine | 24.4242 | 888 | 1340.2521
% | 11.1% | 11.1% | 11.1%

## Report (hidden)
| Bdgt apertura | B02 - Gen26 | B07 - Feb26 | [7 empty] | Consorzio | PORR 80%
Costi diretti | 505757853 | 505748852.9907 | 501457853.0228 | [8 empty] | TME 20%
Costi indiretti | 40391014.15 | 40391014.15 | 40355204.7049
Contingency | 0 | 22098535.15 | 22098535.15 | [7 empty] | Cliente | PreZero
Totale costi | 546148867.15 | 568238402.2907 | 563911592.8777
Ricavi base | 631386000 | 631386000 | 627086000 | [7 empty] | Inizio progetto | 2026-01-30
Margine | 85237132.85 | 63147597.7093 | 63174407.1223
% | 13.5% | 10% | 10.07% | [7 empty] | Fine progetto | 2028-06-30
COSTI DIRETTI (PLN)
[5 empty] | Apertura | B07 | Dettaglio costi diretti
|  |  |  | DESIGN | 45590000 | 45590000.0126 | Ordinato totale (senza TME) | 190930424.0313 | #REF!
|  |  |  | CIVIL WORKS | 112409767 | 108109767.01 | Ordini a TME | 77399999.9978 | #REF!
|  |  |  | ELECTRICAL WORKS | 58345340 | 58345340 | Negoziazioni totale | 43012548.9904 | #REF!
|  |  |  | SANITARY WORKS AND FF | 21293319 | 21293319.0015 | Pianificato totale | 190114880.0034 | #REF!
|  |  |  | MECHANICAL AND TECHNOLOGICAL | 258666645.9977 | 258666646.0016 | Buffer totale | #REF! | #REF!
|  |  |  | COMMISSIONING | 8500000 | 8499999.9971 |  | #REF!
|  |  |  | ALIGNEMENT AND BACKUP | 952781 | 952781
[5 empty] | 505757852.9977 | 501457853.0228
|  |  |  | COSTI INDIRETTI (PLN) |  |  | Lista ordini/ negoziazioni
[5 empty] | Apertura | B07 | Fornitore | Sezione | Item | Descrizione | Ordine | Importo
|  |  |  | STAFF | 29056500 | 29056500 | FOROOM | 1_Design | 1.2.1 | Detailed architectural, structural, sanitary and road designs | 4502938068 | 12100000
|  |  |  | EQUIPMENT | 2404000 | 2404000.0003 | THYSSENKRUPP MATERIALS POLAND S.A. | 2_Civil Works | 2.5.1.1.1 | Supply of reinforcing steel | 4502938804 | 1821319
|  |  |  | CONSTRUCTION OFFICE | 4216821 | 4216821 | THYSSENKRUPP MATERIALS POLAND S.A. | 2_Civil Works | 2.5.2.3.1 | Supply of reinforcing steel | 4502938804 | 1602760.999
|  |  |  | CONSTRUCTION | 3767010 | 3767010.001 | MAR-KOP Marcin Mierzwa | 2_Civil Works | 2.2.1 | Working platform for foundation works | 4502939064 | 176673
|  |  |  | INSTALLATION / UNINSTALLATION OF CONSTRUCTION | 2278160 | 2278159.9933 | MAR-KOP Marcin Mierzwa | 2_Civil Works | 2.2.2 | Earthworks | 4502939064 | 2196542
|  |  |  | MISCELLANEOUS COSTS | 1600208 | 1600208.001 | MAR-KOP Marcin Mierzwa | 2_Civil Works | 2.2.3 | Earthworks – backfilling of retaining wall | 4502939064 | 313419
|  |  |  | FINANCIAL COSTS | -2931684.85 | -2936425.7055 | MAR-KOP Marcin Mierzwa | 7_Backup | 7.1.1 | Earthmoving robots ECR 3 | 4502939064 | 322212.81
Dati: Budget B07 di Febbraio 2026 |  |  |  |  | 40391014.15 | 40386273.2902 | KaBo | 7_Backup | 8.1.2 | Obtaining ECR 4 decisions and permits | 4502946461 | 400000
[7 empty] | ZAKŁAD SOZOTECHNIKI | 1_Design | 1.2.7.1 | Preparation of an application for an integrated permit, together with all necessary documents. | 4502966963 | 113000
[7 empty] | BARG | 2_Civil Works | 2.5.1.1.2 | Concrete testing | 4502968920 | 131560
[7 empty] | PROJBUD | 7_Backup | 8.1.1 | Temporary traffic organization ECD 34 | 4502971480 | 950
[7 empty] | Stump-Franki Sp. z o.o. | 2_Civil Works | 2.1.2 | Diaphragm wall and barrettes part 1 | ok | 3176000
[7 empty] | Stump-Franki Sp. z o.o. | 2_Civil Works | 2.1.3 | Barrettes part 2 | ok | 1124000
23478436.809
[7 empty] | TM.E. S.p.A - Termomeccanica Ecologia | 5_Mechanical & Tech. | 5.3.1 | Furnace charging hopper + Furnace supporting steel structure + Complete grate fired furnace with waste feeding system + Hoppers under grate | ok | 33754999.9978
[7 empty] | TM.E. S.p.A - Termomeccanica Ecologia | 5_Mechanical & Tech. | 5.7.2 | Flue gas treatment (FGT): Bag filter, Reactor, DeNOx, Flue gas condensation, Lime and activated carbon silos, dosing system | ok | 33755000
[7 empty] | TME | 1_Design | 1.1 | TME design | ok | 9890000
77399999.9978
[7 empty] | ELEKTROSERV - ZAP | 1_Design | 1.2.4 | Electrical & I/C detailed design | 0 | 1580000
[7 empty] | ELEKTROSERV - ZAP | 3_Electrical Works | 3.1.1.1 | Delivery and installation of electrical equipment | 0 | 28282000
[7 empty] | ELEKTROSERV - ZAP | 3_Electrical Works | 3.2.1 | Teletechnical installations | 0 | 2579200
[7 empty] | ELEKTROSERV - ZAP | 3_Electrical Works | 3.4.1.1 | Automation system and instrumentation, communication networks and control room devices | 0 | 5208800
[7 empty] | ELEKTROSERV - ZAP | 6_Commissioning | 6.4.1 | Warranty extension for electrical works | 0 | 100000
[7 empty] | MENOS | 1_Design | 1.2.5.1 | Building and detailed design of the GPO/GPZ station | 0 | 389999.9994
[7 empty] | KaBo | 1_Design | 1.11 | Obtaining decisions and permits | 0 | 17000000
[7 empty] | BETARD | 2_Civil Works | 2.5.2.1.1 | Reinforced concrete structure of the above-ground part of the B1 building - delivery and assembly of prefabricated elements | 0 | 18700000
[7 empty] | BUSZREM | 2_Civil Works | 2.5.2.4 | Supply of concrete mix with pumping service | 0 | 29639
[7 empty] | BUSZREM | 2_Civil Works | 2.11.5.1 | Delivery of concrete mix with pumping service | 0 | 1040470.0025
[7 empty] | BUSZREM | 2_Civil Works | 2.5.1.2 | Supply of concrete mix with pumping service | 0 | 3420000
[7 empty] | AS Rusztowania | 5_Mechanical & Tech. | 5.14.1.1 | Scaffoldings | 0 | 700000
79030109.0019
Dettaglio delle negoziazioni
ELEKTROSERV - ZAP
MENOS
KaBo
BUSZREM
BETARD
AS Rusztowania
45.590.000
108.109.767
21.293.319
8.500.000
58.345.340
258.666.646
Ricavi base: 631.386.000 PLN

## Ordinato (hidden)
Totale costi | 501457853.0228
Totale ordinato/negoziazione | 179908545.8087 | 35.88%
TME | 77399999.9978 | 43.02%
Chiusi | 19178436.809 | 10.66%
Negoziazione | 83330109.0019 | 46.32%
TME | 9890000 | 5.497%
TM.E. S.p.A - Termomeccanica Ecologia | 67509999.9978 | 37.52%
FOROOM | 12100000 | 6.726%
ELEKTROSERV - ZAP | 37750000 | 20.98% | Lump sum
MENOS | 389999.9994 | 0.2168%
ZAKŁAD SOZOTECHNIKI | 113000 | 0.06281%
KaBo | 17400000 | 9.672%
Stump-Franki Sp. z o.o. | 4300000 | 2.39%
MAR-KOP Marcin Mierzwa | 3008846.81 | 1.672%
THYSSENKRUPP MATERIALS POLAND S.A. | 3424079.999 | 1.903%
BARG | 131560 | 0.07313%
BUSZREM | 4490109.0025 | 2.496%
BETARD | 18700000 | 10.39%
AS Rusztowania | 700000 | 0.3891%
PROJBUD | 950 | 0.000528%
Fornitore | Macroattività | Item | Descrizione | Ordine | Importo
FOROOM | 1_Design | 1.2.1 | Detailed architectural, structural, sanitary and road designs | 4502938068 | 12100000
THYSSENKRUPP MATERIALS POLAND S.A. | 2_Civil Works | 2.5.1.1.1 | Supply of reinforcing steel | 4502938804 | 1821319
THYSSENKRUPP MATERIALS POLAND S.A. | 2_Civil Works | 2.5.2.3.1 | Supply of reinforcing steel | 4502938804 | 1602760.999
MAR-KOP Marcin Mierzwa | 2_Civil Works | 2.2.1 | Working platform for foundation works | 4502939064 | 176673
MAR-KOP Marcin Mierzwa | 2_Civil Works | 2.2.2 | Earthworks | 4502939064 | 2196542
MAR-KOP Marcin Mierzwa | 2_Civil Works | 2.2.3 | Earthworks – backfilling of retaining wall | 4502939064 | 313419
MAR-KOP Marcin Mierzwa | 7_Backup | 7.1.1 | Earthmoving robots ECR 3 | 4502939064 | 322212.81
KaBo | 7_Backup | 8.1.2 | Obtaining ECR 4 decisions and permits | 4502946461 | 400000
ZAKŁAD SOZOTECHNIKI | 1_Design | 1.2.7.1 | Preparation of an application for an integrated permit, together with all necessary documents. | 4502966963 | 113000
BARG | 2_Civil Works | 2.5.1.1.2 | Concrete testing | 4502968920 | 131560 | 7077486.809
PROJBUD | 7_Backup | 8.1.1 | Temporary traffic organization ECD 34 | 4502971480 | 950
TME | 1_Design | 1.1 | TME design | ok | 9890000
ELEKTROSERV - ZAP | 1_Design | 1.2.4 | Electrical & I/C detailed design |  | 1580000
MENOS | 1_Design | 1.2.5.1 | Building and detailed design of the GPO/GPZ station |  | 389999.9994
KaBo | 1_Design | 1.11 | Obtaining decisions and permits |  | 17000000
Stump-Franki Sp. z o.o. | 2_Civil Works | 2.1.2 | Diaphragm wall and barrettes part 1 | ok | 3176000
Stump-Franki Sp. z o.o. | 2_Civil Works | 2.1.3 | Barrettes part 2 | ok | 1124000
BUSZREM | 2_Civil Works | 2.5.1.2 | Supply of concrete mix with pumping service |  | 3420000
BETARD | 2_Civil Works | 2.5.2.1.1 | Reinforced concrete structure of the above-ground part of the B1 building - delivery and assembly of prefabricated elements |  | 18700000
BUSZREM | 2_Civil Works | 2.5.2.4 | Supply of concrete mix with pumping service |  | 29639
BUSZREM | 2_Civil Works | 2.11.5.1 | Delivery of concrete mix with pumping service |  | 1040470.0025 | 27490109.0025
ELEKTROSERV - ZAP | 3_Electrical Works | 3.1.1.1 | Delivery and installation of electrical equipment |  | 28282000
ELEKTROSERV - ZAP | 3_Electrical Works | 3.2.1 | Teletechnical installations |  | 2579200
ELEKTROSERV - ZAP | 3_Electrical Works | 3.4.1.1 | Automation system and instrumentation, communication networks and control room devices |  | 5208800
TM.E. S.p.A - Termomeccanica Ecologia | 5_Mechanical & Tech. | 5.3.1 | Furnace charging hopper + Furnace supporting steel structure + Complete grate fired furnace with waste feeding system + Hoppers under grate | ok | 33754999.9978
TM.E. S.p.A - Termomeccanica Ecologia | 5_Mechanical & Tech. | 5.7.2 | Flue gas treatment (FGT): Bag filter, Reactor, DeNOx, Flue gas condensation, Lime and activated carbon silos, dosing system | ok | 33755000
AS Rusztowania | 5_Mechanical & Tech. | 5.14.1.1 | Scaffoldings |  | 700000
ELEKTROSERV - ZAP | 6_Commissioning | 6.4.1 | Warranty extension for electrical works |  | 100000

## 0_Indirect
|  | BUDGET APERTURA | BUDGET 02 | BUDGET 07 | BUDGET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 |  | 40357635.0624
0 | INDIRECT | 40391014.15 | 40391014.15 | 40386273.2902 | 40355204.7049 | 40036817.2737 | 40357635.0624
[6 empty] | 318387.4312 | -2430.3576
[8 empty] | Ordered | 36343125.9564
[8 empty] | Negotiation+buffer | 3545712.9541
[8 empty] | Planned | 468796.1519
[8 empty] | (Buffer) | 3545712.9541
1 | STAFF | 29056500 | 29056500 | 29056500 | 29056500 | 28713000 | 29017400
[6 empty] | -343500 | -39100
1.1 | Remuneration PORR | 18824500 | 18824500 | 18824500 | 18824500 | 18481000 | 18824500 | PORR kadra
1.2 | Remuneration TME | 10232000 | 10232000 | 10232000 | 10232000 | 10232000 | 10192900 | TME kadra
|  | 29056500 | 29056500 | 29056500 | 29056500 | 28713000 | 29017400
[6 empty] | -343500 | -39100
2 | EQUIPMENT | 2404000 | 2404000 | 2404000.0003 | 2388999.9907 | 2419000.6407 | 2404100.0052
[6 empty] | 30000.65 | 15100.0145
2.1 | Safety and health protection | 96000 | 96000 | 96000 | 96000 | 96000 | 90866.46
2.1.1 | Lunches ECD 53 / 53rev 1 | 0 | 0 | 0 | 0 | 0 | 5233.54 | MICHELIN
|  | 96000 | 96000 | 96000 | 96000 | 96000 | 96100
[6 empty] | 0 | 100
2.2 | Small equipment hire | 90000 | 89038 | 84038 | 55834 | 48734 | 43734
2.2.1 | Rental of a crane for driving a shovel ECD 3 | 0 | 962 | 962 | 962 | 962 | 962 | BUDIZOL | 4502914407
2.2.2 | Rental of ECD 15 (Świnoujście - Włocławek) | 0 | 0 | 2500 | 2500 | 2500 | 2500 | SILOGOSTIC | 4502946426
2.2.3 | Rental of ECD 15 rev 1 (Rzeszów - Włocławek) | 0 | 0 | 2500 | 2500 | 2500 | 2500 | SILOGOSTIC | 4502946426
2.2.4 | Rental of ECD 15 rev 2 (Świnoujście - Włocławek) | 0 | 0 | 0 | 2400 | 2400 | 2400 | SILOGOSTIC | 4502946426
2.2.5 | Rental of ECD 15 rev 3 (Rzeszów - Włocławek) | 0 | 0 | 0 | 1400 | 1400 | 1400 | SILOGOSTIC | 4502946426
2.2.6 | Rental of ECD 44 generators | 0 | 0 | 0 | 23904 | 23904 | 23904 | MOBIL SERWIS | 4503007260
2.2.7 | Rental of ECD 15 rev 4 (Lublin - Włocławek) | 0 | 0 | 0 | 500 | 500 | 500 | SILOGOSTIC | 4502946426
2.2.8 | Rental of a drainage pump ECD 49 | 0 | 0 | 0 | 0 | 4600 | 4600 | KLAUDIA | 4503061913
2.2.9 | Rental of ECD 15 rev 5 (Świnoujście - Włocławek) | 0 | 0 | 0 | 0 | 2500 | 2500 | SILOGOSTIC | 4502946426
2.2.10 | Transport - ECD56 | 0 | 0 | 0 | 0 | 0 | 2700 | FROGTRANS | 4503121690
2.2.11 | Transport - ECD56 rev 1 | 0 | 0 | 0 | 0 | 0 | 2300 | FROGTRANS | 4503121690
|  | 90000 | 90000 | 90000 | 90000 | 90000 | 90000
[6 empty] | 0 | 0
2.3 | 30 T Truck Crane | 314000 | 314000 | 123833 | 123832.99 | 123833 | 123833
2.3.1 | Open order - small building materials ECD 18 | 0 | 0 | 50000.0041 | 50000.0031 | 50000.6431 | 50000.0014 | MAT-BUD | 4502950515
2.3.2 | Open order - small building materials ECD 19 | 0 | 0 | 49999.9962 | 49999.9972 | 49999.9972 | 50000.0034 | HURTOWNIA TOOLS | 4502950551
2.3.3 | ECR 8 stationary cranes | 0 | 0 | 90167 | 90167.0037 | 90167.0037 | 90167.0037 | ŻURAWIE WIELKOPOLSKIE
|  | 314000 | 314000 | 314000.0003 | 313999.994 | 314000.644 | 314000.0085
[6 empty] | 0.65 | 0.014483
2.4 | Manitou Charger | 544000 | 544000 | 544000 | 544000 | 544000 | 544000
|  | 544000 | 544000 | 544000 | 544000 | 544000 | 544000
[6 empty] | 0 | 0
2.5 | Stationary cranes | 1360000 | 1360000 | 0 | 1917 | 16917 | 1917
2.5.1 | Water-sewage connection ECD 5 | 0 | 0 | 101500 | 101500 | 101500 | 101500 | KRZYŚ | 4502939080
2.5.1.1 | Water-sewage connection ECD 5 rev 1 | 0 | 0 | 21000 | 21000 | 21000 | 21000 | KRZYŚ aneks 1 | 4502939080
2.5.2 | Geodesy ECD 6 | 0 | 0 | 155550 | 140549.9967 | 155549.9967 | 155549.9967 | Geobet | 4502939075
2.5.3 | ECR 8 stationary cranes | 0 | 0 | 1917 | 0 | 0 | 0
2.5.4 | ECR 8 stationary cranes | 0 | 0 | 1080033 | 1080033 | 1080033 | 1080033 | ŻURAWIE WIELKOPOLSKIE
|  | 1360000 | 1360000 | 1360000 | 1344999.9967 | 1374999.9967 | 1359999.9967
[6 empty] | 30000 | 15000
3 | CONSTRUCTION OFFICE | 4216821 | 4216821 | 4216821 | 4230235.6403 | 4213421.0003 | 4244737.3338
[6 empty] | -16814.64 | 14501.6934
3.1 | Rental of office space or office containers | 1984000 | 1984000 | 1150802 | 1150802 | 1145682 | 1173395.39
3.1.1 | Rental of office premises or office containers lease for 2 months ECD 2 | 0 | 0 | 4080 | 4080 | 4080 | 4080 | CONTAINEX | 4502914369
3.1.2 | Rental of office premises or office containers ECD 20 | 0 | 0 | 821840 | 821840 | 821840 | 821840 | PORR/PESA
3.1.3 | Temporary office ECD 24 | 0 | 0 | 7278 | 7278 | 7278 | 7278 | Staler Market | 4502952746
3.1.4 | Rental of office premises or office containers lease for 2 months ECD 2 rev 1 | 0 | 0 | 0 | 0 | 720 | 720 | CONTAINEX | 4502914369
3.1.5 | Rental of office premises or office containers lease for 2 months ECD 2 rev 2 | 0 | 0 | 0 | 0 | 0 | 660 | CONTAINEX | 4502914369
|  | 1984000 | 1984000 | 1984000 | 1984000 | 1979600 | 2007973.39
[6 empty] | -4400 | 23973.39
3.2 | Municipal waste disposal | 114240 | 114240 | 64240 | 64240 | 64240 | 64240
3.2.1 | Municipal waste disposal ECD 12 | 0 | 0 | 50000 | 50000.0003 | 50000.0003 | 50000.0003 | SANIKO | 4502943626
|  | 114240 | 114240 | 114240 | 114240.0003 | 114240.0003 | 114240.0003
[6 empty] | 0 | 0
3.3 | Electricity | 219130 | 219130 | 169130 | 169130 | 169130 | 169130
3.3.1 | Electricity ECD 26 | 0 | 0 | 50000 | 50000 | 50000 | 53942.94 | MPEC | 4502138477
|  | 219130 | 219130 | 219130 | 219130 | 219130 | 223072.94
[6 empty] | 0 | 3942.94
3.4 | Drinking water | 108800 | 108800 | 108800 | 108800 | 109800 | 108800
|  | 108800 | 108800 | 108800 | 108800 | 109800 | 108800
[6 empty] | 1000 | 0
3.5 | Sewage costs/ septic tank disposal/ | 157760 | 157760 | 157760 | 157760 | 157760 | 157760
|  | 157760 | 157760 | 157760 | 157760 | 157760 | 157760
[6 empty] | 0 | 0
3.6 | Monthly internet costs | 179520 | 179520 | 179520 | 179520 | 179520 | 179520
|  | 179520 | 179520 | 179520 | 179520 | 179520 | 179520
[6 empty] | 0 | 0
3.7 | Office supplies | 174080 | 174080 | 84080 | 84080 | 84080 | 84080
3.7.1 | ECD 32 Office Supplies | 0 | 0 | 90000 | 90000 | 90000 | 90000.0034 | ABIS
|  | 174080 | 174080 | 174080 | 174080 | 174080 | 174080.0034
[6 empty] | 0 | 0.0034483
3.8 | Cleaning | 282880 | 282880 | 104680 | 74680 | 74680 | 74680
3.8.1 | Cleaning the ECD 35 back room | 0 | 0 | 178200 | 178200 | 178200 | 178200 | CERBER | 4502976093
3.8.2 | Sanitary Wholesaler - Open Order ECD 40 | 0 | 0 | 0 | 30000 | 30000 | 30000 | ATMOMAT | 4502983951
|  | 282880 | 282880 | 282880 | 282880 | 282880 | 282880
[6 empty] | 0 | 0
3.9 | Coffee/tea | 84320 | 84320 | 26702.22 | 26702.22 | 26702.22 | 26702.22
3.9.1 | Coffee Tea - ECD 8 kick off meeting | 0 | 0 | 6277.78 | 6277.78 | 6277.78 | 6277.78 | KA-BO Borkowski | 4502940616
3.9.2 | Coffee tea - meeting 29.01.2026 ECD 23 | 0 | 0 | 1340 | 1340 | 1340 | 1340 | Hotel Aleksander | 4502955423
3.9.3 | Lease of ECD 28 coffee machine | 0 | 0 | 50000 | 50000 | 50000 | 50000 | COFFE PARTNER | 4502960536
|  | 84320 | 84320 | 84320 | 84320 | 84320 | 84320
[6 empty] | 0 | 0
3.10 | Representation costs | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
3.11 | Office costs PORR (with PC service) | 500480 | 500480 | 500480 | 500480 | 500480 | 500480
|  | 500480 | 500480 | 500480 | 500480 | 500480 | 500480
[6 empty] | 0 | 0
3.12 | Office equipment | 43520 | 43520 | 29190 | 29190 | 29190 | 29190
3.12.1 | multimedia equipment ECD 33 | 0 | 0 | 11980 | 11980 | 11980 | 11980 | AV Kreator | 4502971588
3.12.2 | ECD 37 Internet connection | 0 | 0 | 2350 | 2350 | 2350 | 2350 | THORNET
|  | 43520 | 43520 | 43520 | 43520 | 43520 | 43520
[6 empty] | 0 | 0
3.13 | Cleaning products | 38080 | 38080 | 38080 | 38080 | 38080 | 38080
|  | 38080 | 38080 | 38080 | 38080 | 38080 | 38080
[6 empty] | 0 | 0
3.14 | ECD 37 Internet connection | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | THORNET
|  | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
[6 empty] | 0 | 0
3.16 | Equipment (kitchen equipment, offices + furniture) ECD 9; ECD 9 rev 1 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | Meblorent | 4502943059
|  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
[6 empty] | 0 | 0
3.17 | Installation of office counters / changing rooms + energy + water supply connection | 158511 | 158511 | 99824.36 | 113239 | 99824.36 | 95414.36
3.17.1 | Equipment (kitchen equipment, offices + furniture) ECD 9; ECD 9 rev 1 | 0 | 0 | 45272 | 45272 | 45272 | 45272 | Meblorent | 4502943059
3.17.2 | Kitchen with ECD 36 household appliances | 0 | 0 | 13414.64 | 13414.64 | 13414.64 | 13414.64 | MIRRO
3.17.3 | Furniture for the investor ECD 9 rev 2 | 0 | 0 | 0 | 0 | 0 | 4410 | Meblorent | 4502943059
|  | 158511 | 158511 | 158511 | 171925.64 | 158511 | 158511
[6 empty] | -13414.64 | -13414.64
3.18 | Water-sewage connection ECD 5 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | KRZYŚ | 4502939080
|  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
[6 empty] | 0 | 0
3.19 | Cost of preparing the construction site (aggregate) ECD 14 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | MAT-BUD | 4502934293
|  | 34000 | 34000 | 34000 | 34000 | 34000 | 34000
[6 empty] | 0 | 0
3.20 | Multifunctional printer/xerox/scanner/fax | 12500 | 12500 | 12500 | 12500 | 12500 | 12500
|  | 12500 | 12500 | 12500 | 12500 | 12500 | 12500
[6 empty] | 0 | 0
4 | CONSTRUCTION (monthly cost) | 3767010 | 3767010 | 3767010.001 | 3765083.3449 | 3767009.9066 | 3767011.9926
[6 empty] | 1926.5617 | 1928.6477
4.1 | Electricity costs | 1569780 | 1569780 | 1569780 | 1569779.9975 | 1569779.9975 | 1569780.9975
|  | 1569780 | 1569780 | 1569780 | 1569779.9975 | 1569779.9975 | 1569780.9975
[6 empty] | 0 | 1
4.2 | Drinking water costs | 190400 | 190400 | 181900 | 151900 | 151900 | 123953.75
4.2.1 | Lease of ECD 29 water dispensers | 0 | 0 | 8500 | 8500.0031 | 8500.0031 | 8500.0031 | AQUAMO | 4502960520
4.2.2 | Sanitary Wholesale - Open Order ECD 39 | 0 | 0 | 0 | 30000 | 30000 | 30000 | INSTALNOVA | 4502983881
4.2.3 | "Groundbreaking Event" - ECD 57 | 0 | 0 | 0 | 0 | 0 | 27946.25 | PRZYSTAŃ
|  | 190400 | 190400 | 190400 | 190400.0031 | 190400.0031 | 190400.0031
[6 empty] | 0 | 0
4.3 | Sewage costs | 272000 | 272000 | 205120 | 205120 | 205120 | 205120
4.3.1 | Cost of wastewater ECD 21 | 0 | 0 | 66880 | 66880 | 66880 | 66880 | MPWIK
|  | 272000 | 272000 | 272000 | 272000 | 272000 | 272000
[6 empty] | 0 | 0
4.4 | Waste disposal | 108800 | 108800 | 108800 | 108800 | 108800 | 108801
|  | 108800 | 108800 | 108800 | 108800 | 108800 | 108801
[6 empty] | 0 | 1
4.5 | Wywóz odpadów budowlanych | 326400 | 326400 | 35680 | 35680 | 35680 | 35680
4.5.1 | Construction waste disposal ECD 38 | 0 | 0 | 290720 | 290720 | 290720.0057 | 290719.9957 | PREZERO | 4502980901
|  | 326400 | 326400 | 326400 | 326400 | 326400.0057 | 326399.9957
[6 empty] | 0.0057143 | -0.0042857
4.6 | Construction site backend protection 1st x 24h x 25PLN /hour x 31 days | 585600 | 585600 | 21903.19 | 21903.19 | 21903.19 | 16755.29
4.6.1 | Construction Site Backend Protection 1st x 24h x 25PLN /hour x 31 days ECD 4 | 0 | 0 | 563696.811 | 561770.1573 | 563696.7073 | 563696.7073 | SOLID SECURITY | 4502939860
4.6.2 | Access control - ECD 55 | 0 | 0 | 0 | 0 | 0 | 5148 | SOLID SECURITY | 4503103862
|  | 585600 | 585600 | 585600.001 | 583673.3473 | 585599.8973 | 585599.9973
[6 empty] | 1926.55 | 1926.65
4.7 | Toi-Toi | 44030 | 44030 | 17564 | 17564 | 17564 | 17564
4.7.1 | Toi-Toi ECD 17 | 0 | 0 | 26466 | 26465.9985 | 26466.0045 | 26466.0005 | WC SERWIS
|  | 44030 | 44030 | 44030 | 44029.9985 | 44030.0045 | 44030.0005
[6 empty] | 0.006 | 0.002
4.8 | Geodesy ECD 6 | 350000 | 350000 | 350000 | 349999.9985 | 349999.9985 | 349999.9985 | GEOBET | 4502939075
|  | 350000 | 350000 | 350000 | 349999.9985 | 349999.9985 | 349999.9985
[6 empty] | 0 | 0
4.9 | Geotechnics / ECD 31 Laboratory | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | BARG | 4502968920
|  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
[6 empty] | 0 | 0
4.10 | Cost of preparing the construction site (aggregate) ECD 14 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | MAT-BUD | 4502934293
|  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
[6 empty] | 0 | 0
4.11 | Snow clearing on site / month | 120000 | 120000 | 120000 | 120000 | 120000 | 103000
4.11.1 | Gas network renovation- ECD 58 | 0 | 0 | 0 | 0 | 0 | 17000 | Daniel Bartosz Usługi instalacyjne | 4503138430
|  | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
[6 empty] | 0 | 0
4.12 | Snow clearing on site / month | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
|  | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
[6 empty] | 0 | 0
4.13 | Site clearance | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
5 | INSTALLATION / UNINSTALLATION OF CONSTRUCTION | 2278160 | 2278160 | 2278159.9933 | 2278160.0033 | 2278160.0003 | 2278160.0003
[6 empty] | -0.003 | -0.003
5.1 | Utwardzenie terenu pod dźwigi i sprzęt montażowy | 200000 | 200000 | 0 | 0 | 0 | 0
5.1.1 | Płyty MON ECD 1 | 0 | 0 | 200000 | 200000 | 200000 | 200000 | BUDIZOL | 4502902128
|  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
[6 empty] | 0 | 0
5.2.0 | Storage and storage yards (aggregate) | 250000 | 250000 | 0 | 0 | 92289.73 | 92289.73
5.2.0.1 | Storage and storage yards (aggregate) ECR 3 | 0 | 0 | 134645 | 134645 | 42355.267 | 42355.267 | MAR-KOP Marcin Mierzwa | 4502939064
5.2.0.2 | Cost of preparing the construction site (aggregate) ECD 14 | 0 | 0 | 115354.9967 | 115355.0033 | 115355.0033 | 115355.0033 | MAT-BUD | 4502934293
5.2 | Construction Site Power Supply, Back-End Power Supply, Construction Site and Temporary Road Lighting | 1040000 | 1040000 | 168000 | 168000 | 151000 | 151000
5.2.1 | Electrical power supply of the ECD 7 construction | 0 | 0 | 680000 | 647500 | 647500 | 647500 | EL-MAR | 4502939085
5.2.2. | Construction site and temporary road lighting ECD 7 | 0 | 0 | 57000 | 89500 | 89500 | 89500 | EL-MAR | 4502939085
5.2.3 | Construction site and temporary road lighting ECD 7 REV 1 | 0 | 0 | 135000 | 135000 | 135000 | 135000 | EL-MAR | 4502939085
5.3.4 | Delivery of the ECD 7 REV 2 cabinet | 0 | 0 | 0 | 0 | 17000 | 17000 | EL-MAR | 4502939085
5.2.3 | Back-end electrical power supply |  |  |  |  | 0 | 0
|  | 1290000 | 1290000 | 1289999.9967 | 1290000.0033 | 1290000.0003 | 1290000.0003
[6 empty] | -0.003 | -0.003
5.3 | Hardening of construction and assembly sites (aggregate) | 300000 | 300000 | 0 | 0 | 0 | 0
5.3.1 | MON ECD 1 boards | 0 | 0 | 269000 | 269000 | 269000 | 269000 | BUDIZOL | 4502902128
5.3.2 | Cost of preparing the construction site (aggregate) ECD 14 | 0 | 0 | 31000 | 31000 | 31000 | 31000 | MAT-BUD | 4502934293
|  | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
[6 empty] | 0 | 0
5.4 | Vehicle wheel washer | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
|  | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
[6 empty] | 0 | 0
5.5 | Fence of the construction site with wickets and gates | 340000 | 340000 | 242559.9966 | 217302.42 | 198852.42 | 197552.42
5.5.1 | Fence of the construction site with wickets and gates ECD 16 | 0 | 0 | 97440 | 97440 | 97440 | 97440 | PORR/PES
5.5.2 | Aggregate ECD 14 rev 2 | 0 | 0 | 0 | 25257.58 | 25257.58 | 25257.58 | MAT-BUD | 4502934293
5.5.3 | TAS ECD 48 stairs | 0 | 0 | 0 | 0 | 17530 | 17530 | TLC RENTAL
5.5.4 | Application for occupying the ECD 52 road lane | 0 | 0 | 0 | 0 | 920 | 920 | ZNAKTOM | 4503121343
5.5.5 | Bicycle crossing signage - ECD52 REV 1 | 0 | 0 | 0 | 0 | 0 | 1300 | ZNAKTOM | 4503121343
|  | 340000 | 340000 | 339999.9966 | 340000 | 340000 | 340000
[6 empty] | 0 | 0
5.6 | 4 information boards | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
|  | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
[6 empty] | 0 | 0
5.8 | Restoration of greenery (grass seeding) | 40160 | 40160 | 40160 | 40160 | 40160 | 40160
|  | 40160 | 40160 | 40160 | 40160 | 40160 | 40160
[6 empty] | 0 | 0
6 | MISCELLANEOUS COSTS | 1600208 | 1600208 | 1600208.001 | 1600207.9931 | 1600207.9931 | 1600207.9931
[6 empty] | 0 | 0
6.1 | Fire service and fire-fighting equipment. | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
[6 empty] | 0 | 0
6.2 | Monitoring of existing buildings | 20000 | 20000 | 1920.34 | 1583.75 | 1583.75 | 1583.75
6.2.1 | Monitoring of existing buildings ECD 22 | 0 | 0 | 16616.25 | 16616.25 | 16616.25 | 16616.25 | SETCON | 4502957582
6.2.2 | Mountaineering service - installation of ECD 30 / ECD 30 rev 1 cameras | 0 | 0 | 1463.41 | 1800 | 1800 | 1800 | ARBO-DRWAL | 4502971778
|  | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
[6 empty] | 0 | 0
6.3 | Safety and Environmental Management System | 20000 | 20000 | 6720 | 4720 | 4720 | 4720
6.3.1 | Safety and Environmental Management System ECD 25 | 0 | 0 | 13280 | 13280 | 13280 | 13280 | GEOTEST | 4502956394
6.3.2 | Road Signs | 0 | 0 | 0 | 2000 | 2000 | 2000 | DROG-ZNAK | 4502992375
|  | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
[6 empty] | 0 | 0
6.4 | Removal of clashes associated with the preparation of the back-up and construction area | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
|  | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
[6 empty] | 0 | 0
6.5 | Personal OHS equipment | 160208 | 160208 | 160208 | 130208 | 130208 | 130208
6.5.1 | Open order - OHS equipment ECD 43 | 0 | 0 | 0 | 30000 | 30000 | 30000 | PROSAVE
|  | 160208 | 160208 | 160208 | 160208 | 160208 | 160208
[6 empty] | 0 | 0
6.6 | Final cleaning | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
6.6.0 | Construction service | 1280000 | 1280000 | 557000.01 | 557000 | 557000 | 557000
6.6.1 | ECD 10 construction support | 0 | 0 | 361499.9955 | 361499.9966 | 361499.9966 | 361499.9966 | Adam Kujawka | 4502948806
6.6.2 | ECD 11 construction support | 0 | 0 | 361499.9955 | 361499.9966 | 361499.9966 | 361499.9966 | Grzegorz Kujawka | 4502948820
|  | 1330000 | 1330000 | 1330000.001 | 1329999.9931 | 1329999.9931 | 1329999.9931
[6 empty] | 0 | 0
7 | FINANCIAL COSTS | -2931684.85 | -2931684.85 | -2936425.7055 | -2963982.2674 | -2953982.2673 | -2953982.2625
[6 empty] | 10000.0001 | 10000.0049
7.1 | CAR insurance | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
7.2 | Design insurance | 822999.19 | 822999.19 | 589999.1869 | 256178.0441 | 256178.0441 | 256178.0441
7.2.1 | Design insurance Designer's liability insurance | 0 | 0 | 232999.9972 | 343821.14 | 343821.14 | 343821.14 | Guarantee of due performance
7.2.2 | Design insurance OC projektanta | 0 | 0 | 0 | 223000.0017 | 232999.999 | 232999.999 | UNIQA | 4502944036
|  | 822999.19 | 822999.19 | 822999.1841 | 822999.1859 | 832999.1831 | 832999.1831
[6 empty] | 9999.9972 | 9999.9972
7.3 | OC insurance | 329199.67 | 329199.67 | 324460.07 | 329199.67 | 329199.67 | 329199.67
|  | 329199.67 | 329199.67 | 324460.07 | 329199.67 | 329199.67 | 329199.67
[6 empty] | 0 | 0
7.4 | Bid bond | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
7.5 | Advance payment guarantee | 2371941.5 | 2371941.5 | 2371940.2504 | 2371941.5011 | 2371941.504 | 2371941.504
|  | 2371941.5 | 2371941.5 | 2371940.2504 | 2371941.5011 | 2371941.504 | 2371941.504
[6 empty] | 0.002867 | 0.002867
7.6 | Performance bond | 2155415.11 | 2155415.11 | 2155415.11 | 2155415.1056 | 2155415.1056 | 2155415.1104
|  | 2155415.11 | 2155415.11 | 2155415.11 | 2155415.1056 | 2155415.1056 | 2155415.1104
[6 empty] | 0 | 0.0048
7.7 | Warranty guarantee | 1721141.67 | 1721141.67 | 1721141.67 | 1721141.67 | 1721141.67 | 1721141.67
|  | 1721141.67 | 1721141.67 | 1721141.67 | 1721141.67 | 1721141.67 | 1721141.67
[6 empty] | 0 | 0
8 | Other income | -10332381.99 | -10332381.99 | -10332381.99 | -10332381.99 | -10332381.99 | -10332381.99
| Other income | 0 | 0 | 0 | -32297.41 | -32297.41 | -32297.41
|  | -10332381.99 | -10332381.99 | -10332381.99 | -10364679.4 | -10364679.4 | -10364679.4
[6 empty] | 0 | 0
9 | Other costs | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
10 | Exchange rate differences | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
11 | Financial interest | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0

## 1_Design
|  | BUDGET APERTURA | BUDGET 02 | BUDGET 07 | BUDGET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 | ORDINATO | DA ORDINARE EXTRA | TOTALE CON FORECAST
|  | 45590000 | 45589999.9994 | 45989999.9994 | [5 empty] | 45590000.0126 |  | 45590000.0126
1 | DESIGN | 27170000 | 27169999.9994 | 27169999.9994 | 27169999.9994 | 27170000.0046 | 27170000.0045 | 0 | 0 | 27170000.0045
[6 empty] | 0.0052067 | 0.0051455 |  |  | 0.0051455
[11 empty] | Ordered | 24886974.0045
[11 empty] | Negotiation | 17372026
|  |  | SAVINGS | 0 | 0 | 0 | -0.003334 |  | SAVINGS |  | Planned | 3331000.0081
|  |  | EXTRA | 0 | 0 | 0 | 0 |  | EXTRA |  | Extra | 0
[11 empty] | (Buffer) | 372026
1.1 | TME design | 9890000 | 9890000 | 9890000 | 9890000 | 9890000.0033 | 9890000 |  |  | 9890000 | TME
|  | 9890000 | 9890000 | 9890000 | 9890000 | 9890000.0033 | 9890000 | 0 | 0 | 9890000
[6 empty] | -0.003334 | 0 |  |  | 0
1.2 | Detailed architectural, structural, sanitary and road designs | 12200000 | 100000 | 100000 | 100000 | 100000 | 100000 |  |  | 100000
1.2.1 | Detailed architectural, structural, sanitary and road designs - ECR 1 | 0 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 |  |  | 12100000 | FOROOM | 4502938068
1.2.2 | Detailed design: boiler support steel structure and equipment support structures - ECD 41 | 500000 | 500000 | 500000 | 500000 | 499999.9973 | 500000.0045 |  |  | 500000.0045 | ODS | Ok
1.2.3 | Detailed design: fire-fighting system | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 |  |  | 260000
1.2.4 | Electrical & I/C detailed design | 1580000 | 1580000 | 1580000 | 1580000 | 1580000 | 1580000 |  |  | 1580000 | ELEKTROSERV - ZAP | Ok
1.2.5 | Building and detailed design of the GPO/GPZ station | 440000 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  | 50000
1.2.5.1 | Building and detailed design of the GPO/GPZ station | 0 | 389999.9994 | 389999.9994 | 389999.9994 | 390000.004 | 390000 |  |  | 390000 | MENOS | Ok
1.2.6 | Piping and ducts design | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1901000 |  |  | 1901000
1.2.6.1 | Air and flue gas ducts design - ECR20 | 0 | 0 | 0 | 0 | 0 | 99000 |  |  | 99000 | ODS | 4502993588
1.2.7 | Other documentation, opinions, agreements, permits, provisions, approvals and decisions necessary for the design, execution of the Works and commissioning of the investment (concession documentation for the generation of electricity and heat from a renewable energy source, ITPOE operating permit, integrated permit, geological designs and documentation, commissioning designs, operating instructions, etc.). | 300000 | 300000 | 187000 | 187000 | 187000 | 187000 |  |  | 187000
1.2.7.1 | Preparation of the application for the issuance of an integrated permit with all necessary documents ECD 27 | 0 | 0 | 113000 | 113000 | 113000 | 113000 |  |  | 113000 | ZAKŁAD SOZOTECHNIKI | 4502966963
|  | 17280000 | 17279999.9994 | 17279999.9994 | 17279999.9994 | 17280000.0013 | 17280000.0045 | 0 | 0 | 17280000.0045
[6 empty] | -0.0018727 | -0.0051455 |  |  | -0.0051455
| Service companies | 18420000 | 18420000 | 18820000 | 18420000 | 18420000.0076 | 18420000.0081 |  |  | 18420000.0081
1.3 | Noise Analysis and noise protection design | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 |  |  | 100000
|  | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 100000
[6 empty] | 0 | 0 |  |  | 0
1.4 | HAZOP study and SIL analysis | 250000 | 250000 | 250000 | 35026 | 35026 | 35026 |  |  | 35026
1.4.1 | HAZOP study and SIL analysis |  |  |  | 214974 | 214974 | 214974 |  |  | 214974 | UDT CERT | 4503027816
|  | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 0 | 0 | 250000
[6 empty] | 0 | 0 |  |  | 0
1.5 | Fire safety instructions | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 |  |  | 100000
|  | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 100000
[6 empty] | 0 | 0 |  |  | 0
1.6 | Explosion hazard assessment | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 |  |  | 120000
|  | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 0 | 0 | 120000
[6 empty] | 0 | 0 |  |  | 0
1.7 | Technical Consultant for certification and for complying with European Directives | 100000 | 100000 | 100000 | 100000 | 100000.0046 | 100000.0069 |  |  | 100000.0069
|  | 100000 | 100000 | 100000 | 100000 | 100000.0046 | 100000.0069 | 0 | 0 | 100000.0069
[6 empty] | -0.0046154 | -0.0069231 |  |  | -0.0069231
1.8 | Notification Bodies | 350000 | 350000 | 350000 | 350000 | 350000 | 349999.9982 |  |  | 349999.9982
|  | 350000 | 350000 | 350000 | 350000 | 350000 | 349999.9982 | 0 | 0 | 349999.9982
[6 empty] | 0 | 0.0018182 |  |  | 0.0018182
1.9 | Translations (Polish / English) | 250000 | 250000 | 250000 | 250000 | 250000.003 | 250000.003 |  |  | 250000.003
|  | 250000 | 250000 | 250000 | 250000 | 250000.003 | 250000.003 | 0 | 0 | 250000.003
[6 empty] | -0.00298 | -0.00298 |  |  | -0.00298
1.10 | NC Rfg certification | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 |  |  | 150000
|  | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 0 | 0 | 150000
[6 empty] | 0 | 0 |  |  | 0
1.11 | Obtaining decisions and permits - ECR 4 | 17000000 | 17000000 | 17400000 | 17000000 | 17000000 | 17000000 |  |  | 17000000 | KaBo | 4502946461
|  | 17000000 | 17000000 | 17400000 | 17000000 | 17000000 | 17000000 | 0 | 0 | 17000000
[6 empty] | 0 | 0 |  |  | 0
Note on F65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Da considerare sempre in negoziazione
Note on G65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Da considerare sempre in negoziazione
Note on H65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Da considerare sempre in negoziazione

## 2_Civil Work
|  | BUDGET APERTURA | BUDGET 02 | BUDGET 07 | BUDGET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 | ORDINATO | DA ORDINARE EXTRA | TOTALE CON FORECAST |  | 108109767.01
2 | CIVIL WORKS | 112409767 | 112409766.992 | 112409766.9919 | 108109767.0044 | 108109767.0078 | 108109767.01 | 0 | 0 | 108109767.01
[6 empty] | 0.0033721 | 0.005506 |  |  | 0.005506
[11 empty] | Ordered | 53496524.1586 | 53701520.1564
[11 empty] | Negotiation + buffer | 16378806.852
|  |  | SAVINGS | [5 empty] | SAVINGS |  | Planned | 38234435.9994
|  |  | EXTRA | [5 empty] | EXTRA |  | Extra | 0
[11 empty] | (Buffer) | 16378806.852
2.1 | Foundation works | 4613087 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.1.1 | Buffer | 0 | 1113087 | 313087 | 229887 | 229887 | 229887 |  |  | 229887
2.1.2 | Diaphragm wall and barrettes part 1 | 0 | 3500000 | 3176000 | 0 | 0 | 0 |  |  | 0 | Stump-Franki Sp. z o.o.
2.1.3 | Barrettes part 2 | 0 | 0 | 1124000 | 0 | 0 | 0 |  |  | 0 | Stump-Franki Sp. z o.o.
2.1.4 | Concrete rubble ECD 45 | 0 | 0 | 0 | 83200 | 83200 | 83200 |  |  | 83200 | Usługi Sprzętowo - Transportowe Sławomir Boruczkowski
|  | 4613087 | 4613087 | 4613087 | 313087 | 313087 | 313087 | 0 | 0 | 313087
[6 empty] | 0 | 0 |  |  | 0
2.2 | Earthworks | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.2.1 | ECR 3 / ECR 3 rev 1 working platform | 176673 | 176673 | 176673 | 176673 | 176673 | 176673 |  |  | 176673 | MAR-KOP Marcin Mierzwa | 4502939064
2.2.2 | Earthmoving robots ECR 3 / ECR 3 rev 1 | 2196542 | 2196542 | 2196542 | 2196542 | 2196542 | 2196542 |  |  | 2196542 | MAR-KOP Marcin Mierzwa | 4502939064
2.2.3 | Earthworks - backfill of retaining wall ECR 3 / ECR rev 1 | 313419 | 313419 | 313419 | 313419 | 313419 | 313419 |  |  | 313419
|  | 2686634 | 2686634 | 2686634 | 2686634 | 2686634 | 2686634 | 0 | 0 | 2686634
[6 empty] | 0 | 0 |  |  | 0
2.3 | Drainage | 437599 | 437599 | 437598.9971 | 437598.9971 | 367599 | 332599 |  |  | 332599
2.3.1 | Dehydration ECD 50 | 0 | 0 | 0 | 0 | 70000 | 70000 |  |  | 70000 | HAMER | 4503066286
2.3.1 | Dehydration ECD 50 rev 1 | 0 | 0 | 0 | 0 | 0 | 35000 |  |  | 35000 | HAMER | 4503066286
|  | 437599 | 437599 | 437598.9971 | 437598.9971 | 437599 | 437599 | 0 | 0 | 437599
[6 empty] | -0.0028571 | -0.0028571 |  |  | -0.0028571
2.4 | Insulation | 1138973 | 1138973 | 1138973 | 403973 | 345021 | 298038 |  |  | 298038
2.4.1 |  | 0 | 0 | 0 | 1953.86 | 1953.85 | 1953.85 |  |  | 1953.85
2.4.1 | ECR 11 reinforced concrete works | 0 | 0 | 0 | 733046.15 | 733046.15 | 733046.15 |  |  | 733046.15 | AF KONSTRUKCJE | 4502997466
2.4.2 | Waterproofing ECD 51 | 0 | 0 | 0 | 0 | 31352 | 31352 |  |  | 31352 | TWS | 4503071267
2.4.3 | Foundation insulation materials ECD 14 rev 3 | 0 | 0 | 0 | 0 | 27600 | 27600 |  |  | 27600 | MAT-BUD | 4502934293
2.4.4 | Waterproofing - ECD 51 rev 1 | 0 | 0 | 0 | 0 | 0 | 46983 |  |  | 46983 | TWS | 4503071267
|  | 1138973 | 1138973 | 1138973 | 1138973.01 | 1138973 | 1138973 | 0 | 0 | 1138973
[6 empty] | 0.01 | 0.01 |  |  | 0.01
2.5 | Reinforced concrete structure | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.5.1 | Reinforced concrete foundation structure | 16024473 | 14169473.15 | 10617413.2959 | 5117413.3 | 5117413.3 | 5117413.3 |  |  | 5117413.3
2.5.1.1 | Supply of reinforcing steel | 0 | 33680.7 | 33680.7 | 33680.7 | 33680.7 | 7240.7 |  |  | 7240.7
2.5.1.1.1 | Supply of ECR 2 reinforcing steel | 0 | 1821319 | 1821319 | 1821319 | 1821319.0014 | 1821319.0014 |  |  | 1821319.0014 | THYSSENKRUPP MATERIALS POLAND S.A. | 4502938804
2.5.1.1.2 | Reinforced meches - ECD 14 rev 4 | 0 | 0 | 0 | 0 | 0 | 26440 |  |  | 26440 | MAT-BUD | 4502934293
2.5.1.1.2 | Concrete testing | 0 | 0 | 500 | 500 | 500 | 500 |  |  | 500
2.5.1.1.2 | Concrete testing - ECD 31 | 0 | 0 | 131560 | 131560 | 131560.0022 | 131559.997 |  |  | 131559.997 | BARG | 4502968920
2.5.1.1.3 | Reinforced concrete works | 0 | 0 | 0 | 223042 | 223042 | 223042 |  |  | 223042
2.5.1.1.4 |  | 0 | 0 | 0 | 5276958 | 5276958 | 5276958 |  |  | 5276958 | AF KONSTRUKCJE
2.5.1.2 | Delivery of concrete mix including pumping service ECR 9 rev 1 / ECR 12 | 0 | 0 | 3420000 | 3419999.9994 | 3419999.9988 | 3419999.9988 |  |  | 3419999.9988 | BUSZREM / HOLCIM | 4502986603
2.5.1.3 | Construction of reinforced concrete foundations and underground structures | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.5.2 | Reinforced concrete structure of the above-ground part, including prefabricated elements | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.5.2.1 | Reinforced concrete structure of the above-ground part of the B1 building - delivery and assembly of prefabricated elements | 18708794 | 8794 | 8794 | 0 | 0 | 0 |  |  | 0
2.5.2.1.1 | Reinforced concrete structure of the above-ground part of the B1 facility - delivery and assembly of ECR 10 prefabricated elements | 0 | 18700000 | 18700000 | 18708794 | 18708794 | 18708794 |  |  | 18708794 | BETARD
2.5.2.2 | Reinforced concrete structure of the above-ground part of other buildings, including prefabricated elements | 3426648 | 1794248 | 1794248 | 990112 | 990112 | 990112 |  |  | 990112
2.5.2.2.1 | Reinforced concrete works | 0 | 0 | 0 | 41927 | 41927 | 41927 |  |  | 41927
2.5.2.2.2 | ECR 11 reinforced concrete works | 0 | 0 | 0 | 708073 | 708073 | 708073 |  |  | 708073 | AF KONSTRUKCJE
2.5.2.3 | Supply of reinforcing steel | 0 | 29639.15 | 0 | 0 | 0 | 0 |  |  | 0
2.5.2.3.1 | Supply of ECR 2 reinforcing steel | 0 | 1602760.999 | 1602760.999 | 1602760.999 | 1602761.002 | 1602761.002 |  |  | 1602761.002 | THYSSENKRUPP MATERIALS POLAND S.A. | 4502938804
2.5.2.4 | Delivery of concrete mix including pumping service ECR 9 rev 1 / ECR 12 | 0 | 0 | 29639 | 29639 | 29639 | 29639 |  |  | 29639 | BUSZREM / HOLCIM | 4502986603
2.5.4.4.1 | Delivery of concrete mix with ECR 12 pumping service | 0 | 0 | 0 | 54136 | 54136 | 54136 |  |  | 54136 | BUSZREM / HOLCIM
2.5.2.5 | Flyover for belt conveyor | 386500 | 386500 | 386500 | 386500 | 386500 | 386500 |  |  | 386500
2.5.2.6 | Retaining wall | 718448 | 718448 | 718448 | 718448 | 718448 | 718448 |  |  | 718448
|  | 39264863 | 39264862.999 | 39264862.9949 | 39264862.9984 | 39264863.0045 | 39264862.9993 | 0 | 0 | 39264862.9993
[6 empty] | -0.0060626 | -0.00087737 |  |  | -0.00087737
2.6 | Steel structures | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.6.1 | Structure, including platforms, walkways, ladders, roofing | 23700876 | 23700876 | 23700876 | 21982670 | 7982670 | 7982670 |  |  | 7982670
2.6.1.1 | Detailed Design: Boiler Steel Support Structure and ECD 41 Equipment Support Structures | 0 | 0 | 0 | 443000 | 443000 | 443000.0076 |  |  | 443000.0076 | ODS
2.6.1.2 | Reinforced concrete structure of the above-ground part of the B1 facility - delivery and assembly of ECR 10 prefabricated elements | 0 | 0 | 0 | 1275206 | 1275206.0044 | 1275206.0044 |  |  | 1275206.0044 | BETARD
2.6.1.3 | Structure, including platforms, platforms, ladders, canopies | 0 | 0 | 0 | 0 | 953352 | 953352 |  |  | 953352
2.6.1.3 | Structure, including platforms, walkways, ladders, roofing | 0 | 0 | 0 | 0 | 13046648 | 13046647.9997 |  |  | 13046647.9997 | NOWOSTAL
2.6.2 | Steel structure of the staircase in the B1.4 facility (change from the reinforced concrete structure in relation to the acquisition stage) | 470146 | 470146 | 470146 | 470146 | 470146 | 470146 |  |  | 470146
2.6.3 | Gantry beams | 425469 | 425469 | 425469 | 425469 | 44669 | 44669 |  |  | 44669
2.6.3.1 |  | 0 | 0 | 0 | 0 | 380800 | 380800 |  |  | 380800 | NOWOSTAL
|  | 24596491 | 24596491 | 24596491 | 24596491 | 24596491.0044 | 24596491.0118 | 0 | 0 | 24596491.0118
[6 empty] | -0.0044524 | -0.011771 |  |  | -0.011771
2.7 | Brick walls | 687451 | 687451 | 687451 | 687451 | 687451 | 687451 |  |  | 687451
|  | 687451 | 687451 | 687451 | 687451 | 687451 | 687451 | 0 | 0 | 687451
[6 empty] | 0 | 0 |  |  | 0
2.8 | Facades | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.8.1 | Parapet | 82476 | 82476 | 82476 | 82476 | 82476 | 82476 |  |  | 82476
2.8.2 | Steel-aluminum canopy | 120923 | 120923 | 120922.9998 | 120922.9998 | 120922.9998 | 120922.9998 |  |  | 120922.9998
2.8.3 | Aluminum-glass facade | 296487 | 296487 | 296487 | 296487 | 296487 | 296487 |  |  | 296487
2.8.4 | ETICS | 122038 | 122038 | 122038 | 122038 | 122038 | 122038 |  |  | 122038
2.8.5 | Flashings | 366599 | 366599 | 366598.9999 | 366598.9999 | 366598.9999 | 366598.9999 |  |  | 366598.9999
2.8.6 | Sheet metal cladding | 1172887 | 1172887 | 1172887.002 | 1172887.002 | 1172887.002 | 1172887.002 |  |  | 1172887.002
2.8.7 | Sandwich panel cladding | 5792280 | 5792280 | 5792280 | 5792280 | 5792280 | 5792280 |  |  | 5792280
2.8.8 | Fiber cement panel cladding | 241171 | 241171 | 241171.0002 | 241171.0002 | 241171.0002 | 241171.0002 |  |  | 241171.0002
2.8.9 | Substructures | 419580 | 419580 | 419580 | 419580 | 419580 | 419580 |  |  | 419580
2.8.10 | Soffit lining | 308662 | 308662 | 308662.0002 | 308662.0002 | 308662.0002 | 308662.0002 |  |  | 308662.0002
2.8.11 | Scaffolding | 77076 | 77076 | 77076 | 77076 | 77076 | 77076 |  |  | 77076
2.8.12 | Safety system | 150018 | 150018 | 150018.0003 | 150018.0003 | 150018.0003 | 150018.0003 |  |  | 150018.0003
2.8.13 | Shutters | 107601 | 107601 | 107601 | 107601 | 107601 | 107601 |  |  | 107601
|  | 9257798 | 9257798 | 9257798.0024 | 9257798.0024 | 9257798.0024 | 9257798.0024 | 0 | 0 | 9257798.0024
[6 empty] | 0 | 0 |  |  | 0
2.9 | Doors, windows, gates and hatches | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.9.1 | Gates | 1169929 | 1169929.002 | 1169929.002 | 1169929.002 | 1169929.002 | 1169929.002 |  |  | 1169929.002
2.9.2 | Interior doors | 433042 | 433042.0002 | 433042.0002 | 433042.0002 | 433042.0002 | 433042.0002 |  |  | 433042.0002
2.9.3 | Exterior doors | 164459 | 164458.9998 | 164458.9998 | 164458.9998 | 164458.9998 | 164458.9998 |  |  | 164458.9998
2.9.4 | Windows | 366536 | 366535.9998 | 366535.9998 | 366535.9998 | 366535.9998 | 366535.9998 |  |  | 366535.9998
2.9.5 | Bunker windows | 205428 | 205428 | 205428 | 205428 | 205428 | 205428 |  |  | 205428
2.9.6 | Hatches | 327191 | 327190.9998 | 327190.9998 | 327190.9998 | 327190.9998 | 327190.9998 |  |  | 327190.9998
|  | 2666585 | 2666585.0016 | 2666585.0016 | 2666585.0016 | 2666585.0016 | 2666585.0016 | 0 | 0 | 2666585.0016
[6 empty] | 0 | 0 |  |  | 0
2.10 | Roofs | 7198646 | 7198646 | 7198646.002 | 7198646.002 | 7198646.002 | 7198646.002 |  |  | 7198646.002
|  | 7198646 | 7198646 | 7198646.002 | 7198646.002 | 7198646.002 | 7198646.002 | 0 | 0 | 7198646.002
[6 empty] | 0 | 0 |  |  | 0
2.11 | Finishing works, including equipment and furniture | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.11.1 | Painting | 669443 | 669442.998 | 669442.998 | 669442.998 | 669442.998 | 669442.998 |  |  | 669442.998
2.11.2 | Furniture | 631074 | 631074 | 631074 | 631074 | 631074 | 631074 |  |  | 631074
2.11.3 | Tiles | 498448 | 498448.0002 | 498448.0002 | 498448.0002 | 498448.0002 | 498448.0002 |  |  | 498448.0002
2.11.4 | Raised floor | 621908 | 621907.998 | 621907.998 | 621907.998 | 621907.998 | 621907.998 |  |  | 621907.998
2.11.5 | Concrete floor + screed | 4432229 | 4432228.997 | 3381867.997 | 1631867.997 | 1631867.997 | 1631867.997 |  |  | 1631867.997
2.11.5.1 | Delivery of concrete mix with pumping service | 0 | 0 | 9891 | 0 | 0 | 0 |  |  | 0
2.11.5.1 | Delivery of concrete mix including pumping service ECR 9 rev 1 / ECR 12 | 0 | 0 | 1040470.0025 | 1050360.9975 | 1050360.9975 | 1050360.9975 |  |  | 1050360.9975 | BUSZREM / HOLCIM | 4502986603
2.11.5.1.1 | Reinforced concrete works | 0 | 0 | 0 | 14607 | 14607 | 14607 |  |  | 14607
2.11.5.1.1 | Reinforced concrete works - ECR 11 | 0 | 0 | 0 | 1735393 | 1735393 | 1735393 |  |  | 1735393 | AF KONSTRUKCJE
2.11.6 | Microcement floor | 133705 | 133705.0002 | 133705.0002 | 133705.0002 | 133705.0002 | 133705.0002 |  |  | 133705.0002
2.11.7 | Resin floor | 655175 | 655174.998 | 655174.998 | 655174.998 | 655174.998 | 655174.998 |  |  | 655174.998
2.11.8 | Suspended ceilings | 220670 | 220669.9998 | 220669.9998 | 220669.9998 | 220669.9998 | 220669.9998 |  |  | 220669.9998
2.11.9 | Segmented sliding wall | 65014 | 65014.0002 | 65014.0002 | 65014.0002 | 65014.0002 | 65014.0002 |  |  | 65014.0002
2.11.10 | Plasterboard wall, sandwich panel wall | 39027 | 39027 | 39027 | 39027 | 39027 | 39027 |  |  | 39027
2.11.11 | Glass wall | 75045 | 75045 | 75045 | 75045 | 75045 | 75045 |  |  | 75045
2.11.12 | Plastering | 1241085 | 1241085 | 1241085 | 1241085 | 1241085 | 1241085 |  |  | 1241085
2.11.13 | Carpet / polyamide | 87498 | 87498 | 87498 | 87498 | 87498 | 87498 |  |  | 87498
2.11.14 | Wall and column protection up to 2.5 m + hydrophobic protection | 186490 | 186490 | 186490 | 186490 | 186490 | 186490 |  |  | 186490
|  | 9556811 | 9556810.9914 | 9556810.9939 | 9556810.9889 | 9556810.9889 | 9556810.9889 | 0 | 0 | 9556810.9889
[6 empty] | 0 | 0 |  |  | 0
2.12 | Elevators | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.12.1 | Passenger and good elevator | 415350 | 415350 | 415350 | 415350 | 415350 | 415350 |  |  | 415350
2.12.2 | Passenger elevator | 98644 | 98644 | 98644 | 98644 | 98644 | 98644 |  |  | 98644
|  | 513994 | 513994 | 513994 | 513994 | 513994 | 513994 | 0 | 0 | 513994
[6 empty] | 0 | 0 |  |  | 0
2.13 | Weigh bridge | 551900 | 551900 | 551900 | 551900 | 551900 | 551900 |  |  | 551900
|  | 551900 | 551900 | 551900 | 551900 | 551900 | 551900 | 0 | 0 | 551900
[6 empty] | 0 | 0 |  |  | 0
2.14 | Roads and pavements | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.14.1 | Internal road | 4457840 | 4457840 | 4457840 | 4457840.002 | 4457840.002 | 4457840.002 |  |  | 4457840.002
2.14.2 | External road | 1833166 | 1833166 | 1833166 | 1698766.002 | 1448126.002 | 1448126.002 |  |  | 1448126.002
2.14.2.1 | Crushed aggregate ECD 46 | 0 | 0 | 0 | 134400 | 134400 | 134400 |  |  | 134400 | KSM Parsęcko | 4503012737
2.14.2.1 | External Road ECR 3 rev 1 | 0 | 0 | 0 | 0 | 250640 | 250640 |  |  | 250640 | MAR-KOP Marcin Mierzwa | 4502939064
2.14.3 | Pavement surface | 1112965 | 1112965 | 1112965 | 1112965 | 1112965 | 1112965 |  |  | 1112965
|  | 7403971 | 7403971 | 7403971 | 7403971.004 | 7403971.004 | 7403971.004 | 0 | 0 | 7403971.004
[6 empty] | 0 | 0 |  |  | 0
2.15 | Greenery | 1097187 | 1097187 | 1097187 | 1097187 | 1097187 | 1097187 |  |  | 1097187
|  | 1097187 | 1097187 | 1097187 | 1097187 | 1097187 | 1097187 | 0 | 0 | 1097187
[6 empty] | 0 | 0 |  |  | 0
2.16 | Fencing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
2.16.1 | Delivery of fences, gates and wickets | 321395 | 321395 | 321395 | 321395 | 321395 | 321395 |  |  | 321395
2.16.2 | Installation of fences, gates and wickets | 416382 | 416382 | 416382 | 416382 | 416382 | 416382 |  |  | 416382
|  | 737777 | 737777 | 737777 | 737777 | 737777 | 737777 | 0 | 0 | 737777
[6 empty] | 0 | 0 |  |  | 0

## 3_Electrical Works
|  | BUDGET APERTURA | BUDGET 02 | BUDGET 07 | BUDGET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 | ORDINATO | DA ORDINARE EXTRA | TOTALE CON FORECAST |  | 58345340
3 | ELECTRICAL WORKS | 58345340 | 58345339.9993 | 58345340 | 58345340 | 58345340 | 58345340 | 0 | 0 | 58345340
[6 empty] | 0 | 0 |  |  | 0
[11 empty] | Ordered | 36070000
[11 empty] | Negotiation + Buffer | 2016200
|  |  | SAVINGS | [7 empty] | Planned | 20259140
|  |  | EXTRA | [7 empty] | Extra | 0
[11 empty] | (Buffer) | 2016200
3.1 | Electrical installation | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
3.1.1 | Delivery and installation of electrical equipment | 29982000 | 29982000 | 1700000 | 1700000 | 1700000 | 1700000 |  |  | 1700000
3.1.1.1 | Delivery and installation of electrical equipment | 0 | 0 | 28282000 | 28282000 | 28282000 | 28282000 |  |  | 28282000 | ELEKTROSERV - ZAP | ok
3.1.2 | Electrical heat treacing of piping - hot part | 742140 | 742140 | 742140 | 742140 | 742140 | 742140 |  |  | 742140
3.1.3 | Aviation warning lights | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 |  |  | 140000
3.1.4 | Fire detection and alarm system ( electrical&teletechnical part ) | 980000 | 980000 | 980000 | 980000 | 980000 | 980000 |  |  | 980000
3.1.5 | Smoke extraction from waste bunker and tipping hall (electrical&teletechnical part ) | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 |  |  | 175000
|  | 32019140 | 32019140 | 32019140 | 32019140 | 32019140 | 32019140 | 0 | 0 | 32019140
[6 empty] | 0 | 0 |  |  | 0
3.2 | Teletechnical installations | 2579200 | 0 | 0 | 0 | 0 | 0 |  |  | 0
3.2.1 | Teletechnical installations | 0 | 2579200 | 2579200 | 2579200 | 2579200 | 2579200 |  |  | 2579200 | ELEKTROSERV - ZAP | ok
|  | 2579200 | 2579200 | 2579200 | 2579200 | 2579200 | 2579200 | 0 | 0 | 2579200
[6 empty] | 0 | 0 |  |  | 0
3.3 | GPO/GPZ power supply | 13510000 | 13510000 | 13510000 | 13510000 | 13510000 | 13510000 |  |  | 13510000
|  | 13510000 | 13510000 | 13510000 | 13510000 | 13510000 | 13510000 | 0 | 0 | 13510000
[6 empty] | 0 | 0 |  |  | 0
3.3 | I&C works | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
3.4.1 | Automation system and instrumentation, communication networks and control room devices | 5525000 | 686199.9993 | 316200 | 316200 | 316200 | 316200 |  |  | 316200
3.4.1.1 | Automation system and instrumentation, communication networks and control room devices | 0 | 4838800 | 5208800 | 5208800 | 5208800 | 5208800 |  |  | 5208800 | ELEKTROSERV - ZAP | ok
3.4.2 | DCS System | 2752000 | 2752000 | 2752000 | 2752000 | 2752000 | 2752000 |  |  | 2752000
3.4.3 | Emission monitoring system (CEMS) | 1960000 | 1960000 | 1960000 | 1960000 | 1960000 | 1960000 |  |  | 1960000
|  | 10237000 | 10236999.9993 | 10237000 | 10237000 | 10237000 | 10237000 | 0 | 0 | 10237000
[6 empty] | 0 | 0 |  |  | 0

## 4_Sanitary works and FF
|  | BUDHET APERTURA | BUDHET 02 | BUDHET 07 | BUDHET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 | ORDINATO | DA ORDINARE EXTRA | TOTALE CON FORECAST |  | 21293319.0015
4 | SANITARY WORKS AND FIRE-FIHHTINH SYSTEM | 21293319 | 21293319 | 21293319.0015 | 21293319.0015 | 21293319.0015 | 21293319.0015 | 0 | 0 | 21293319.0015
[6 empty] | 0 | 0 |  |  | 0
[11 empty] | Ordered | 0
|  |  | SAVINH | [5 empty] | SAVINH |  | NeHotiation | 0
|  |  | EXTRA | [5 empty] | EXTRA |  | Planned | 21293319.0015
[10 empty] | 0 | Extra | 0
[11 empty] | (Buffer) | 0
4.1 | Deodorization system | 1009700 | 1009700 | 1009700 | 1009700 | 1009700 | 1009700 |  |  | 1009700
|  | 1009700 | 1009700 | 1009700 | 1009700 | 1009700 | 1009700 | 0 | 0 | 1009700
[6 empty] | 0 | 0 |  |  | 0
4.2 | FirefiHhtinH system | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
4.2.1 | Fire detection and alarm system | 2211870 | 2211870 | 2211870 | 2211870 | 2211870 | 2211870 |  |  | 2211870
4.2.2 | FirefiHhtinH water tank | 275700 | 275700 | 275700 | 275700 | 275700 | 275700 |  |  | 275700
4.2.3 | FirefiHhtinH water pumpinH | 715920 | 715920 | 715920 | 715920 | 715920 | 715920 |  |  | 715920
4.2.4 | FirefiHhtinH water external distribution, hoses, sprinklers | 821016 | 821016 | 821016 | 821016 | 821016 | 821016 |  |  | 821016
4.2.5 | Installation of internal hydrants in buildinHs B1 and B2 | 240990 | 240990 | 240990 | 240990 | 240990 | 240990 |  |  | 240990
4.2.6 | Wireless radio controller system type WRC, Hun control | 45500 | 45500 | 45500 | 45500 | 45500 | 45500 |  |  | 45500
4.2.7 | FirefiHhtinH water external distribution, hoses, sprinklers | 542750 | 542750 | 542750.0001 | 542750.0001 | 542750.0001 | 542750.0001 |  |  | 542750.0001
4.2.8 | Dry bunker sprinkler system. Installation of water and foam cannons in the bunker hall, and assembly of the valve sub-control unit. | 1925350 | 1925350 | 1925350 | 1925350 | 1925350 | 1925350 |  |  | 1925350
4.2.9 | Natural Has (if any) and ammonia detection system | 285000 | 285000 | 284999.9999 | 284999.9999 | 284999.9999 | 284999.9999 |  |  | 284999.9999
4.2.10 | Smoke extraction from waste bunker and tippinH hall | 1178293 | 1178293 | 1178292.997 | 1178292.997 | 1178292.997 | 1178292.997 |  |  | 1178292.997
|  | 8242389 | 8242389 | 8242388.997 | 8242388.997 | 8242388.997 | 8242388.997 | 0 | 0 | 8242388.997
[6 empty] | 0 | 0 |  |  | 0
4.3 | Sanitary installations | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
4.3.1 | Boiler room roof ventilators and wall shutters | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 |  |  | 1500000
4.3.2 | HVAC for the technoloHical buildinHs | 3107033 | 3107033 | 3107032.999 | 3107032.999 | 3107032.999 | 3107032.999 |  |  | 3107032.999
4.3.3 | HVAC for the other buildinHs | 1548256 | 1548256 | 1548256.002 | 1548256.002 | 1548256.002 | 1548256.002 |  |  | 1548256.002
4.3.4 | Service water storaHe, pumpinH, underHround and external distribution + Sanitary facilities (toilets, showers, etc.) | 1053444 | 1053444 | 1053444 | 1053444 | 1053444 | 1053444 |  |  | 1053444
4.3.5 | Sanitary water, connection to source, storaHe, pumpinH, underHround and external distribution | 637613 | 637613 | 637613 | 637613 | 637613 | 637613 |  |  | 637613
4.3.6 | EmerHency showers and eye washers | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 |  |  | 10000
4.3.7 | Sanitary waste water collection, treatment and connection to discharHe point | 624272 | 624272 | 624272.0004 | 624272.0004 | 624272.0004 | 624272.0004 |  |  | 624272.0004
4.3.8 | Waste water collection and connection to discharHe point | 200969 | 200969 | 200969.0001 | 200969.0001 | 200969.0001 | 200969.0001 |  |  | 200969.0001
4.3.9 | Rain water and snowmelt collection, treatment and connection to discharHe point | 3359643 | 3359643 | 3359643.003 | 3359643.003 | 3359643.003 | 3359643.003 |  |  | 3359643.003
|  | 12041230 | 12041230 | 12041230.0045 | 12041230.0045 | 12041230.0045 | 12041230.0045 | 0 | 0 | 12041230.0045
[6 empty] | 0 | 0 |  |  | 0

## 5_Mechanical and technological
|  | BUDGET APERTURA | BUDGET 02 | BUDGET 07 | BUDGET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 | ORDINATO | DA ORDINARE EXTRA | TOTALE CON FORECAST |  | 258666646.0016
5 | MECHANICAL AND TECHNOLOGICAL WORKS | 258666646 | 258666645.9977 | 258666645.9975 | 258666645.9992 | 258666645.9971 | 258666646.0016 | 0 | 0 | 258666646.0016
[6 empty] | 0.0003953 | -0.0041679 |  |  | -0.0041679
[11 empty] | Ordered | 153053763.0559
[11 empty] | Negotiation + buffer | 6615897.95
|  | SAVINGS | 0 | 0 | 0 | 0 | 0 |  | SAVINGS | 0 | Planned | 98996984.9957
|  | EXTRA | 0 | 0 | 0 | 0 | 0 |  | EXTRA | 0 | Extra | 0
[11 empty] | (Buffer) | 6615897.95
5.1 | Reception | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.1.1 | Radioactivity detector | 185000 | 185000 | 185000 | 185000 | 185000 | 185000 |  |  | 185000
|  | 185000 | 185000 | 185000 | 185000 | 185000 | 185000 | 0 | 0 | 185000
[6 empty] | 0 | 0 |  |  | 0
5.2 | Waste bunker | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.2.1 | Overhead crane, grab and operator seat + Spare Grab - ECR 14 | 9072785 | 9072785 | 9072785 | 9072785 | 9072785 | 9072785 |  |  | 9072785 | ZBUD | 4503036767
5.2.2 | Trapdoors for grab maintenance | 81600 | 81600 | 81600 | 81600 | 81600 | 81600 |  |  | 81600
|  | 9154385 | 9154385 | 9154385 | 9154385 | 9154385 | 9154385 | 0 | 0 | 9154385
[6 empty] | 0 | 0 |  |  | 0
5.3 | Furnace | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.3.1 | Furnace charging hopper + Furnace supporting steel structure + Complete grate fired furnace with waste feeding system + Hoppers under grate | 33755000 | 33754999.9978 | 33754999.9978 | 33755000.0044 | 33755000.0044 | 33755000.0011 |  |  | 33755000.0011 | TM.E. S.p.A - Termomeccanica Ecologia
5.3.2 | Primary and secondary air fan, Flue gas recirculation fan, ID Fan | 595000 | 595000 | 595000 | 595000 | 595000 | 595000 |  |  | 595000 | OWENT | 4503139940
5.3.3 | Primary & secondary air heat exchanger | 1281400 | 1281400 | 1281400 | 1281400 | 1281400 | 1281400 |  |  | 1281400 | AS TECHNOLOGIE | 4503139820
5.3.4 | Primary / secondary air ducts + Flue gas recirculation ducts + Auxiliary burners ducts + Supporting structures | 2502500 | 2502500 | 2502500 | 2502500 | 2502500 | 2502500 |  |  | 2502500
5.3.5 | Fire curtain for primary air opening | 100000 | 99999.9999 | 99999.9999 | 99999.9999 | 99999.9999 | 99999.9999 |  |  | 99999.9999
5.3.6 | Primary & secondary air dampers | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 |  |  | 220000
5.3.7 | Flue gas recirculation dampers | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 |  |  | 40000
5.3.8 | Camera for furnace monitoring | 51600 | 51600 | 51600 | 51600 | 51600 | 51600 |  |  | 51600
|  | 38545500 | 38545499.9977 | 38545499.9977 | 38545500.0043 | 38545500.0043 | 38545500.001 | 0 | 0 | 38545500.001
[6 empty] | 0 | 0.0033333 |  |  | 0.0033333
5.4 | Boiler | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.4.1 | Boiler - pressure parts | 54332011 | 54332011 | 54332011 | 54332011 | 8342011 | 4948411 |  |  | 4948411
5.4.1.1 | Boiler - ECR 13 | 0 | 0 | 0 | 0 | 45990000 | 45990000 |  |  | 45990000 | SEFAKO | 4503036513
5.4.1.2 | Burners including fans | 0 | 0 | 0 | 0 | 0 | 17900 |  |  | 17900
5.4.1.2 | Burners including fans - ECR 21 | 0 | 0 | 0 | 0 | 0 | 492100 |  |  | 492100 | BCE
5.4.1.3 | Primary & secondary air heat exchanger - ECR 22 | 0 | 0 | 0 | 0 | 0 | 1118600 |  |  | 1118600 | AS TECHNOLOGIE | 4503139820
5.4.1.4 | Primary and secondary air fan, Flue gas recirculation fan, ID Fan - ECR 23 | 0 | 0 | 0 | 0 | 0 | 1765000 |  |  | 1765000 | OWENT | 4503139940
5.4.2 | Boiler - supporting structure including walkways - ECR 16 | 6374147 | 6374147 | 6374147 | 6374147 | 6374147 | 6374147 |  |  | 6374147 | NOWOSTAL
5.4.3 | Fly ash extraction system for the boiler and conveyors | 4260000 | 4260000 | 4260000 | 4260000 | 4260000 | 4260000 |  |  | 4260000
5.4.4 | Sampling system | 1010500 | 1010500 | 1010500 | 1010500 | 1010500 | 1010500 |  |  | 1010500
5.4.5 | Chemical dosing for the boiler | 223600 | 223600 | 223600 | 223600 | 223600 | 223600 |  |  | 223600
5.4.6 | Compensator between boiler and ECO | 129000 | 129000 | 129000 | 129000 | 129000 | 129000 |  |  | 129000
|  | 66329258 | 66329258 | 66329258 | 66329258 | 66329258 | 66329258 | 0 | 0 | 66329258
[6 empty] | 0 | 0 |  |  | 0
5.5 | Refractory | 3993000 | 3993000 | 3993000 | 3993000 | 3993000 | 3993000 |  |  | 3993000
|  | 3993000 | 3993000 | 3993000 | 3993000 | 3993000 | 3993000 | 0 | 0 | 3993000
[6 empty] | 0 | 0 |  |  | 0
5.6 | Burners including fans | 1062800 | 1062800 | 1062800 | 1062800 | 1062800 | 1062800 |  |  | 1062800 | BCE
|  | 1062800 | 1062800 | 1062800 | 1062800 | 1062800 | 1062800 | 0 | 0 | 1062800
[6 empty] | 0 | 0 |  |  | 0
5.7 | Flue gas treatment (FGT) | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.7.1 | SNCR DeNOx system including silo, pumps | 1090000 | 1090000 | 1090000 | 1089999.999 | 1089999.999 | 1089999.999 |  |  | 1089999.999
5.7.2 | Flue gas treatment (FGT): Bag filter, Reactor, DeNOx, Flue gas condensation, Lime and activated carbon silos, dosing system | 33755000 | 33755000 | 33755000 | 33755000 | 33755000 | 33755000 |  |  | 33755000 | TM.E. S.p.A - Termomeccanica Ecologia
5.7.3 | Bag filters delivery | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 |  |  | 400000
5.7.4 | Fly ash silos | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 |  |  | 2000000
|  | 37245000 | 37245000 | 37245000 | 37244999.999 | 37244999.999 | 37244999.999 | 0 | 0 | 37244999.999
[6 empty] | 0 | 0 |  |  | 0
5.8 | Bottom ash extraction | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.8.1 | Chain conveyor under grate + Bottom ash extractor + Vibrating table / bulk screen | 1567228 | 1567228 | 1567227.9999 | 1567227.9999 | 1567227.9999 | 118828 |  |  | 118828
5.8.1 | Prefabrication, delivery, and commissioning of a system for removing bottom ash and slag ECR 17 | 0 | 0 | 0 | 0 | 0 | 1448400 |  |  | 1448400 | LOIBL | 4503106362
5.8.2 | Belt conveyors | 2347800 | 2347800 | 2347800 | 2347800 | 2347800 | 2347800 |  |  | 2347800
|  | 3915028 | 3915028 | 3915027.9999 | 3915027.9999 | 3915027.9999 | 3915028 | 0 | 0 | 3915028
[6 empty] | 0 | -0.0001 |  |  | -0.0001
5.9 | Bottom ash / slag valorization | 8271000 | 8271000 | 8271000 | 8271000 | 8271000 | 8271000 |  |  | 8271000
|  | 8271000 | 8271000 | 8271000 | 8271000 | 8271000 | 8271000 | 0 | 0 | 8271000
[6 empty] | 0 | 0 |  |  | 0
5.10 | Steam turbine, thermal cycle & district heating network | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.10.1 | Steam turbine - gear box - generator. Including accessories: oil system, coolers, insulation, pipes and valves, control panel, protection panel, synchro system etc. | 13374290 | 13374290 | 13374290 | 13374290 | 13374290 | 394396 |  |  | 394396
5.10.1.1 | Steam turbine - gear box - generator. Including accessories: oil system, coolers, insulation, pipes and valves, control panel, protection panel, synchro system etc. - ECR 19 | 0 | 0 | 0 | 0 | 0 | 12979894 |  |  | 12979894 | TRIVIENI TURBINE | 4503120533
5.10.2 | Auxiliary crane and hoists for the maintenance of the steam turbine | 300000 | 300000 | 300000 | 300000 | 222785 | 222785 |  |  | 222785
5.10.2 | Gripper service flaps - ECR 14 | 0 | 0 | 0 | 0 | 77215 | 77215 |  |  | 77215 | ZBUD | 4503036767
5.10.3 | Air cooled condenser | 9000000 | 9000000 | 9000000.002 | 9000000.002 | 9000000.002 | 9000000.002 |  |  | 9000000.002
5.10.4 | Feed water tank and Deaerator | 1000000 | 1000000 | 999999.999 | 999999.999 | 999999.999 | 267260 |  |  | 267260
5.10.4.1 | Feed water tank and Deaerator ECR 18 | 0 | 0 | 0 | 0 | 0 | 732740 |  |  | 732740 | ESTANC AS | 4503121635
5.10.5 | Piping, fitting and supports | 18664194 | 18664194 | 18664194 | 18664194 | 18664194 | 18664194 |  |  | 18664194
5.10.6 | Chemical dossing for thermal cycle and district heating | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 |  |  | 550000
5.10.7 | Main cooler | 2000000 | 2000000 | 2000000.002 | 2000000.002 | 2000000.002 | 2000000.002 |  |  | 2000000.002
5.10.8 | Cooler tank, condensate tank | 1000000 | 1000000 | 999999.999 | 999999.999 | 999999.999 | 999999.999 |  |  | 999999.999
5.10.9 | Water pressure stabilization system | 350000 | 350000 | 350000.0001 | 350000.0001 | 350000.0001 | 0 |  |  | 0
5.10.9.1 | Feed water tank and Deaerator ECR 18 | 0 | 0 | 0 | 0 | 0 | 350000 |  |  | 350000 | ESTANC AS | 4503121635
5.10.10 | Water tank 100 m3 | 200000 | 200000 | 199999.9998 | 199999.9998 | 199999.9998 | 199999.9998 |  |  | 199999.9998
5.10.11 | Heat exchangers 2 pcs., LP pre-heater, external economizer | 3242866 | 3242866 | 3242866 | 3242866 | 3242866 | 3242866 |  |  | 3242866
5.10.12 | Stabilising pumps 2 x 100%, network pumps 3 x 50%, condensate pumps 2 x 100%, feed water pumps 3 pcs., cooling pumps | 5517325 | 5517325 | 5517325 | 5517325 | 5517325 | 5517325 |  |  | 5517325
5.10.13 | Valves ( Manual, motorized , safety, ON-OF , control etc… ) | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.10.13.1 | Manual valves | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 |  |  | 2200000
5.10.13.2 | Motorized valves | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  |  | 1000000
5.10.13.3 | Safety valves | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 |  |  | 200000
5.10.13.4 | ON/OFF valves | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 |  |  | 400000
5.10.13.5 | Control valves | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 |  |  | 700000
|  | 59698675 | 59698675 | 59698675.0019 | 59698675.0019 | 59698675.0019 | 59698675.0028 | 0 | 0 | 59698675.0028
[6 empty] | 0 | -0.0009 |  |  | -0.0009
5.11 | Stack | 1850000 | 1850000 | 1850000 | 1850000 | 346317.95 | 346317.95 |  |  | 346317.95
5.11.1 | Stack - ECR 15 | 0 | 0 | 0 | 0 | 1503682.05 | 1503682.05 |  |  | 1503682.05 | AVANTEA STEEL SOLUTIONS | 4503064698
|  | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 0 | 0 | 1850000
[6 empty] | 0 | 0 |  |  | 0
5.12 | Boiler and piping insulation | 11000000 | 11000000 | 11000000 | 10999999.998 | 10999999.998 | 10999999.998 |  |  | 10999999.998
|  | 11000000 | 11000000 | 11000000 | 10999999.998 | 10999999.998 | 10999999.998 | 0 | 0 | 10999999.998
[6 empty] | 0 | 0 |  |  | 0
5.13 | Ancillary systems | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.13.1 | Compressors 2 x 50% + 1 x 50% | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 |  |  | 1500000
5.13.2 | Auxiliary fuel tank (light oil/diesel oil) | 200000 | 200000 | 200000 | 200000.0002 | 200000.0002 | 200000.0002 |  |  | 200000.0002
5.13.3 | Light oil unloading installation with TDT documentation approval | 200000 | 200000 | 200000 | 200000.0002 | 200000.0002 | 200000.0002 |  |  | 200000.0002
5.13.4 | Auxiliary fuel pumps (light oil/diesel oil), demi water pumps, other water pumps | 3337500 | 3337500 | 3337500 | 3337500 | 3337500 | 3337500 |  |  | 3337500
5.13.5 | Auxiliary system pipelines – light oil, demineralised water, chemical dosing, compressed air | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 |  |  | 2600000
5.13.6 | Auxiliary hoists for maintenance | 350000 | 350000 | 350000 | 349999.9998 | 349999.9998 | 349999.9998 |  |  | 349999.9998
5.13.7 | Demi water system including storage tank 100m3 and piping | 3010000 | 3010000 | 3010000 | 3010000 | 3010000 | 3010000 |  |  | 3010000
5.13.8 | Chemical dosing system for thermal cycle and district heating | 838500 | 838500 | 838500 | 838500 | 838500 | 838500 |  |  | 838500
5.13.9 | Grate cooling system | 731000 | 731000 | 731000 | 730999.9998 | 730999.9998 | 730999.9998 |  |  | 730999.9998
5.13.10 | Centralized cleaning system for Boiler house | 800000 | 800000 | 800000 | 799999.998 | 799999.998 | 799999.998 |  |  | 799999.998
|  | 13567000 | 13567000 | 13567000 | 13566999.998 | 13566999.998 | 13566999.998 | 0 | 0 | 13566999.998
[6 empty] | 0 | 0 |  |  | 0
5.14 | Others | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
5.14.1 | Scaffoldings | 1000000 | 300000 | 300000 | 300000 | 300000 | 300000 |  |  | 300000
5.14.1.1 | Scaffoldings - ECR 5 | 0 | 700000 | 700000 | 700000 | 699999.9979 | 700000.0048 |  |  | 700000.0048 | AS Rusztowania | Ok
5.14.2 | Mechanical installation of technological equipment | 1500000 | 1500000 | 1499999.998 | 1499999.998 | 1499999.998 | 1499999.998 |  |  | 1499999.998
5.14.3 | Devices support structures | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  |  | 1000000
5.14.4 | Installation marking | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 |  |  | 350000
|  | 3850000 | 3850000 | 3849999.998 | 3849999.998 | 3849999.9959 | 3850000.0028 | 0 | 0 | 3850000.0028
[6 empty] | 0.002069 | -0.0048276 |  |  | -0.0048276

## 6_ Commissioning
|  | BUDGET APERTURA | BUDGET 02 | BUDGET 07 | BUDGET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 | ORDINATO EXTRA | DA ORDINARE EXTRA | TOTALE CON FORECAST |  | 8499999.9971
6 | COLD AND HOT COMMISSIONING & TRIAL RUN OF TECHNOLOGICAL EQUIPMENT | 8500000 | 8500000 | 8499999.9984 | 8499999.9971 | 8499999.9971 | 8499999.9971 | 0 | 0 | 8499999.9971
[7 empty] | 0 |  |  | 0
[11 empty] | Ordered | 100000
[11 empty] | Negotiation + buffer | 399999.9984
|  |  | SAVINGS | [5 empty] | SAVINGS |  | Planned | 7999999.9987
|  |  | EXTRA | [5 empty] | EXTRA |  | Extra | 0
[11 empty] | (Buffer) | 399999.9984
6.1 | Cold & Hot Commissioning + Trial Run - Staff | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
6.1.1 | Start-up personnel | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 |  |  | 5000000
6.1.2 | Boiler boiling | 200000 | 200000 | 200000 | 200000.0001 | 200000.0001 | 200000.0001 |  |  | 200000.0001
6.1.3 | Steam blowing | 550000 | 550000 | 550000 | 549999.999 | 549999.999 | 549999.999 |  |  | 549999.999
6.1.4 | Nitrogenation | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  | 50000
|  | 5800000 | 5800000 | 5800000 | 5799999.9991 | 5799999.9991 | 5799999.9991 | 0 | 0 | 5799999.9991
[6 empty] | 0 | 0 |  |  | 0
6.2 | Media, reagents for start-up and commissioning | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
6.2.1 | Fuel (light oil) | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 |  |  | 500000
6.2.2 | Nitrogen cylinders | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  | 50000
6.2.3 | Handling and disposal of bottom and fly ash | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 |  |  | 150000
6.2.4 | Chemical supplies | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  | 50000
6.2.5 | Lime supplies | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 |  |  | 350000
6.2.6 | Active carbon supplies | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 |  |  | 200000
6.2.7 | Disposal of waste after testing - discharge of waste water | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 |  |  | 150000
|  | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 0 | 0 | 1450000
[6 empty] | 0 | 0 |  |  | 0
6.3 | Training | 500000 | 500000 | 500000 | 499999.9998 | 499999.9998 | 499999.9998 |  |  | 499999.9998
|  | 500000 | 500000 | 500000 | 499999.9998 | 499999.9998 | 499999.9998 | 0 | 0 | 499999.9998
[6 empty] | 0 | 0 |  |  | 0
6.4 | Spare parts (guarantee period 48 msc) | 500000 | 500000 | 399999.9984 | 399999.9984 | 399999.9984 | 399999.9984 |  |  | 399999.9984
6.4.1 | Warranty extension for electrical works | 0 | 0 | 100000 | 100000 | 100000 | 100000 |  |  | 100000 | ELEKTROSERV - ZAP | ok
|  | 500000 | 500000 | 499999.9984 | 499999.9984 | 499999.9984 | 499999.9984 | 0 | 0 | 499999.9984
[6 empty] | 0 | 0 |  |  | 0
6.5 | Compliance tests and simulations of the generation module | 150000 | 150000 | 150000 | 149999.9998 | 149999.9998 | 149999.9998 |  |  | 149999.9998
|  | 150000 | 150000 | 150000 | 149999.9998 | 149999.9998 | 149999.9998 | 0 | 0 | 149999.9998
[6 empty] | 0 | 0 |  |  | 0
6.6 | Operating instructions | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 |  |  | 100000
|  | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 100000
[6 empty] | 0 | 0 |  |  | 0

## 7_Backup
|  | BUDGET APERTURA | BUDGET 02 | BUDGET 07 | BUDGET 14 (B0 approvato Mar 26) | BUDGET 17 | BUDGET 19 | ORDINATO EXTRA | DA ORDINARE EXTRA | TOTALE CON FORECAST |  | 952781
7 - 8 | ALIGNMENT TO TCO VALUES / BACKUP | 952781 | 952781 | 952781 | 952781 | 952781 | 952781 | 0 | 0 | 952781
[7 empty] | 0 |  |  | 0
[11 empty] | Ordered | 723162.81
[11 empty] | Negotiation | 229618.19
|  |  | SAVINGS | [5 empty] | SAVINGS |  | Planned | 0
|  |  | EXTRA | [5 empty] | EXTRA |  | Extra | 0
[11 empty] | (Buffer) | 0
7.1 | Backup | 538352 | 216139.19 | 216139.19 | 216139.19 | 216139.19 | 216139.19 |  |  | 216139.19
7.1.1 | Earthmoving robots - ECR 3 | 0 | 322212.81 | 322212.81 | 322212.81 | 322212.81 | 322212.81 |  |  | 322212.81 | MAR-KOP Marcin Mierzwa | 4502939064
|  | 538352 | 538352 | 538352 | 538352 | 538352 | 538352 | 0 | 0 | 538352
[6 empty] | 0 | 0 |  |  | 0
8.1 | Backup | 414429 | 14429 | 13479 | 13479 | 13479 | 13479 |  |  | 13479
8.1.1 | Temporary traffic organization - ECD 34 | 0 | 0 | 950 | 950 | 950 | 950 |  |  | 950 | PROJBUD | 4502971480
8.1.2 | Obtaining decisions and permits - ECR 4 | 0 | 400000 | 400000 | 400000 | 400000 | 400000 |  |  | 400000 | KaBo | 4502946461
|  | 414429 | 414429 | 414429 | 414429 | 414429 | 414429 | 0 | 0 | 414429
[6 empty] | 0 | 0 |  |  | 0