## 00_Report
Wloclawek - Waste-to-Energy Project Dashboard Report
Generato: 2026-05-25 12:41 |  |  |  | Budget: Budget.xlsm
Report aggiornato al momento del download: i dati derivano dai file Excel presenti in data/current.
KPI | Value | KPI | Value |  |  | baseline_direct | 501457853
Costi diretti |  | Budget attuale (col. AB) |  |  |  | updated_direct | 501457853.02
Costi indiretti |  | Delta % |  |  |  | baseline_indirect | 40355205
Costi garanzia, difetti, imprevisti: |  | Costi garanzia, difetti, imprevisti: |  |  |  | updated_indirect | 40036817.27
Ricavi base |  | Ricavi base |  |  |  | baseline_contingency | 22098535
Margine |  | Margine |  |  |  | updated_contingency | 22098535.15
Ordini chiusi ultimi 3 mesi |  | Prossimi ordini 3 mesi |  |  |  | baseline_revenue | 627086000
Milestones penalizzate |  | Da ordinare / Planned |  |  |  | updated_revenue | 627086000
[6 empty] | baseline_margin | 63174407
[6 empty] | updated_margin | 63492794.56
[6 empty] | baseline_pct_costs | 0
Curva S degli ordini rispetto al pianificato |  |  |  |  | Mix ordini diretti - valore e numero pacchetti | updated_pct_costs

## 01_Budget_Delta
Budget Delta - Totale e WBS
I dati sono linkati al foglio 07_Source_Budget_Delta. Budget 0 = colonna I del Budget; Budget attuale = colonna AB; Delta AB-I e Delta % sono formule.
Budget 0 - col. I | Budget attuale - col. AB | Delta AB-I | Delta %
Section | WBS | Description PL | Description EN | Budget 0 - col. I | Budget attuale - col. AB | Delta AB-I | Delta %

## 02_PORR_Production
Month | PORR declared production / Budget monthly | Cumulative
Year | Annual total declared
2025
2026
2027
2028

## 03_Milestones
Nota logica
Le milestone qui riportate sono considerate “penalizzate” perché sono classificate nella sezione “Milestones penalizzate” del file Programma Wloclawek_Milestones.xlsx. Non è un calcolo automatico della penale scattata: indica milestone contrattualmente soggette a penale / penalizzabili.
No. | Milestone | Start date | Finish date
1 | Water pressure test | 2027-10-16 | 2027-10-16
2 | Placement of the turbo-generator on the foundation | 2027-09-16 | 2027-09-16
3 | Measurement of guaranteed parameters A | 2028-06-23 | 2028-06-23
4 | Handover of the ITPO project to operation | 2028-06-30 | 2028-06-30

## 04_Orders_3M
Type | WBS | Package | Status | Date | Value | Buyer

## 05_Status_Mix
Status group | Count | Value | % Value | % Count
Nota: perimetro limitato ai soli ordini diretti (root group 1-7); esclusi indiretti/servizi e opportunities/risks.

## 06_S_Curve_Data
Month | Label | Procurement monthly | Procurement cumulative | Budget monthly | Budget cumulative | Contracted monthly | Contracted cumulative | Current marker

## 07_Source_Budget_Delta
Nota origine dati
Dati estratti dal file Budget in data/current: Budget.xlsm, sheet Włocławek Budget. Totale Budget 0 = cella I12; Budget attuale = cella AB12. La tabella WBS sotto riporta le righe top-level trovate in colonna A: WBS 1-8 della sezione costi diretti e WBS 1-17 della sezione riepilogo/finanziaria. I valori Budget 0 e Budget attuale derivano rispettivamente dalle colonne I e AB; Delta e Delta % sono formule nel report.
Metric | Value | Source file | Source sheet | Source cell
Budget 0 - col. I | 505343424 | Budget.xlsm | Włocławek Budget | I12
Budget attuale - col. AB | 501457853.0157 | Budget.xlsm | Włocławek Budget | AB12
Section | WBS | Description PL | Description EN | Budget 0 - col. I | Budget attuale - col. AB | Delta AB-I | Delta % | Source row | Source cells
Direct cost / root budget group | 1 | PROJEKTOWANIE | DESIGN | 30550000 | 27170000.0046 |  |  | 13 | I13 / AB13
Direct cost / root budget group | 2 | Roboty branży budowlano-konstrukcyjnej | Civil works | 113409768 | 108109767.0078 |  |  | 38 | I38 / AB38
Direct cost / root budget group | 3 | BRANŻA ELEKTRYCZNA | ELECTRICAL WORKS | 10912000 | 58345340 |  |  | 149 | I149 / AB149
Direct cost / root budget group | 4 | Roboty branży sanitarnej i ppoż | Sanitary works and fire-fighting system | 34223555 | 21293319.0015 |  |  | 166 | I166 / AB166
Direct cost / root budget group | 5 | Roboty branży mechanicznej i technologicznej | Mechanical and technological works | 293798902 | 258666645.9971 |  |  | 191 | I191 / AB191
Direct cost / root budget group | 6 | Zimny i gorący rozruch, Ruch próbny instalacji technologicznych | Cold and hot commissioning & Trial run of technological equipment | 8499199 | 8499999.9971 |  |  | 265 | I265 / AB265
Financial summary / WBS 1-17 | 7 | Wyrównanie do wartości z TCO / Rezerwa | Alignment to TCO values / Backup | 0 | 538352 |  |  | 284 | I284 / AB284
Financial summary / WBS 1-17 | 8 | Pozostałe koszty |  | 0 | 414429 |  |  | 287 | I287 / AB287
Financial summary / WBS 1-17 | 1 | TKW |  | 505757853 | 501457853.0157 |  |  | 291 | I291 / AB291
Financial summary / WBS 1-17 | 1 | PERSONEL | STAFF | 0 | 0 |  |  | 298 | I298 / AB298
Financial summary / WBS 1-17 | 2 | TKW Razem | Direct + indirect costs | 546148867.15 | 563593205.4394 |  |  | 440 | I440 / AB440
Financial summary / WBS 1-17 | 3 | Kwota narzutów kalkulacyjnych |  | 85237132.85 | 63492794.56 |  |  | 441 | I441 / AB441
Financial summary / WBS 1-17 | 4 | % narzutów kalkulacyjnych |  | 0.15607 | 0.11266 |  |  | 442 | I442 / AB442
Financial summary / WBS 1-17 | 5 | Zlecenie otrzymane/Planowany przerób |  | 631386000 | 627086000 |  |  | 452 | I452 / AB452
Financial summary / WBS 1-17 | 6 | Podwykonawstwo wewn. udzielone |  | 0 | 0 |  |  | 453 | I453 / AB453
Financial summary / WBS 1-17 | 7 | Planowany Przerób po REGIE | Planned capacity (REGIE) | 631386000 | 627086000 |  |  | 454 | I454 / AB454
Financial summary / WBS 1-17 | 8 | Korekta kosztowa wpływająca tylko na wynik |  | 0 | 0 |  |  | 457 | I457 / AB457
Financial summary / WBS 1-17 | 9 | Kwota narzutów kalkulacyjnych |  | 85237132.85 | 63492794.56 |  |  | 458 | I458 / AB458
Financial summary / WBS 1-17 | 10 | Kwota narzutów kalkulacyjnych po korekcie | Amount of imputed mark-ups after correction | 0 | 63492794.56 |  |  | 459 | I459 / AB459
Financial summary / WBS 1-17 | 11 | Alokacje - REGIE |  | 45080960.4 | 31178095.3778 |  |  | 475 | I475 / AB475
Financial summary / WBS 1-17 | 12 | EBT w PLN - po uwzględnieniu REGIE |  | 40156172.45 | 32314699.1822 |  |  | 477 | I477 / AB477
Financial summary / WBS 1-17 | 13 | % EBT bez revaluation |  | 0.0636 | 0.051532 |  |  | 478 | I478 / AB478
Financial summary / WBS 1-17 | 14 | EBT z Rewaluation |  | 40156172.45 | 54413234.3322 |  |  | 480 | I480 / AB480
Financial summary / WBS 1-17 | 15 | % EBT bez Contingency |  | 0.0636 | 0.086772 |  |  | 481 | I481 / AB481
Financial summary / WBS 1-17 | 16 | Wartość robót wykonywanych przez konsorcjantów |  | 0 | 0 |  |  | 488 | I488 / AB488
Financial summary / WBS 1-17 | 17 | Łączna wartość kontraktu (BBB + konsorcjanci) |  | 631386000 | 627086000 |  |  | 489 | I489 / AB489

## 08_Source_PORR_Production
Nota origine dati
Dati estratti dal file Budget in data/current: Budget.xlsm, sheet Włocławek Budget. La produzione mensile dichiarata PORR / budget monthly deriva dalla riga 12, colonne AM:BW; le intestazioni mese sono sulla riga 11.
Month | Value | Source cell | Source header cell
2025-12-01 00:00:00 | 6199140 | AM12 | AM11
2026-01-01 00:00:00 | 1209845.03 | AN12 | AN11
2026-02-01 00:00:00 | 4914057.77 | AO12 | AO11
2026-03-01 00:00:00 | 6224860.4689 | AP12 | AP11
2026-04-01 00:00:00 | 3080461.271 | AQ12 | AQ11
2026-05-01 00:00:00 | 10298268.1992 | AR12 | AR11
2026-06-01 00:00:00 | 24920618.4908 | AS12 | AS11
2026-07-01 00:00:00 | 11044595.675 | AT12 | AT11
2026-08-01 00:00:00 | 12651060.2408 | AU12 | AU11
2026-09-01 00:00:00 | 16840968.4786 | AV12 | AV11
2026-10-01 00:00:00 | 21259070.9007 | AW12 | AW11
2026-11-01 00:00:00 | 17153971.6389 | AX12 | AX11
2026-12-01 00:00:00 | 19773194.8502 | AY12 | AY11
2027-01-01 00:00:00 | 24861930.3933 | AZ12 | AZ11
2027-02-01 00:00:00 | 27968549.5048 | BA12 | BA11
2027-03-01 00:00:00 | 35342841.7608 | BB12 | BB11
2027-04-01 00:00:00 | 30823036.8911 | BC12 | BC11
2027-05-01 00:00:00 | 32016185.0583 | BD12 | BD11
2027-06-01 00:00:00 | 26848740.9669 | BE12 | BE11
2027-07-01 00:00:00 | 23300575.3162 | BF12 | BF11
2027-08-01 00:00:00 | 17197990.1163 | BG12 | BG11
2027-09-01 00:00:00 | 22446419.5511 | BH12 | BH11
2027-10-01 00:00:00 | 10601806.8521 | BI12 | BI11
2027-11-01 00:00:00 | 8350089.7725 | BJ12 | BJ11
2027-12-01 00:00:00 | 24637776.5005 | BK12 | BK11
2028-01-30 00:00:00 | 5817816.9662 | BL12 | BL11
2028-02-01 00:00:00 | 3279069.2332 | BM12 | BM11
2028-03-01 00:00:00 | 2859802.3872 | BN12 | BN11
2028-04-01 00:00:00 | 308626.9264 | BO12 | BO11
2028-05-01 00:00:00 | 3335488.4409 | BP12 | BP11
2028-06-01 00:00:00 | 966685.0738 | BQ12 | BQ11
2028-07-01 00:00:00 | 0 | BR12 | BR11
2028-08-01 00:00:00 | 0 | BS12 | BS11
2028-09-01 00:00:00 | 174000 | BT12 | BT11
2028-10-01 00:00:00 | 0 | BU12 | BU11
2028-11-01 00:00:00 | 0 | BV12 | BV11
2028-12-01 00:00:00 | 44750308.29 | BW12 | BW11

## 09_Source_Status_Mix
Nota origine e logica calcolo
Dati derivati dal file Procurement in data/current, sheet Procurement Schedule. PERIMETRO: solo ordini diretti, root group 1-7; sono esclusi 8 = indiretti/servizi e 9 = opportunities/risks. Colonne di riferimento: Q = stato procurement, S = Budget AK / budget aggiornato, T = valore contracted quando disponibile. Raggruppamento: Closed / Finalized / PCT approval = Ordinato; Planned = Da ordinare; tutti gli altri stati attivi = In negoziazione. Count = numero pacchetti nel gruppo; Value = somma economica del gruppo; % Value = Value gruppo / totale Value; % Count = Count gruppo / totale Count.
Status group | Count | Value | % Value | % Count
Ordinato | 42 | 266491549.72
In negoziazione | 45 | 105177552.26
Da ordinare | 124 | 133674322

## 10_Source_Orders_3M
Type | WBS | Package | Status | Date | Value | Buyer
Closed last 3 months | 8.1.3.3 | Open order - sanitary industry assortment ECd_39 | closed | 2026-02-24 | 30000
Closed last 3 months | 8.1.3.4 | Open order - sanitary industry assortment ECd_40 | closed | 2026-02-24 | 30000
Closed last 3 months | 1.2.2 | Detailed design: boiler support steel structure and equipment support structures | closed | 2026-02-27 | 943000
Closed last 3 months | 8.4.1.1 | Personal Occupational Health and Safety Equipment ECd_43 | closed | 2026-03-09 | 30000
Closed last 3 months | 8.3.1.2 | Generator rental ECd_44 | closed | 2026-03-15 | 23904
Closed last 3 months | 8.7.1.6 | Purchase of road signs ECd_42 | closed | 2026-03-15 | 2000
Closed last 3 months | 8.7.1.7 | Purchase of rubble for the construction of storage yards and work platforms ECd_45 | closed | 2026-03-15 | 83200
Closed last 3 months | 2.11.5.3 | Concrete slab installation on the ground | closed | 2026-03-25 | 1735392.78 | Agnieszka Zając
Closed last 3 months | 2.14.2.2 | External road - aggregate delivery ECd_46 | closed | 2026-03-25 | 134400 | Agnieszka Zając
Closed last 3 months | 2.4.1 | Insulation - work | closed | 2026-03-25 | 733045.25 | Agnieszka Zając
Closed last 3 months | 2.5.1.3 | Construction of reinforced concrete foundations and underground structures | closed | 2026-03-25 | 5276959.37 | Agnieszka Zając
Closed last 3 months | 2.5.2.1 | Reinforced concrete structure of the above-ground part of the B1 building - delivery and assembly of prefabricated elements | closed | 2026-03-25 | 16616880 | Jan Szczubiał
Closed last 3 months | 2.5.2.2.3 | Reinforced concrete structure of the above-ground part of the B3 building - delivery and assembly of prefabricated elements | closed | 2026-03-25 | 2115950 | Jan Szczubiał
Closed last 3 months | 2.5.2.2.4 | Reinforced concrete structure of the above-ground part of the other buildings | closed | 2026-03-25 | 708072.75 | Jan Szczubiał
Closed last 3 months | 2.6.2.1 | Precast reinforced concrete structure of facility B3 (change from steel structure compared to the acquisition stage) | closed | 2026-03-25 | 1004390 | Robert Klimczak
Closed last 3 months | 2.6.3.1 | Precast reinforced concrete structure of facility B4 (change from steel structure compared to the acquisition stage) | closed | 2026-03-25 | 246780 | Robert Klimczak
Closed last 3 months | 2.14.2.1 | External road- sub-base construction | closed | 2026-04-10 | 250640 | Agnieszka Zając
Closed last 3 months | 8.3.1.1 | Electricity Costs | closed | 2026-04-10 | 100000
Closed last 3 months | 8.7.1.4 | Construction of aggregate squares | closed | 2026-04-10 | 124700 | Agnieszka Zając
Closed last 3 months | 8.8.4 | Removing collisions related to site preparation and construction | closed | 2026-04-10 | 0
Closed last 3 months | 8.8.4.1 | Removal of existing reinforced concrete foundations in the vicinity of Building B2 | closed | 2026-04-10 | 50000
Closed last 3 months | 5.10.2 | Auxiliary crane and hoists for the maintenance of the steam turbine | closed | 2026-04-13 | 499000 | Magdalena Białorucka
Closed last 3 months | 5.2.1 | Overhead crane, grab and operator seat + Spare Grab | closed | 2026-04-13 | 8701000 | Magdalena Białorucka
Closed last 3 months | 5.11 | Stack | closed | 2026-04-15 | 1498200 | Magdalena Białorucka
Closed last 3 months | 5.4.1.1 | Boiler - pressure parts | closed | 2026-04-15 | 45990000 | Roger Gołombek
Closed last 3 months | 8.3.5 | Construction Waste Removal ECd_38 | closed | 2026-04-15 | 290720
Closed last 3 months | 2.3 | Drainage | closed | 2026-04-17 | 0
Closed last 3 months | 2.3.1 | Rental of an drainage pump ECd_49 | closed | 2026-04-17 | 4600
Closed last 3 months | 2.3.2 | Mobilization, installation and leasing of a wellpoint system including pumps ECd_50 | closed | 2026-04-17 | 70000
Closed last 3 months | 1.2.4 | Electrical & I/C detailed design | closed | 2026-04-22 | 1620000
Closed last 3 months | 3.1.1 | Delivery and installation of electrical equipment | closed | 2026-04-22 | 0 | Radosław Zdancewicz
Closed last 3 months | 3.1.1.1 | Delivery and installation of electrical equipment | closed | 2026-04-22 | 27750000 | Radosław Zdancewicz
Closed last 3 months | 3.2 | Teletechnical installations | closed | 2026-04-22 | 1750000 | Radosław Zdancewicz
Closed last 3 months | 3.4.1 | Automation system and instrumentation, communication networks and control room devices | closed | 2026-04-22 | 0 | Radosław Zdancewicz
Closed last 3 months | 3.4.1.1 | Automation system and instrumentation, communication networks and control room devices | closed | 2026-04-22 | 6280000 | Radosław Zdancewicz
Closed last 3 months | 6.4.1 | Extension of the guarantee and warranty period to 48 months for electrical, technical and I&C works | closed | 2026-04-22 | 350000 | Radosław Zdancewicz
Closed last 3 months | 5.10.1 | Steam turbine - gear box - generator. Including accessories: oil system, coolers, insulation, pipes and valves, control panel, protection panel, synchro system etc. | PCT/approval | 2026-04-25 | 0 | Magdalena Białorucka / Stanisław Rucki
Closed last 3 months | 5.8.1 | Chain conveyor under grate + Bottom ash extractor + Vibrating table / bulk screen | PCT/approval | 2026-04-25 | 1462000 | Stanisław Rucki
Closed last 3 months | 2.4.2 | Insulation – supply – Hydrostop ECd_51 | closed | 2026-04-30 | 31352
Closed last 3 months | 2.4.3 | Insulation – supply – foil, compound ECd_14 | closed | 2026-04-30 | 27600
Closed last 3 months | 8.1.1.1 | Purchase of temporary stairs ECd_48 | closed | 2026-04-30 | 17530
Closed last 3 months | 8.1.1.2 | Meals ECd_53 | closed | 2026-04-30 | 5711
Closed last 3 months | 8.7.1.8 | Installation of road markings and traffic signs ECd_52 | closed | 2026-04-30 | 920
Next orders 3 months | 5.13.7 | Demi water system including storage tank 100m3 and piping | planned | 2026-05-27 | 3010000 | Magdalena Białorucka
Next orders 3 months | 2.7 | Brick walls | planned | 2026-05-31 | 687451.25
Next orders 3 months | 5.2.2 | Trapdoors for grab maintenance | planned | 2026-05-31 | 81600
Next orders 3 months | 1.2.6.1 | Ducts design | enquiry | 2026-06-01 | 0
Next orders 3 months | 1.6 | Explosion hazard assessment | planned | 2026-06-01 | 120000
Next orders 3 months | 5.10.4 | Feed water tank and Deaerator | negotiation | 2026-06-01 | 1000000 | Magdalena Białorucka
Next orders 3 months | 5.9 | Bottom ash / slag valorization | planned | 2026-06-02 | 8271000 | Roger Gołombek
Next orders 3 months | 5.8.2 | Belt conveyors | planned | 2026-06-03 | 2347800 | Stanisław Rucki
Next orders 3 months | 5.10.3 | Air cooled condenser | enquiry | 2026-06-05 | 9000000 | Roger Gołombek
Next orders 3 months | 2.5.2.3 | Supply of reinforcing steel | enquiry | 2026-06-08 | 386500 | Agnieszka Zając
Next orders 3 months | 5.13.2 | Auxiliary fuel tank (light oil/diesel oil) | enquiry | 2026-06-16 | 200000 | Magdalena Białorucka
Next orders 3 months | 2.8.1 | Parapet | planned | 2026-06-17 | 82476 | Joanna Sawicka
Next orders 3 months | 2.8.10 | Soffit lining | planned | 2026-06-17 | 308662.24 | Joanna Sawicka
Next orders 3 months | 2.8.11 | Scaffolding | planned | 2026-06-17 | 77076 | Joanna Sawicka
Next orders 3 months | 2.8.12 | Safety system | planned | 2026-06-17 | 150018.35 | Joanna Sawicka
Next orders 3 months | 2.8.13 | Shutters | planned | 2026-06-17 | 107600.56 | Joanna Sawicka
Next orders 3 months | 2.8.2 | Steel-aluminum canopy | planned | 2026-06-17 | 120922.87 | Joanna Sawicka
Next orders 3 months | 2.8.3 | Aluminum-glass facade | planned | 2026-06-17 | 296487.48 | Joanna Sawicka
Next orders 3 months | 2.8.4 | ETICS | planned | 2026-06-17 | 122038.26 | Joanna Sawicka
Next orders 3 months | 2.8.5 | Flashings | planned | 2026-06-17 | 366598.98 | Joanna Sawicka
Next orders 3 months | 2.8.6 | Sheet metal cladding | planned | 2026-06-17 | 1172886.87 | Joanna Sawicka
Next orders 3 months | 2.8.7 | Sandwich panel cladding | enquiry | 2026-06-17 | 5792279.88 | Joanna Sawicka
Next orders 3 months | 2.8.8 | Fiber cement panel cladding | planned | 2026-06-17 | 241170.5 | Joanna Sawicka
Next orders 3 months | 2.8.9 | Substructures | planned | 2026-06-17 | 419580 | Joanna Sawicka
Next orders 3 months | 1.8 | Notification Bodies | planned | 2026-06-28 | 350000
Next orders 3 months | 2.5.1.4 | Execution of pre-wall insulation | negotiation | 2026-06-28 | 500000
Next orders 3 months | 5.4.3 | Fly ash extraction system for the boiler and conveyors | enquiry | 2026-06-29 | 4260000 | Roger Gołombek
Next orders 3 months | 1.2.6.2 | Piping design | planned | 2026-07-02 | 0
Next orders 3 months | 5.7.1 | SNCR DeNOx system including silo, pumps | planned | 2026-07-02 | 1090000 | Magdalena Białorucka
Next orders 3 months | 4.3.6 | Emergency showers and eye washers | planned | 2026-07-09 | 10000 | Magdalena Przeździak
Next orders 3 months | 5.10.11 | Heat exchangers 2 pcs., LP pre-heater, external economizer | planned | 2026-07-12 | 3242866 | Stanisław Rucki
Next orders 3 months | 1.2.3 | Detailed design: fire-fighting system | planned | 2026-07-15 | 260000
Next orders 3 months | 4.3.1 | Boiler room roof ventilators and wall shutters | planned | 2026-07-15 | 1500000 | Magdalena Przeździak
Next orders 3 months | 4.3.2 | HVAC for the technological buildings | planned | 2026-07-15 | 3107033 | Magdalena Przeździak
Next orders 3 months | 4.3.3 | HVAC for the other buildings | planned | 2026-07-15 | 1548256 | Magdalena Przeździak
Next orders 3 months | 3.4.3 | Emission monitoring system (CEMS) | planned | 2026-07-16 | 1960000 | Radosław Zdancewicz
Next orders 3 months | 4.1 | Deodorization system | enquiry | 2026-07-16 | 1009700 | Stanisław Rucki
Next orders 3 months | 5.13.3 | Light oil unloading installation with TDT documentation approval | planned | 2026-07-19 | 200000
Next orders 3 months | 5.10.12 | Stabilising pumps 2 x 100%, network pumps 3 x 50%, condensate pumps 2 x 100%, feed water pumps 3 pcs., cooling pumps | enquiry | 2026-07-28 | 5517325 | Stanisław Rucki
Next orders 3 months | 5.13.4 | Auxiliary fuel pumps (light oil/diesel oil), demi water pumps, other water pumps | planned | 2026-07-28 | 3337500 | Stanisław Rucki
Next orders 3 months | 2.11.1 | Painting | planned | 2026-07-31 | 669442.8 | Magdalena Białorucka
Next orders 3 months | 2.11.10 | Plasterboard wall, sandwich panel wall | planned | 2026-07-31 | 39026.75
Next orders 3 months | 2.11.11 | Glass wall | planned | 2026-07-31 | 75045.3
Next orders 3 months | 2.11.12 | Plastering | planned | 2026-07-31 | 1241084.64 | Magdalena Białorucka
Next orders 3 months | 2.11.13 | Carpet / polyamide | planned | 2026-07-31 | 87497.52
Next orders 3 months | 2.11.14 | Wall and column protection up to 2.5 m + hydrophobic protection | planned | 2026-07-31 | 186490.48
Next orders 3 months | 2.11.2 | Furniture | planned | 2026-07-31 | 631074 | Magdalena Białorucka
Next orders 3 months | 2.11.3 | Tiles | planned | 2026-07-31 | 498448.22 | Magdalena Białorucka
Next orders 3 months | 2.11.4 | Raised floor | planned | 2026-07-31 | 621907.75 | Magdalena Białorucka
Next orders 3 months | 2.11.5 | Concrete floor + screed | enquiry | 2026-07-31 | 610629.23
Next orders 3 months | 2.11.5.4 | Concrete flooring and screed with insulation | planned | 2026-07-31 | 0
Next orders 3 months | 2.11.6 | Microcement floor | planned | 2026-07-31 | 133705.44
Next orders 3 months | 2.11.7 | Resin floor | planned | 2026-07-31 | 655174.75 | Magdalena Białorucka
Next orders 3 months | 2.11.8 | Suspended ceilings | planned | 2026-07-31 | 220670.05
Next orders 3 months | 2.11.9 | Segmented sliding wall | planned | 2026-07-31 | 65014.1
Next orders 3 months | 2.12.1 | Passenger and good elevator | enquiry | 2026-07-31 | 415350 | Izabela Malarecka
Next orders 3 months | 2.12.2 | Passenger elevator | enquiry | 2026-07-31 | 98643.6 | Izabela Malarecka
Next orders 3 months | 2.13 | Weigh bridge | planned | 2026-07-31 | 551900 | Stanisław Rucki
Next orders 3 months | 5.14.2 | Mechanical installation of technological equipment | planned | 2026-07-31 | 1500000 | Stanisław Rucki
Next orders 3 months | 5.4.6 | Compensator between boiler and ECO | planned | 2026-07-31 | 129000
Next orders 3 months | 5.5 | Refractory | planned | 2026-07-31 | 3993000 | Magdalena Białorucka
Next orders 3 months | 4.2.2 | Firefighting water tank | enquiry | 2026-08-01 | 275700 | Magdalena Białorucka
Next orders 3 months | 5.13.1 | Compressors 2 x 50% + 1 x 50% | planned | 2026-08-01 | 1500000 | Roger Gołombek
Next orders 3 months | 4.3.5 | Sanitary water, connection to source, storage, pumping, underground and external distribution | planned | 2026-08-02 | 637613 | Magdalena Przeździak
Next orders 3 months | 4.3.7 | Sanitary waste water collection, treatment and connection to discharge point | planned | 2026-08-02 | 624272 | Magdalena Przeździak
Next orders 3 months | 4.3.8 | Waste water collection and connection to discharge point | planned | 2026-08-02 | 200969 | Magdalena Przeździak
Next orders 3 months | 4.3.9 | Rain water and snowmelt collection, treatment and connection to discharge point | planned | 2026-08-02 | 3359643 | Magdalena Przeździak
Next orders 3 months | 5.13.9 | Grate cooling system | planned | 2026-08-02 | 731000 | Magdalena Białorucka
Next orders 3 months | 2.6.4 | Steel structure of the staircase in the B1.4 facility (change from the reinforced concrete structure in relation to the acquisition stage) | planned | 2026-08-03 | 470146.23 | Robert Klimczak
Next orders 3 months | 3.4.2 | DCS System | planned | 2026-08-16 | 2752000 | Roger Gołombek
Next orders 3 months | 5.7.4 | Fly ash silos | planned | 2026-08-16 | 2000000 | Roger Gołombek
Next orders 3 months | 5.10.7 | Main cooler | planned | 2026-08-17 | 2000000 | Roger Gołombek
Next orders 3 months | 5.10.8 | Cooler tank, condensate tank | planned | 2026-08-17 | 1000000 | Roger Gołombek
Next orders 3 months | 5.13.11 | waste water treatment | planned | 2026-08-17 | 800000 | Roger Gołombek
Next orders 3 months | 5.4.5 | Chemical dosing for the boiler | planned | 2026-08-17 | 223600 | Magdalena Białorucka
Next orders 3 months | 5.10.9 | Water pressure stabilization system | negotiation | 2026-08-18 | 350000

## 11_Source_S_Curve_Data
Nota origine e logica calcolo
La Curva S deriva dal dashboard payload rigenerato dai file Excel in data/current. Procurement schedule cumulativo: somma mensile/cumulata dei valori Updated Budget / Budget AK del Procurement Schedule secondo le date procurement. Budget Baseline cumulativo: curva mensile/cumulata letta dal Budget, riga 12, colonne AM:BW. Ordini contrattualizzati cumulativo: somma mensile/cumulata dei valori Contracted secondo le date di chiusura/contrattualizzazione disponibili nel Procurement Schedule.
Month | Label | Procurement monthly | Procurement cumulative | Budget monthly | Budget cumulative | Contracted monthly | Contracted cumulative | Current marker
2025-12 | dic-2025 | 6583222.55 | 6583222.55 | 6199140 | 6199140 | 0 | 0
2026-01 | gen-2026 | 9354454.44 | 15937676.99 | 1209845.03 | 7408985.03 | 0 | 0
2026-02 | feb-2026 | 15217247.88 | 31154924.87 | 7794586.93 | 15203571.96 | 0 | 0
2026-03 | mar-2026 | 17664420.45 | 48819345.32 | 12423640.08 | 27627212.04 | 0 | 0
2026-04 | apr-2026 | 32610741.4 | 81430086.72 | 11336449.17 | 38963661.21 | 0 | 0
2026-05 | mag-2026 | 25126114.16 | 106556200.88 | 13624888.02 | 52588549.23 | 0 | 0 | Current
2026-06 | giu-2026 | 50027765.79 | 156583966.67 | 14910518.13 | 67499067.36 | 0 | 0
2026-07 | lug-2026 | 44614937.25 | 201198903.92 | 15028245.62 | 82527312.98 | 0 | 0
2026-08 | ago-2026 | 31388394.81 | 232587298.73 | 24539477.12 | 107066790.1 | 0 | 0
2026-09 | set-2026 | 28927011.96 | 261514310.69 | 31216463.12 | 138283253.22 | 0 | 0
2026-10 | ott-2026 | 26801511.96 | 288315822.65 | 27608192.85 | 165891446.07 | 0 | 0
2026-11 | nov-2026 | 23020290.23 | 311336112.88 | 26540967.3 | 192432413.37 | 0 | 0
2026-12 | dic-2026 | 19232675.49 | 330568788.37 | 28846792.41 | 221279205.78 | 0 | 0
2027-01 | gen-2027 | 19092679.12 | 349661467.49 | 27022580.63 | 248301786.41 | 0 | 0
2027-02 | feb-2027 | 48251591.24 | 397913058.73 | 28325747.31 | 276627533.72 | 0 | 0
2027-03 | mar-2027 | 16687397.24 | 414600455.97 | 35039986.08 | 311667519.8 | 0 | 0
2027-04 | apr-2027 | 14237428.39 | 428837884.36 | 33822381.41 | 345489901.21 | 0 | 0
2027-05 | mag-2027 | 7430822.59 | 436268706.95 | 25897922.24 | 371387823.45 | 0 | 0
2027-06 | giu-2027 | 7430822.59 | 443699529.54 | 28095849.06 | 399483672.51 | 0 | 0
2027-07 | lug-2027 | 9132146.75 | 452831676.29 | 20736784.02 | 420220456.53 | 0 | 0
2027-08 | ago-2027 | 9132146.76 | 461963823.05 | 17315684.93 | 437536141.46 | 0 | 0
2027-09 | set-2027 | 9132146.75 | 471095969.8 | 15763709.59 | 453299851.05 | 0 | 0
2027-10 | ott-2027 | 8530301.03 | 479626270.83 | 12623620.61 | 465923471.66 | 0 | 0
2027-11 | nov-2027 | 6894099.11 | 486520369.94 | 10976891.07 | 476900362.73 | 0 | 0
2027-12 | dic-2027 | 5164130.92 | 491684500.86 | 11889923.67 | 488790286.4 | 0 | 0
2028-01 | gen-2028 | 5049870.1 | 496734370.96 | 0 | 488790286.4 | 0 | 0
2028-02 | feb-2028 | 3301596.76 | 500035967.72 | 1910542.1 | 490700828.5 | 0 | 0
2028-03 | mar-2028 | 3301596.75 | 503337564.47 | 2167008.58 | 492867837.08 | 0 | 0
2028-04 | apr-2028 | 3285685.65 | 506623250.12 | 758299.79 | 493626136.87 | 0 | 0
2028-05 | mag-2028 | 3285685.64 | 509908935.76 | 3740876.04 | 497367012.91 | 0 | 0
2028-06 | giu-2028 | 3285685.65 | 513194621.41 | 1069040.53 | 498436053.44 | 0 | 0
2028-07 | lug-2028 | 0 | 513194621.41 | 454545.46 | 498890598.9 | 0 | 0
2028-08 | ago-2028 | 0 | 513194621.41 | 454545.45 | 499345144.35 | 0 | 0
2028-09 | set-2028 | 0 | 513194621.41 | 628545.46 | 499973689.81 | 0 | 0
2028-10 | ott-2028 | 0 | 513194621.41 | 0 | 499973689.81 | 0 | 0
2028-11 | nov-2028 | 0 | 513194621.41 | 0 | 499973689.81 | 0 | 0
2028-12 | dic-2028 | 0 | 513194621.41 | 0 | 499973689.81 | 0 | 0